## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Bullhorn CRM
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
No | Date | Category | Customer Questions | Sample Data | Issue Type | Can be fixed? | Fix Stage | Fix Method | Next Step? | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference
1 | 2018-10-08 | CANDIDATES | Please enter your Review issues or questions here | Please provide an exact DATA example here so we can reproduce the issue.
| 2018-10-23 | COMPANIES | I added a file on Companies - but it isnt simply visable after adding - I need to go through the process of adding another file for it to be visible. Is that the standard setting? |  | PRODUCT LIMITATION | NO | N/A | N/A | AT: Next move to decide | 2018-10-24 | AT: Yes the company has folder and was intended to store Terms and Conditions type of Documents. But we would change this in the future as part of the Roadmap to make it the same view as other data sets. So during the migration, if we submit the file under the Companies Files, once we updated the view, it would show up as it would look like in the Candidate Files. But the timeline of this has not been decided.
| 2018-10-23 | COMPANIES | See field 24 - We have 2 lables for accounts "active" and "Archived" - are you able to archive accouts - please advise - I will add this question in Q&A too |  | PRODUCT LIMITATION | YES | REVIEW | STANDARD SCRIPT | AT: Next move to decide which option to take | 2018-10-24 | AT: We don't have "Archived" state under the company. But we can do the following options: 1. Create Custom Field and mark the company as "Archived" on this field. You can search all archived company thru this Custom Field but the Company would still be visible and searchable. 2. We can move the Company to the status of "No Open Jobs or Will Not Work With Us" status under the 1st Chevron. This way, when you open the Company, you will see it on the Chevron. They wil still be available under the Search though.
| 2018-10-24 | CONTACTS | There are a lot of "tasks" in the contact fields mapping. And looking at BH they "seem" to be connecting to the jobs that are linked to the managers. Yet you have it defaulting to a "activity" which for me seems to be a note. The link between the hiring manager and the job needs to be maitained - can you please advise. |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-25 | AT: This can be done. The link to each Contacts, Candidates and Job records will be showing in the activities comments. This means the tasks will be linked to each Data Sets and will appear accordingly in the data sets that it was being referenced.
| 2018-10-24 | CANDIDATES | Please see candidates / field 49 - re archived / deleted canddiates |  | REQUIREMENTS | YES | PRODUCTION | CUSTOM SCRIPT |  | 2018-10-25 | AT: This can be done. The archived / deleted Candidates will be migrated as "soft deleted" candidates. In search, by default they cannot be searched. But if you turn the filter to also search the deleted candidates, you can still search them.
| 2018-10-24 | CANDIDATES | EMAIL field - 130 - can you please confirm if this is the email history, given you have listed it as migrating to activity comments. Is this where emails are stored or is it a special migration on the DB import? |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-25 | AT: Yes the email will show up in the Activities Comments including all the body text. But the attachments of the email won't be migrated.
| 2018-10-26 | JOBS | Field 17 - the Job description field is a text field and has very bad formatting - I would like to use attachment as public JD - is this possible? |  | REQUIREMENTS | YES | PRODUCTION | CUSTOM SCRIPT |  | 2018-10-25 | AT: The Public Job Description is actually HTML enabled text box. This means, if your JD is loaded with HTML contents, we can retain the formatting so it looks the same. If you prefer to save this to an external HTML file, it is possible as well but we would need to generate a custom script for this. Please let me know which one you prefer ?
| 2018-10-26 | JOBS | I would like to not transfer the tasks - as we need a clear DB and will upload and candidates we have in play - does that make sense? |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-26 | AT: Please clarify if you don't want to migrate all tasks related to the Jobs Data Set or all tasks related to all data sets ? We can do both.
| 2018-10-26 | JOBS | I would like to make all jobs closed and we can open live jobs - however status of "placement" shoudl be kept - as such I have left the jobs field quite minimal just linking to the hiring managers and companies - does this make sense as good practice? Given my goal is to have all the job info searchable - but also clean for the new system |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-26 | AT: Yes this is possible. And yes it is the best practice because then you can start activating the jobs that you are currently working on. Each jobs will be linking to the Company and Contacts as well.
| 2018-10-26 | JOBS | Again - fields industry and category - I want to use in VC but we never used well in the past so dont want to migrate - will that cause issues? |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-26 | AT: This is no problem. The best practice is to leave the fields that you don't use so it won't create noise when they migrated across. In Vincere, we will load the default industries and functional expertise values that is also shared by linkedin. So once you moved over, you can start utilizing these tags.
| 2018-10-26 | JOBS | See field 24 This field was used badly before - does transferring make sense given only 10% will have a salary number? If not - please make no and we will start afresh |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-26 | AT: No, it doesn't make sense to migrate them. It is better to start fresh as Vincere has a detailed calculation on the Salary info and they would be projected to the Dashboard as forecasted fee.
| 2018-10-26 | OTHERS | See Job application mapping "placed" - and please advise best practice. |  | REQUIREMENTS | YES | REVIEW | STANDARD SCRIPT |  | 2018-10-26 | AT: This can be done. We will migrate the PLACED state to the CANDIDATE Brief. We will not migrate the JOB APPLICATIONS records. This means you will see 0 records on the JOB APPLICATIONS under SHORTLISTED, FIRST INTERVIEW, 2nd+ INTERVIEW, OFFERED and PLACED.

## 1. Company Fields Mapping
Next Move to Vincere Fields Mapping (COMPANY) |  |  | Status : | Approved |  |  |  | 3 Custom Scripts are inclusive to the Data Migration Project
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn DB Tablename | Bullhorn CRM DB Fieldname | Bullhorn CRM UI Fieldname | Required ? | Vincere Field | CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client | clientCorporationID | Company # | YES | Company External ID | YES | GN: They need a number - but doenst need to be BH one AT: Yes we have the number auto generated. We will still be migrating BH ID for support reference. So is it ok to still bring this BH ID to Brief as well so if there is issue, we can quickly query it ? GN: Yes NP | STANDARD | REVIEW
2 | Client | address1 | Address | YES | Location Address Location Name | YES |  | STANDARD | REVIEW
3 | Client | address2 |  | YES | Location Address Location Name | YES |  | STANDARD | REVIEW
4 | Client | city | City | YES | Location Address Location Name Location Town / City Default City=Tokyo | YES | GN: Can you default all to Tokyo? AT: Yes we can default all to Tokyo | STANDARD | REVIEW
5 | Client | companyDescription | Company Description | YES | FILES > .HTML | NO | GN: Please create a formatted / editable file for each record - so formatting is retained. If possible change to "Company overview" rather than company description AT: Yes this is possible. We would require a custom script to convert this to .HTML file and upload it to the Company FILES section. | CUSTOM | PRODUCTION
6 | Client | companyURL | Company Website | YES | Website | YES |  | STANDARD | REVIEW
7 | Client | countryID | Country | YES | Location Address Location Name Location Country Default Country = Japan | YES | GN: Please default all to Japan AT: Yes this is possble. We will default Country to Japan. | STANDARD | REVIEW
8 | Client | CustomComponent1 | Send Out Instructions | YES | CUSTOM FIELD > Send Out Instructions | NO | GN: Create Custom field. AT: No Problem | CUSTOM | PRODUCTION
9 | Client | CustomComponent2 | Custom Component 2 | NO | Brief | YES |  | STANDARD | REVIEW
10 | Client | CustomComponent3 | Custom Component 3 | NO | Brief | YES |  | STANDARD | REVIEW
11 | Client | customTextBlock1 | Send Out Instructions | NO | Brief | YES | GN: This is a duplicate field and we use the one above (BH Customcomponent1 so not needed | STANDARD | REVIEW
12 | Client | dateAdded | Date Added | YES | Brief | YES | GN: Please list before sendout instructions AT: We will append this to the first value on the Brief. Sendout Instruction won't be appended to Brief but to the Custom Field. | STANDARD | REVIEW
13 | Client | dateLastModified | Date Last Modified | NO | Brief | YES |  | STANDARD | REVIEW
14 | Client | fax | Fax | YES | Fax | YES |  | STANDARD | REVIEW
15 | Client | fullAddress | Address | NO | N/A | YES | VC: Duplicated with Location address fields above. Will not be migrated. | STANDARD | REVIEW
16 | Client | name | Company Name | YES | Company name | YES |  | STANDARD | REVIEW
17 | Client | notes | Company Overview | NO | Brief | YES |  | STANDARD | REVIEW
18 | Client | ownership | Ownership | YES | Company Owners | YES |  | STANDARD | REVIEW
19 | Client | phone | Main Phone | YES | Company Phone | YES |  | STANDARD | REVIEW
20 | Client | revenue | revenue | NO | Brief | YES |  | STANDARD | REVIEW
21 | Client | status | Status | NO | Brief | YES | GN : We have 2 lables for accounts "active" and "Archived" - are you able to archive accouts - please advise - I will add this question in Q&A too AT: We don't have "Archived" state under the company. But we can do the following options: 1. Create Custom Field and mark the company as "Archived" on this field. You can search all archived company thru this Custom Field but the Company would still be visible and searchable. 2. We can move the Company to the status of "No Open Jobs or Will Not Work With Us" status under the 1st Chevron. This way, when you open the Company, you will see it on the Chevron. They wil still be available under the Search though. GN: Lets go for 2 - and make it "no open jobs" thats simple | STANDARD | REVIEW
22 | Client | yearFounded | Year Founded | YES | Brief | YES |  | STANDARD | REVIEW
23 | Client | zip | Post Code | YES | Location Address Location Name Location Postal (ZIP) Code | YES |  | STANDARD | REVIEW
24 | Company File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
25 | Company File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migration Stage) and not the Review Site.

## 2. Contact Fields Mapping
Bullhorn CRM to Vincere Fields Mapping (CONTACTS) |  |  |  | Status : | Approved |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn DB Tablename | Bullhorn CRM DB Field Name | Bullhorn CRM UI Field Name | Required ? | Vincere Field | CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client Contact | userID | ID | YES | Contact External ID | YES | GN: I assume a new ID will be allocated - we dont use the numbers now so a new number is no problem AT: We will use BH ID as reference purposes so we will still be migrating this to the Brief. Is it ok ? GN: No problem | STANDARD | REVIEW
2 | Client Contact | address1 | Address | YES | Current Location Address Location Name | YES |  | STANDARD | REVIEW
3 | Client Contact | address2 |  | YES | Current Location Address Location Name | YES |  | STANDARD | REVIEW
4 | Client Contact | city | City | YES | Current Location Address Location Name Location Town / City | YES |  | STANDARD | REVIEW
5 | Client Contact | clientCorporationID | Company | YES | Company External ID | YES |  | STANDARD | REVIEW
6 | Client Contact | comments | General Contact Comments | YES | Brief | YES |  | STANDARD | REVIEW
7 | Client Contact | countryID | Country | YES | Current Location Address Location Name Location Country | YES |  | STANDARD | REVIEW
8 | Client Contact | CustomComponent1 | Custom Component 1 | NO | Brief | YES |  | STANDARD | REVIEW
9 | Client Contact | CustomComponent2 | Custom Component 2 | NO | Brief | YES |  | STANDARD | REVIEW
10 | Client Contact | CustomComponent3 | Custom Component 3 | NO | Brief | YES |  | STANDARD | REVIEW
11 | Client Contact | division | Department | YES | Department | YES |  | STANDARD | REVIEW
12 | Client Contact | email | Email 1 | YES | Primary Email | YES |  | STANDARD | REVIEW
13 | Client Contact | email2 | Email 2 | YES | Personal Email | YES |  | STANDARD | REVIEW
14 | Client Contact | fax | Fax | NO | Brief | YES |  | STANDARD | REVIEW
15 | Client Contact | firstName | Contact Name | YES | First Name | YES |  | STANDARD | REVIEW
16 | Client Contact | fullAddress | Address | NO | N/A | YES | VC: Duplicated with the location fields above. Will not be migrated. | STANDARD | REVIEW
17 | Client Contact | lastName | Contact Name | YES | Last Name | YES |  | STANDARD | REVIEW
18 | Client Contact | mobile | Mobile Phone | YES | Mobile Phone | YES |  | STANDARD | REVIEW
19 | Client Contact | occupation | Title | YES | Job Title | YES |  | STANDARD | REVIEW
20 | Client Contact | phone | Direct Phone | YES | Primary Phone | YES |  | STANDARD | REVIEW
21 | Client Contact | phone2 | Other Phone | YES | Work Phone | YES |  | STANDARD | REVIEW
22 | Client Contact | recruiterUserID | Owner | YES | Contact Owners | YES |  | STANDARD | REVIEW
23 | Client Contact | reportToUserID | Reports to | NO | Brief | YES |  | STANDARD | REVIEW
24 | Client Contact | revenue | revenue | NO | Brief | YES |  | STANDARD | REVIEW
25 | Client Contact | secondaryOwners | Secondary Owners | YES | Contact Owners | YES |  | STANDARD | REVIEW
26 | Client Contact | state | State | YES | Current Location Address Location Name Location State | YES |  | STANDARD | REVIEW
27 | Client Contact | status | Status | YES | Brief | YES |  | STANDARD | REVIEW
28 | Client Contact | zip | Post Code | YES | Current Location Address Location Name Location Postal (ZIP) Code | YES |  | STANDARD | REVIEW
29 | Contact File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
30 | Contact File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
31 | Distribution List | members | Members | YES | DISTRIBUTION LIST | NO |  | CUSTOM | PRODUCTION
32 | Distribution List | name | Name | YES | DISTRIBUTION LIST | NO |  | CUSTOM | PRODUCTION
33 | Note | action | Action | NO | Activities Comments | YES |  | STANDARD | REVIEW
34 | Note | commentingUserID | Author | NO | Activities Comments | YES |  | STANDARD | REVIEW
35 | Note | comments | Comments | NO | Activities Comments | YES |  | STANDARD | REVIEW
36 | Note | dateAdded | Date Added | YES | Activities Comments | YES |  | STANDARD | REVIEW
37 | Note | userID | About | NO | Activities Comments | YES |  | STANDARD | REVIEW
38 | Task | candidateUserID | Candidate | NO | Activities Comments | YES | GN: Please advise on tasks and what they relate too as per question on the Q&A - they seem to link to jobs assigned to a client contact and of course that link should remain - but Im askign the question as you have assigned it as an activity comment - and Im not sure how that fits. AT: Tasks will be migrated to Activities Comments. All related data sets will still be linked on the Activities Comments. This is covered under our Standard Script. GN: I cannot see where the tasks link to the contact and so I have left it out for now - as Id like a clean record if we dont need it. I have only copied the link to job posting ID. Note that the fields I see on bullhorn is in the attached file but it doesnt seem to relate. As such I assume we can change it after first import if in fact something is missing? AT: No problem. We will check your tasks settings and see how the records being linked. If only Job ID is linked, then the tasks will only be linked to the Jobs. | STANDARD | REVIEW
39 | Task | childTaskOwners | Assigned To | NO | Activities Comments | YES | See question above for fields down to 52 | STANDARD | REVIEW
40 | Task | clientUserID | Contact | NO | Activities Comments | YES |  | STANDARD | REVIEW
41 | Task | dateBegin | Due Date And Time | NO | Activities Comments | YES |  | STANDARD | REVIEW
42 | Task | dateEnd | Date End | NO | Activities Comments | YES |  | STANDARD | REVIEW
43 | Task | description | Description | NO | Activities Comments | YES |  | STANDARD | REVIEW
44 | Task | isPrivate | Visibility | NO | Activities Comments | YES |  | STANDARD | REVIEW
45 | Task | jobPostingID | Job | YES | Activities Comments | YES |  | STANDARD | REVIEW
46 | Task | leadUserID | Lead | NO | Activities Comments | YES |  | STANDARD | REVIEW
47 | Task | notificationMinutes | Reminder | NO | Activities Comments | YES |  | STANDARD | REVIEW
48 | Task | opportunityJobPostingID | Opportunity | NO | Activities Comments | YES |  | STANDARD | REVIEW
49 | Task | placementID | Placement | YES | Activities Comments | YES |  | STANDARD | REVIEW
50 | Task | priority | Priority | NO | Activities Comments | YES |  | STANDARD | REVIEW
51 | Task | subject | Subject | NO | Activities Comments | YES |  | STANDARD | REVIEW
52 | Task | type | Type | NO | Activities Comments | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 4. Job Fields Mapping
Bullhorn CRMto Vincere Fields Mapping (JOB) |  |  | Status : | Approved |  |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn CRM Section | Bullhorn CRM DB Field Name | Bullhorn CRM UI Field Name | Required ? | Vincere Field | Core Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Job Posting | jobPostingID | ID | YES | Job External ID | YES | GN: This is the searchable number we use to locate jobs. I would like to move to using VC's job number. | STANDARD | REVIEW
2 | Job Posting | address | Address | NO | Note | YES | VC: In VC, job location is taken from the Contact and Company's location. For this reason, BH Job Address will be migrated to NOTE. | STANDARD | REVIEW
3 | Job Posting | benefits | Benefits | NO | Note | YES |  | STANDARD | REVIEW
4 | Job Posting | businessSectorID | Industry | NO | INDUSTRY | NO |  | CUSTOM | PRODUCTION
5 | Job Posting | categoryID | Category | NO | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
6 | Job Posting | certifications | Certification Requirements | NO | Internal Job Description | YES |  | STANDARD | REVIEW
7 | Job Posting | city | City | NO | Note | YES |  | STANDARD | REVIEW
8 | Job Posting | clientBillRate | Client Bill Rate | NO | Note | YES |  | STANDARD | REVIEW
9 | Job Posting | clientCorporationID | Client Company | YES | Company External ID | YES |  | STANDARD | REVIEW
10 | Job Posting | clientUserID | Contact | YES | Contact External ID | YES |  | STANDARD | REVIEW
11 | Job Posting | countryID | Country | NO | Note | YES |  | STANDARD | REVIEW
12 | Job Posting | CustomComponent1 | Custom Component 1 | NO | Note | YES |  | STANDARD | REVIEW
13 | Job Posting | CustomComponent2 | Custom Component 2 | NO | Note | YES |  | STANDARD | REVIEW
14 | Job Posting | CustomComponent3 | Custom Component 3 | NO | Note | YES |  | STANDARD | REVIEW
15 | Job Posting | dateEnd | Scheduled End | YES | Closed Date | YES | GN: We have never used schedule end - so many of our jobs are open that should be closed AT: We will fill the closed date with yesterday's date so the job will be set all to closed by default. You would have to extend this date so it could be re-opened. | STANDARD | REVIEW
16 | Job Posting | degreeList | Degree Requirements | NO | Internal Job Description | YES |  | STANDARD | REVIEW
17 | Job Posting | description | Job Description | NO | Public Job Description | YES | GN - the Job description field is a text field and has very bad formatting - I would like to use attachment as public JD - is this possible? AT: The Public Job Description is actually HTML enabled text box. This means, if your JD is loaded with HTML contents, we can retain the formatting so it looks the same. If you prefer to save this to an external HTML file, it is possible as well but we would need to generate a custom script for this. Please let me know which one you prefer ? | STANDARD | REVIEW
18 | Job Posting | employmentType | Employment Type | NO | Job Type | YES |  | STANDARD | REVIEW
19 | Job Posting | fullAddress | Address | NO | Note | YES |  | STANDARD | REVIEW
20 | Job Posting | isInterviewRequired | Interview Required? | NO | Note | YES |  | STANDARD | REVIEW
21 | Job Posting | isOpen | Open/Closed | YES | Open Date Closed Date | YES | VC: If the status is CLOSED, we will set the Closed Date to be in the past so the status of the job would be automatically closed in VC. GN: All jobs should be set to closed - as we have never done before and I want to refresh | STANDARD | REVIEW
22 | Job Posting | linkedJobPostingID | Linked Job Posting ID | NO | Note | YES |  | STANDARD | REVIEW
23 | Job Posting | numOpenings | # of Openings | NO | Headcount | YES |  | STANDARD | REVIEW
24 | Job Posting | salary | Salary | YES | Annual Salary | YES | GN: This field was used badly before - does transferring make sense given only 10% will have a salary number? If not - please make no and we will start afresh AT: No, it doesn't make sense to migrate them. It is better to start fresh as Vincere has a detailed calculation on the Salary info and they would be projected to the Dashboard as forecasted fee. | STANDARD | REVIEW
25 | Job Posting | salaryUnit | Pay Rate | NO | Pay Rate | YES | VC: Applicable to Contract Job Only. Will not be migrated for Permanent Job. | STANDARD | REVIEW
26 | Job Posting | skillID | Required Skills | NO | SUB FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
27 | Job Posting | skills | Keywords | YES | skills | YES |  | STANDARD | REVIEW
28 | Job Posting | startDate | Start Date | NO | Open Date | YES |  | STANDARD | REVIEW
29 | Job Posting | state | State | NO | Note | YES |  | STANDARD | REVIEW
30 | Job Posting | status | Status | NO | Note | YES |  | STANDARD | REVIEW
31 | Job Posting | title | Job Title | YES | Job Title | YES |  | STANDARD | REVIEW
32 | Job Posting | type | Priority | NO | Note | YES |  | STANDARD | REVIEW
33 | Job Posting | userID | Owner | NO | Job Owners | YES |  | STANDARD | REVIEW
34 | Job Posting | willSponsor | Visa Sponsorship Provided | NO | Internal Job Description | YES |  | STANDARD | REVIEW
35 | Job Posting | yearsRequired | Minimum Experience | NO | Internal Job Description | YES |  | STANDARD | REVIEW
36 | Job Posting | zip | Post Code | NO | Note | YES |  | STANDARD | REVIEW
37 | Note | action | Action | NO | Activities Comments | YES |  | STANDARD | REVIEW
38 | Note | commentingUserID | Author | NO | Activities Comments | YES |  | STANDARD | REVIEW
39 | Note | comments | Comments | NO | Activities Comments | YES |  | STANDARD | REVIEW
40 | Note | dateAdded | Date Added | NO | Activities Comments | YES |  | STANDARD | REVIEW
41 | Note | userID | About | NO | Activities Comments | YES |  | STANDARD | REVIEW
42 | Task | candidateUserID | Candidate | NO | Activities Comments | YES |  | STANDARD | REVIEW
43 | Task | childTaskOwners | Assigned To | NO | Activities Comments | YES |  | STANDARD | REVIEW
44 | Task | clientUserID | Contact | NO | Activities Comments | YES |  | STANDARD | REVIEW
45 | Task | dateBegin | Due Date And Time | NO | Activities Comments | YES |  | STANDARD | REVIEW
46 | Task | dateEnd | Date End | NO | Activities Comments | YES |  | STANDARD | REVIEW
47 | Task | description | Description | NO | Activities Comments | YES |  | STANDARD | REVIEW
48 | Task | isPrivate | Visibility | NO | Activities Comments | YES |  | STANDARD | REVIEW
49 | Task | jobPostingID | Job | NO | Activities Comments | YES |  | STANDARD | REVIEW
50 | Task | leadUserID | Lead | NO | Activities Comments | YES |  | STANDARD | REVIEW
51 | Task | notificationMinutes | Reminder | NO | Activities Comments | YES |  | STANDARD | REVIEW
52 | Task | opportunityJobPostingID | Opportunity | NO | Activities Comments | YES |  | STANDARD | REVIEW
53 | Task | placementID | Placement | NO | Activities Comments | YES |  | STANDARD | REVIEW
54 | Task | priority | Priority | NO | Activities Comments | YES |  | STANDARD | REVIEW
55 | Task | recurrenceDayBits | Recurrence Day Bits | NO | Activities Comments | YES |  | STANDARD | REVIEW
56 | Task | recurrenceFrequency | Recurrence Frequency | NO | Activities Comments | YES |  | STANDARD | REVIEW
57 | Task | recurrenceMax | Recurrence Max | NO | Activities Comments | YES |  | STANDARD | REVIEW
58 | Task | recurrenceMonthBits | Recurrence Month Bits | NO | Activities Comments | YES |  | STANDARD | REVIEW
59 | Task | recurrenceStyle | Recurrence Style | NO | Activities Comments | YES |  | STANDARD | REVIEW
60 | Task | recurrenceType | Recurrence Type | NO | Activities Comments | YES |  | STANDARD | REVIEW
61 | Task | subject | Subject | NO | Activities Comments | YES |  | STANDARD | REVIEW
62 | Task | type | Type | NO | Activities Comments | YES |  | STANDARD | REVIEW
63 | Task | userID | Owner | NO | Activities Comments | YES |  | STANDARD | REVIEW
64 | Job Order File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
65 | Job Order File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 3. Candidate Fields Mapping
Bullhorn CRM to Vincere Fields Mapping (Candidates) |  |  | Status : | Approved |  |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn CRM Section | Bullhorn CRM DB Field | Bullhorn CRM UI Field | Required ? | Vincere Field | Core Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Candidate | userID | ID | YES | Candidate External ID BRIEF | YES |  | STANDARD | REVIEW
2 | Candidate | address1 | Address | YES | Location Address Location Name | YES |  | STANDARD | REVIEW
3 | Candidate | address2 |  | YES | Location Address Location Name | YES |  | STANDARD | REVIEW
4 | Candidate | businessSectorID | Industry | YES | INDUSTRY | NO |  | CUSTOM | PRODUCTION
5 | Candidate | categoryID | Category | YES | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
6 | Candidate | city | City | YES | Location Address Location Name Location Town / City | YES |  | STANDARD | REVIEW
7 | Candidate | comments | General Candidate Comments | YES | BRIEF | YES |  | STANDARD | REVIEW
8 | Candidate | companyName | Current Company | YES | Current Employer | YES |  | STANDARD | REVIEW
9 | Candidate | countryID | Country | YES | Location Address Location Name Location Country | YES |  | STANDARD | REVIEW
10 | Candidate | CustomComponent1 | Custom Component 1 | NO | BRIEF | YES |  | STANDARD | REVIEW
11 | Candidate | CustomComponent2 | Custom Component 2 | NO | BRIEF | YES |  | STANDARD | REVIEW
12 | Candidate | CustomComponent3 | Custom Component 3 | NO | BRIEF | YES |  | STANDARD | REVIEW
13 | Candidate | customInt1 | ABN# | NO | BRIEF | YES |  | STANDARD | REVIEW
14 | Candidate | customTextBlock1 | Additional Skills | YES | SKILLS | YES |  | STANDARD | REVIEW
15 | Candidate | dateAvailable | Date Available | NO | BRIEF | YES |  | STANDARD | REVIEW
16 | Candidate | description | Resume | NO | BRIEF | YES | VC: If this is the text version of the resume file, we won't be migrating it because it will be duplicated with the text that VC would be rendering as well from the same Resume file. GN: Yes it is the info that BH has pulled out to be viewable - in a serach. Its the most important field for the BH DB - so as long as you are pulling out the info using your tools then its fine - Ill leave to you and have set as "no" only due to your comment | STANDARD | REVIEW
17 | Candidate | desiredLocations | Desired Locations | NO | BRIEF | YES |  | STANDARD | REVIEW
18 | Candidate | email | Email 1 | YES | Primary Email | YES |  | STANDARD | REVIEW
19 | Candidate | email2 | Email 2 | YES | Personal Email | YES |  | STANDARD | REVIEW
20 | Candidate | employmentPreference | Employment Preference | NO | BRIEF | YES |  | STANDARD | REVIEW
21 | Candidate | fax | Fax | NO | BRIEF | YES |  | STANDARD | REVIEW
22 | Candidate | firstName | Candidate Name | YES | First Name | YES |  | STANDARD | REVIEW
23 | Candidate | fullAddress | Address | NO | N/A | YES | VC: Duplicated with the location fields above. Will not be migrating this. | STANDARD | REVIEW
24 | Candidate | hourlyRate | Desired Pay Rate | NO | BRIEF | YES |  | STANDARD | REVIEW
25 | Candidate | hourlyRateLow | Current Pay Rate | NO | BRIEF | YES |  | STANDARD | REVIEW
29 | Candidate | lastName | Candidate Name | YES | Last Name | YES |  | STANDARD | REVIEW
30 | Candidate | latestComment | Latest Comment | NO | BRIEF | YES |  | STANDARD | REVIEW
31 | Candidate | middleName | Candidate Name | YES | Middle Name | YES |  | STANDARD | REVIEW
32 | Candidate | mobile | Mobile Phone | YES | Primary Phone | YES |  | STANDARD | REVIEW
33 | Candidate | occupation | Title | YES | Job Title | YES |  | STANDARD | REVIEW
34 | Candidate | phone | Home Phone | YES | Home Phone | YES |  | STANDARD | REVIEW
35 | Candidate | phone2 | Other Phone | YES | Mobile Phone | YES |  | STANDARD | REVIEW
36 | Candidate | recruiterUserID | Ownership | YES | Candidate Owners | YES |  | STANDARD | REVIEW
37 | Candidate | referredBy | Referred By (Other) | NO | BRIEF | YES |  | STANDARD | REVIEW
38 | Candidate | referredByUserID | Referred By | NO | BRIEF | YES |  | STANDARD | REVIEW
39 | Candidate | salary | Desired Salary | NO | BRIEF | YES |  | STANDARD | REVIEW
40 | Candidate | salaryLow | Current Salary | YES | Current Annual Salary | YES |  | STANDARD | REVIEW
41 | Candidate | secondaryOwners | Secondary Owners | NO | Candidate Owners | YES |  | STANDARD | REVIEW
45 | Candidate | skillID | Skills | YES | SUB FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
46 | Candidate | skillSet | Additonal Skills (resume parser) | YES | SKILLS | YES |  | STANDARD | REVIEW
47 | Candidate | source | Source | YES | CANDIDATE SOURCES | NO |  | CUSTOM | PRODUCTION
48 | Candidate | state | State | YES | Location Address Location Name Location State | YES |  | STANDARD | REVIEW
49 | Candidate | status | Status | YES | BRIEF | NO | GN: We have Achived and deleted candidates - if the are archived then they should not be visible in a search as usually we will archive candidates who request to be deleted as per Japanese privacy laws - so please advise AT: We have "soft deleted" mode. We can make archived / deleted BH status to make the candidates to be in "soft deleted" mode. They will not be showing by default in search but you can choose to search it by enabling the filter if in case required. I am marking this field to be required then. We will need a custom script to apply this custom rule. | CUSTOM | PRODUCTION
50 | Candidate | workPhone | Work Phone | YES | Work Phone | YES |  | STANDARD | REVIEW
51 | Candidate | zip | Post Code | YES | Location Address Location Name Location Postal (ZIP) Code | YES |  | STANDARD | REVIEW
56 | Candidate File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
57 | Candidate File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
58 | CandidateCertification | boardCertification | Board Certification | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
59 | CandidateCertification | candidateCredentialNote | Comments | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
60 | CandidateCertification | certificationID | Requirement Type | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
61 | CandidateCertification | compact | Compact | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
62 | CandidateCertification | dateCertified | Date Certified | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
63 | CandidateCertification | dateExpiration | Expiration Date | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
64 | CandidateCertification | issuingAuthority | Issuing Authority | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
65 | CandidateCertification | licenseNumber | License Number | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
66 | CandidateCertification | licenseType | License Type | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
67 | CandidateCertification | name | Credential | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
68 | CandidateCertification | onFile | On File | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
69 | CandidateCertification | results | Results | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
70 | CandidateCertification | status | Status | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
71 | CandidateCertification | validLocations | Locations | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
72 | Education | certification | Certification | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
73 | Education | city | City | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
74 | Education | comments | Comments | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
75 | Education | customText1 | Country | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
76 | Education | dateAdded | Date Added | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
77 | Education | degree | Degree | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
78 | Education | endDate | End Date | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
79 | Education | expirationDate | Expiration Date | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
80 | Education | gpa | GPA | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
81 | Education | graduationDate | Graduation Date | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
82 | Education | major | Major | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
83 | Education | school | School | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
84 | Education | startDate | Start Date | YES | Education Historical Summary | YES |  | STANDARD | REVIEW
85 | Education | state | State | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
86 | Education | userEducationID | Education ID | NO | Education Historical Summary | YES |  | STANDARD | REVIEW
87 | Note | action | Action | YES | Activities Comments | YES |  | STANDARD | REVIEW
88 | Note | commentingUserID | Author | YES | Activities Comments | YES |  | STANDARD | REVIEW
89 | Note | comments | Comments | YES | Activities Comments | YES |  | STANDARD | REVIEW
90 | Note | dateAdded | Date Added | YES | Activities Comments | YES |  | STANDARD | REVIEW
91 | Note | userID | About | YES | Activities Comments | YES |  | STANDARD | REVIEW
92 | Task | candidateUserID | Candidate | NO | Activities Comments | YES |  | STANDARD | REVIEW
93 | Task | childTaskOwners | Assigned To | NO | Activities Comments | YES |  | STANDARD | REVIEW
94 | Task | clientUserID | Contact | NO | Activities Comments | YES |  | STANDARD | REVIEW
95 | Task | dateBegin | Due Date And Time | NO | Activities Comments | YES |  | STANDARD | REVIEW
96 | Task | dateEnd | Date End | NO | Activities Comments | YES |  | STANDARD | REVIEW
97 | Task | description | Description | NO | Activities Comments | YES |  | STANDARD | REVIEW
98 | Task | isPrivate | Visibility | NO | Activities Comments | YES |  | STANDARD | REVIEW
99 | Task | jobPostingID | Job | NO | Activities Comments | YES |  | STANDARD | REVIEW
100 | Task | leadUserID | Lead | NO | Activities Comments | YES |  | STANDARD | REVIEW
101 | Task | notificationMinutes | Reminder | NO | Activities Comments | YES |  | STANDARD | REVIEW
102 | Task | opportunityJobPostingID | Opportunity | NO | Activities Comments | YES |  | STANDARD | REVIEW
103 | Task | placementID | Placement | YES | Activities Comments | YES |  | STANDARD | REVIEW
104 | Task | priority | Priority | NO | Activities Comments | YES |  | STANDARD | REVIEW
105 | Task | recurrenceDayBits | Recurrence Day Bits | NO | Activities Comments | YES |  | STANDARD | REVIEW
106 | Task | recurrenceFrequency | Recurrence Frequency | NO | Activities Comments | YES |  | STANDARD | REVIEW
107 | Task | recurrenceMax | Recurrence Max | NO | Activities Comments | YES |  | STANDARD | REVIEW
108 | Task | recurrenceMonthBits | Recurrence Month Bits | NO | Activities Comments | YES |  | STANDARD | REVIEW
109 | Task | recurrenceStyle | Recurrence Style | NO | Activities Comments | YES |  | STANDARD | REVIEW
110 | Task | recurrenceType | Recurrence Type | NO | Activities Comments | YES |  | STANDARD | REVIEW
111 | Task | subject | Subject | NO | Activities Comments | YES |  | STANDARD | REVIEW
112 | Task | type | Type | NO | Activities Comments | YES |  | STANDARD | REVIEW
113 | Task | userID | Owner | NO | Activities Comments | YES |  | STANDARD | REVIEW
114 | Work History | bonus | Bonus | YES | Employment History Summary | YES |  | STANDARD | REVIEW
115 | Work History | clientCorporationID | Client Corporation | YES | Employment History Summary | YES |  | STANDARD | REVIEW
116 | Work History | comments | Comments | NO | Employment History Summary | YES |  | STANDARD | REVIEW
117 | Work History | commission | Commission | NO | Employment History Summary | YES |  | STANDARD | REVIEW
118 | Work History | companyName | Company Name | YES | Employment History Summary | YES |  | STANDARD | REVIEW
119 | Work History | dateAdded | Date Added | YES | Employment History Summary | YES |  | STANDARD | REVIEW
120 | Work History | endDate | End Date | YES | Employment History Summary | YES |  | STANDARD | REVIEW
121 | Work History | jobPostingID | Job Posting | YES | Employment History Summary | YES |  | STANDARD | REVIEW
122 | Work History | placementID | Placement | YES | Employment History Summary | YES |  | STANDARD | REVIEW
123 | Work History | salary1 | Salary Low | NO | Employment History Summary | YES |  | STANDARD | REVIEW
124 | Work History | salary2 | Salary High | NO | Employment History Summary | YES |  | STANDARD | REVIEW
125 | Work History | salaryType | Salary Type | NO | Employment History Summary | YES |  | STANDARD | REVIEW
126 | Work History | startDate | Start Date | YES | Employment History Summary | YES |  | STANDARD | REVIEW
127 | Work History | terminationReason | Termination Reason | NO | Employment History Summary | YES |  | STANDARD | REVIEW
128 | Work History | title | Title | YES | Employment History Summary | YES |  | STANDARD | REVIEW
129 | Work History | userWorkHistoryID | User Work History ID | NO | Employment History Summary | YES |  | STANDARD | REVIEW
130 | EMAIL | EMAIL | EMAIL | YES | Activities Comments | YES | GN - can you please confirm if this is the email history, given you have listed it as migrating to activity comments. Is this where emails are stored or is it a special migration on the DB import? AT: Yes Email will be migrated to Activities Comments. The body text and subject will be included. But the email attachments won't be migrated. This is included in our standard script and can be made available in the Review Site. I am marking this as required so you can see it in the Activities Comments. | STANDARD | REVIEW
131 | TEARSHEET | TEARSHEET | TEARSHEET | NO | Talent Pools | NO |  | CUSTOM | PRODUCTION
132 | HISTORICAL PLACEMENTS | HISTORICAL PLACEMENTS | HISTORICAL PLACEMENTS | YES | JOB APPLICATIONS Activities Comments | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 5. Job Application Stage Mappin
3 Custom Scripts are inclusive to the Data Migration Prohect.
|  | Status: | Approved |  |  | 1 Additional Custom Script = 200 USD one time fee
No | Bullhorn CRM Stage | Required ? | Vincere Stage | Comments | STANDARD / CUSTOM | TARGET INSTANCE
1 | Client Rejected | NO | SHORTLISTED > REJECTED |  | STANDARD | REVIEW
2 | Client Submission | NO | SENT |  | STANDARD | REVIEW
3 | Interview Scheduled | NO | FIRST_INTERVIEW |  | STANDARD | REVIEW
4 | Placed | YES | PLACED | GN: I only want the "placed" field to be shown so we dont contact. Not to be in the Job application stages. Would it make sense to be as a note? Or will the "placed" tag not appear in the job application stages? | STANDARD | REVIEW
5 | Submitted | NO | SHORTLISTED |  | STANDARD | REVIEW
Note: REJECTED state can only be mapped to SHORTLISTED stage thru CUSTOM SCRIPT. SUB-STATUS could also be mapped thru CUSTOM SCRIPT if required. SUB-STATUS is configurable status field in Vincere where user can configure the definition accordingly.
Job Types
No | Bullhorn CRM Employment Type | Required ? | Vincere Job Type | Comments
1 | Contract | YES | CONTRACT
2 | Contract To Hire | YES | CONTRACT
3 | Direct Hire | YES | PERMANENT

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
[5 empty] | Total : | 0
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.

## 6. CUSTOM SCRIPT Industry Mappi
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM Business Sector Field | Required ? | Vincere Industry Field | Comments
1 |  |  | TBD by Vincere | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
23
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
25
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM SCRIPT Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment

## 8. CUSTOM SCRIPT Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM SCRIPT Candidate Sou
Candidate Source Field
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM SOURCE Field values | Required ? | Vincere Candidate Source values | Comment