## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Bullhorn
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
No | Date | Category | Customer Questions | Sample Data | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference

## 1. Company Fields Mapping
Bullhorn to Vincere Fields Mapping (COMPANY)
No | Bullhorn Section | Bullhorn DB Fieldname | Bullhorn UI Fieldname | CORE Fields ? | Required ? | Vincere Field | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client | address1 | Address | YES | YES | Location Address |  | STANDARD | REVIEW
2 | Client | address2 |  | YES | YES | Location Address |  | STANDARD | REVIEW
3 | Client | billingAddress1 | Billing Address | YES | YES | Location Address | 1. Will need to add a separate address for the Billing Address. 2. To append "Billing Address" to the Location Name | STANDARD | REVIEW
4 | Client | billingAddress2 |  | YES | YES | Location Address |  | STANDARD | REVIEW
5 | Client | billingCity | Billing City | YES | YES | Current Town ¦ City |  | STANDARD | REVIEW
6 | Client | billingContact | Billing Contact | YES | YES | NOTE |  | STANDARD | REVIEW
7 | Client | billingFrequency | Billing Frequency | YES | YES | NOTE |  | STANDARD | REVIEW
8 | Client | billingPhone | Billing Phone | YES | YES | NOTE |  | STANDARD | REVIEW
9 | Client | billingState | Billing State | YES | YES | State |  | STANDARD | REVIEW
10 | Client | billingZip | Billing Zip | YES | YES | ZIP (Postal) Code |  | STANDARD | REVIEW
11 | Client | city | Suburb | YES | YES | Current Town ¦ City Location Name |  | STANDARD | REVIEW
12 | Client | clientCorporationRatios | stats | NO | NO | NOTE |  | STANDARD | REVIEW
13 | Client | companyDescription | Company Description | YES | YES | NOTE |  | STANDARD | REVIEW
14 | Client | companyURL | Company Website | YES | YES | Website |  | STANDARD | REVIEW
15 | Client | countryID | Country | YES | YES | Location Address Location Country Location Name |  | STANDARD | REVIEW
16 | Client | customText2 | ABN | NO | YES | NOTE |  | STANDARD | REVIEW
17 | Client | dateAdded | Date Added | NO | YES | NOTE |  | STANDARD | REVIEW
18 | Client | dateLastModified | Date Last Modified | NO | YES | NOTE |  | STANDARD | REVIEW
19 | Client | fax | Fax | NO | YES | NOTE |  | STANDARD | REVIEW
20 | Client | feeArrangement | Standard Perm Fee (%) | NO | YES | NOTE |  | STANDARD | REVIEW
21 | Client | fullAddress | Address | YES | YES | Location Address |  | STANDARD | REVIEW
22 | Client | fullBillingAddress | Billing Address | NO | YES | Location Address |  | STANDARD | REVIEW
23 | Client | name | Company Name | YES | YES | Company Name |  | STANDARD | REVIEW
24 | Client | notes | Company Overview | YES | YES | NOTE |  | STANDARD | REVIEW
25 | Client | opportunityTable | Opportunities | NO |  | NOTE |  | STANDARD | REVIEW
26 | Client | ownership | Ownership | YES | YES | Company Owners |  | STANDARD | REVIEW
27 | Client | parentClientCorporationID | Parent Company | NO | NO |  |  | STANDARD | REVIEW
28 | Client | phone | Main Phone | YES | YES |  |  | STANDARD | REVIEW
29 | Client | revenue | revenue | NO | NO |  |  | STANDARD | REVIEW
30 | Client | state | State | YES | YES | Location Address Location State Location Name |  | STANDARD | REVIEW
31 | Client | status | Status | NO | YES | NOTE |  | STANDARD | REVIEW
32 | Client | yearFounded | Year Founded | NO | NO | NOTE |  | STANDARD | REVIEW
33 | Client | zip | Post Code | YES | YES | Location Address Location ZIP (Postal) Code Location Name |  | STANDARD | REVIEW
34 | Client | clientCorporationID | Company ID | YES | YES | Company External ID |  | STANDARD | REVIEW
35 | Company File Attachment | dateAdded | Date Added | YES | YES | FILES |  | STANDARD | REVIEW
36 | Company File Attachment | fileSize | File Size | YES | YES | FILES |  | STANDARD | REVIEW
37 | Company File Attachment | isPrivate | Is Private | YES | YES | FILES |  | STANDARD | REVIEW
38 | Company File Attachment | name | Name | YES | YES | FILES |  | STANDARD | REVIEW
39 | Company File Attachment | type | Type | YES | YES | FILES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 2. Contact Fields Mapping
Bullhorn to Vincere Fields Mapping (CONTACTS)
No | Bullhorn Section | Bullhorn DB Field Name | Bullhorn UI Field Name | CORE Fields ? | Required ? | Vincere Field | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client Contact | address1 | Address | YES | YES | Location Address |  | STANDARD | REVIEW
2 | Client Contact | address2 |  | YES | YES | Location Address |  | STANDARD | REVIEW
3 | Client Contact | city | Suburb | YES | YES | Location Address Location City Location Name |  | STANDARD | REVIEW
4 | Client Contact | clientCorporationID | Company | YES | YES | Company External ID |  | STANDARD | REVIEW
5 | Client Contact | comments | General Contact Comments | YES | YES | NOTE |  | STANDARD | REVIEW
6 | Client Contact | countryID | Country | YES | YES | Location Address Location Country Location Name |  | STANDARD | REVIEW
7 | Client Contact | customText1 | LinkedIn URL | YES | YES | LinkedIn |  | STANDARD | REVIEW
8 | Client Contact | desiredCategories | Desired Categories | NO | NO | NOTE |  | STANDARD | REVIEW
9 | Client Contact | desiredLocations | Desired Locations | NO | NO | NOTE |  | STANDARD | REVIEW
10 | Client Contact | desiredSkills | Desired Skills Sub-Category | NO | NO | NOTE |  | STANDARD | REVIEW
11 | Client Contact | desiredSpecialties | Desired Specialties Sub-Category | NO | NO | NOTE |  | STANDARD | REVIEW
12 | Client Contact | division | Department | YES | YES | Department |  | STANDARD | REVIEW
13 | Client Contact | email | Email 1 | YES | YES | Primary Email |  | STANDARD | REVIEW
14 | Client Contact | email2 | Email 2 | YES | YES | Personal Email |  | STANDARD | REVIEW | Non-chargeable
15 | Client Contact | firstName | Contact Name | YES | YES | First Name |  | STANDARD | REVIEW
16 | Client Contact | fullAddress | Address | YES | YES | Location Address |  | STANDARD | REVIEW
17 | Client Contact | last3Education | Last 3 Education | NO | YES | NOTE |  | STANDARD | REVIEW
18 | Client Contact | last3Reference | Last 3 Reference | NO | YES | NOTE |  | STANDARD | REVIEW
19 | Client Contact | last3workHistory | Last 3 Work History | NO | YES | NOTE |  | STANDARD | REVIEW
20 | Client Contact | lastName | Contact Name | YES | YES | Last Name |  | STANDARD | REVIEW
21 | Client Contact | middleName | Contact Name | YES | YES | Middle Name |  | STANDARD | REVIEW
22 | Client Contact | mobile | Mobile Phone | YES | YES | Mobiile Phone |  | STANDARD | REVIEW
23 | Client Contact | namePrefix | Contact Name | YES | YES | Title |  | STANDARD | REVIEW
24 | Client Contact | npsIsEnrolled | Enrolled in NPS | NO | NO | Note |  | STANDARD | REVIEW
25 | Client Contact | occupation | Title | YES | YES | Job Title |  | STANDARD | REVIEW
26 | Client Contact | phone | Direct Phone | YES | YES | Primary Phone |  | STANDARD | REVIEW
27 | Client Contact | phone2 | Other Phone | YES | YES | Home Phone |  | STANDARD | REVIEW
28 | Client Contact | recruiterUserID | Owner | NO | YES | Contact Owners |  | STANDARD | REVIEW
29 | Client Contact | reportToUserID | Reports to | NO | YES | Note |  | STANDARD | REVIEW
30 | Client Contact | revenue | revenue | YES | YES | Note |  | STANDARD | REVIEW
31 | Client Contact | secondaryOwners | Secondary Owners | NO | YES | Contact Owners |  | STANDARD | REVIEW
32 | Client Contact | state | State | YES | YES | Location Address Location State Location Name |  | STANDARD | REVIEW
33 | Client Contact | status | Status | NO | YES | Note |  | STANDARD | REVIEW
34 | Client Contact | zip | Post Code | YES | YES | Location Address Location ZIP (Postal) Code Location Name |  | STANDARD | REVIEW
35 | Contact File Attachment | dateAdded | Date Added | YES | YES | FILES |  | STANDARD | REVIEW
36 | Contact File Attachment | name | Name | YES | YES | FILES |  | STANDARD | REVIEW
37 | Contact File Attachment | type | Type | YES | YES | FILES |  | STANDARD | REVIEW
38 | Note | action | Action | YES | YES | Activities Comments |  | STANDARD | REVIEW
39 | Note | commentingUserID | Author | YES | YES | Activities Comments |  | STANDARD | REVIEW
40 | Note | comments | Comments | YES | YES | Activities Comments |  | STANDARD | REVIEW
41 | Note | dateAdded | Date Added | YES | YES | Activities Comments |  | STANDARD | REVIEW
42 | Note | userID | About | YES | YES | Activities Comments |  | STANDARD | REVIEW
43 | Task | candidateUserID | Candidate | YES | YES | Activities Comments |  | STANDARD | REVIEW
44 | Task | childTaskOwners | Assigned To | YES | YES | Activities Comments |  | STANDARD | REVIEW
45 | Task | clientUserID | Contact | YES | YES | Activities Comments |  | STANDARD | REVIEW
46 | Task | dateBegin | Due Date And Time | YES | YES | Activities Comments |  | STANDARD | REVIEW
47 | Task | dateEnd | Date End | YES | YES | Activities Comments |  | STANDARD | REVIEW
48 | Task | description | Description | YES | YES | Activities Comments |  | STANDARD | REVIEW
49 | Task | jobPostingID | Job | YES | YES | Activities Comments |  | STANDARD | REVIEW
50 | Task | leadUserID | Lead | YES | YES | Activities Comments |  | STANDARD | REVIEW
51 | Task | notificationMinutes | Reminder | YES | YES | Activities Comments |  | STANDARD | REVIEW
52 | Task | opportunityJobPostingID | Opportunity | YES | YES | Activities Comments |  | STANDARD | REVIEW
53 | Task | placementID | Placement | YES | YES | Activities Comments |  | STANDARD | REVIEW
54 | Task | priority | Priority | YES | YES | Activities Comments |  | STANDARD | REVIEW
55 | Task | subject | Subject | YES | YES | Activities Comments |  | STANDARD | REVIEW
56 | Task | type | Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
57 | Task | userID | Owner | YES | YES | Activities Comments |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 4. Job Fields Mapping
Bullhorn to Vincere Fields Mapping (JOB)
No | Bullhorn Section | Bullhorn DB Field Name | Bullhorn UI Field Name | Core Fields ? | Required ? | Vincere Field | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Job Posting | address | Address | YES | YES | Job Note > Location |  | STANDARD | REVIEW
2 | Job Posting | benefits | Benefits | YES | YES | Job Note > Location |  | STANDARD | REVIEW
3 | Job Posting | businessSectorID | Industry | NO | NO | INDUSTRY | Need to add the original Industry values | CUSTOM | PRODUCTION
4 | Job Posting | categoryID | Category | NO | NO | FUNCTIONAL EXPERTISE | Need to add the original Functional Expertise values | CUSTOM | PRODUCTION
5 | Job Posting | certifications | Certification Requirements | YES | YES | Job Note > Location |  | STANDARD | REVIEW
6 | Job Posting | city | Suburb | YES | YES | Job Note > Location |  | STANDARD | REVIEW
7 | Job Posting | clientBillRate | Client Bill Rate | YES | YES | Job Note > Client Bill Rate |  | STANDARD | REVIEW
8 | Job Posting | clientCorporationID | Client Company | YES | YES | Company External ID |  | STANDARD | REVIEW
9 | Job Posting | clientUserID | Contact | YES | YES | Contact External ID |  | STANDARD | REVIEW
10 | Job Posting | correlatedCustomText1 | Primary Timesheet Approver | YES | YES | Job Note > Primary Timesheet Approver |  | STANDARD | REVIEW
11 | Job Posting | correlatedCustomText2 | Secondary Timecard Approver | YES | YES | Job Note > Secondary Timesheet Approver |  | STANDARD | REVIEW
12 | Job Posting | correlatedCustomText3 | Purchase Order Number | YES | YES | Job Note > Purchase Order Number |  | STANDARD | REVIEW
13 | Job Posting | countryID | Country | YES | YES | Job Note > Location |  | STANDARD | REVIEW
14 | Job Posting | dateEnd | Scheduled End | YES | YES | Job Note > Scheduled End |  | STANDARD | REVIEW
15 | Job Posting | degreeList | Degree Requirements | YES | YES | Job Note > Degree Requirements |  | STANDARD | REVIEW
16 | Job Posting | description | Job Description | YES | YES | Job Note > Job Description |  | STANDARD | REVIEW
18 | Job Posting | educationDegree | Education Requirements | YES | YES | Job Note > Education Requirements |  | STANDARD | REVIEW
19 | Job Posting | employmentType | Employment Type | YES | YES | Job Note > Employement Type |  | STANDARD | REVIEW
20 | Job Posting | feeArrangement | Perm Fee (%) | YES | YES | Job Note > Perm Fee (%) |  | STANDARD | REVIEW
21 | Job Posting | fullAddress | Address | YES | YES | Job Note > Location |  | STANDARD | REVIEW
22 | Job Posting | hoursPerWeek | Hourly Commitment | YES | YES | Job Note > Hourly Commitment |  | STANDARD | REVIEW
23 | Job Posting | isInterviewRequired | Interview Required? | YES | YES | Job Note > Interview Required ? |  | STANDARD | REVIEW
24 | Job Posting | isOpen | Open/Closed | YES | YES | Open / Closed thru Job Open Date / Job Closed Job |  | STANDARD | REVIEW
25 | Job Posting | linkedJobPostingID | Linked Job Posting ID | YES | YES | Job External ID |  | STANDARD | REVIEW
27 | Job Posting | numOpenings | # of Openings | YES | YES | Headcount |  | STANDARD | REVIEW
28 | Job Posting | onSite | Location Requirements | YES | YES | Internal Job Description > Location Requirements |  | STANDARD | REVIEW
29 | Job Posting | payRate | Pay Rate | YES | YES | Job Note > Pay Rate |  | STANDARD | REVIEW
30 | Job Posting | publicDescription | Published Description | YES | YES | Public Job Description |  | STANDARD | REVIEW
31 | Job Posting | reasonClosed | Reason Closed | YES | YES | Job Note > Reason Closed |  | STANDARD | REVIEW
32 | Job Posting | salary | Salary | YES | YES | Annual Salary |  | STANDARD | REVIEW
33 | Job Posting | salaryUnit | Pay Rate | YES | YES | Job Note > Pay Rate |  | STANDARD | REVIEW
34 | Job Posting | skillID | Required Skills | NO | NO | SUB FUNCTIONAL EXPERTISE | Need to add the original Sub Functional Expertise values | CUSTOM | PRODUCTION
35 | Job Posting | skills | Keywords | YES | YES | Skills |  | STANDARD | REVIEW
37 | Job Posting | specialty_categoryID | Specialties Sub-Category | NO | NO | FUNCTIONAL EXPERTISE | Need to add the original Functional Expertise values | CUSTOM | PRODUCTION
38 | Job Posting | startDate | Start Date | YES | YES | Job Open Date |  | STANDARD | REVIEW
39 | Job Posting | state | State | YES | YES | Job Note > Location |  | STANDARD | REVIEW
40 | Job Posting | status | Status | YES | YES | Job Note > Status |  | STANDARD | REVIEW
41 | Job Posting | title | Job Title | YES | YES | Job Title |  | STANDARD | REVIEW
42 | Job Posting | type | Priority | YES | YES | Job Note > Priority |  | STANDARD | REVIEW
43 | Job Posting | userID | Owner | NO | NO | Job Owners | Will need to map the owners to the user's email address | CUSTOM | PRODUCTION
44 | Job Posting | willSponsor | Visa Sponsorship Provided | YES | YES | Job Note > Visa Sponsorship Provided |  | STANDARD | REVIEW
45 | Job Posting | yearsRequired | Minimum Experience | YES | YES | Job Note > Minimum Experience |  | STANDARD | REVIEW
46 | Job Posting | zip | Post Code | YES | YES | Job Note > Location |  | STANDARD | REVIEW
47 | Job Order File Attachment | dateAdded | Date Added | YES | YES | FILES |  | STANDARD | REVIEW
51 | Job Order File Attachment | name | Name | YES | YES | FILES |  | STANDARD | REVIEW
53 | Note | action | Action | YES | YES | Activities Comments |  | STANDARD | REVIEW
54 | Note | commentingUserID | Author | YES | YES | Activities Comments |  | STANDARD | REVIEW
55 | Note | comments | Comments | YES | YES | Activities Comments |  | STANDARD | REVIEW
56 | Note | dateAdded | Date Added | YES | YES | Activities Comments |  | STANDARD | REVIEW
57 | Note | userID | About | YES | YES | Activities Comments |  | STANDARD | REVIEW
58 | Task | candidateUserID | Candidate | YES | YES | Activities Comments |  | STANDARD | REVIEW
59 | Task | childTaskOwners | Assigned To | YES | YES | Activities Comments |  | STANDARD | REVIEW
60 | Task | clientUserID | Contact | YES | YES | Activities Comments |  | STANDARD | REVIEW
61 | Task | dateBegin | Due Date And Time | YES | YES | Activities Comments |  | STANDARD | REVIEW
62 | Task | dateEnd | Date End | YES | YES | Activities Comments |  | STANDARD | REVIEW
63 | Task | description | Description | YES | YES | Activities Comments |  | STANDARD | REVIEW
64 | Task | isPrivate | Visibility | YES | YES | Activities Comments |  | STANDARD | REVIEW
65 | Task | jobPostingID | Job | YES | YES | Activities Comments |  | STANDARD | REVIEW
66 | Task | leadUserID | Lead | YES | YES | Activities Comments |  | STANDARD | REVIEW
67 | Task | notificationMinutes | Reminder | YES | YES | Activities Comments |  | STANDARD | REVIEW
68 | Task | opportunityJobPostingID | Opportunity | YES | YES | Activities Comments |  | STANDARD | REVIEW
69 | Task | placementID | Placement | YES | YES | Activities Comments |  | STANDARD | REVIEW
70 | Task | priority | Priority | YES | YES | Activities Comments |  | STANDARD | REVIEW
71 | Task | recurrenceDayBits | Recurrence Day Bits | YES | YES | Activities Comments |  | STANDARD | REVIEW
72 | Task | recurrenceFrequency | Recurrence Frequency | YES | YES | Activities Comments |  | STANDARD | REVIEW
73 | Task | recurrenceMax | Recurrence Max | YES | YES | Activities Comments |  | STANDARD | REVIEW
74 | Task | recurrenceMonthBits | Recurrence Month Bits | YES | YES | Activities Comments |  | STANDARD | REVIEW
75 | Task | recurrenceStyle | Recurrence Style | YES | YES | Activities Comments |  | STANDARD | REVIEW
76 | Task | recurrenceType | Recurrence Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
77 | Task | subject | Subject | YES | YES | Activities Comments |  | STANDARD | REVIEW
78 | Task | type | Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
79 | Task | userID | Owner | YES | YES | Activities Comments |  | STANDARD | REVIEW

## 3. Candidate Fields Mapping
Bullhorn to Vincere Fields Mapping (Candidates)
No | Bullhorn Section | Bullhorn DB Field | Bullhorn UI Field | Core Fields ? | Required ? | Vincere Field | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Candidate | address1 | Address | YES | YES | Location Address |  | STANDARD | REVIEW
2 | Candidate | address2 |  | YES | YES | Location Address |  | STANDARD | REVIEW
3 | Candidate | businessSectorID | Industry | NO | NO | INDUSTRY | Need to add the original Industry values | CUSTOM | PRODUCTION
4 | Candidate | categoryID | Category | NO | NO | FUNCTIONAL EXPERTISE | Need to add the original Functional Expertise values | CUSTOM | PRODUCTION
5 | Candidate | city | Suburb | YES | YES | Location Address Current Town / City Location Name |  | STANDARD | REVIEW
6 | Candidate | comments | General Candidate Comments | YES | YES | Brief Note |  | STANDARD | REVIEW
7 | Candidate | companyName | Current Company | YES | YES | Work History Company |  | STANDARD | REVIEW
8 | Candidate | countryID | Country | YES | YES | Location Address Location Country Location Name |  | STANDARD | REVIEW
9 | Candidate | customText10 | Pay Type | YES | YES | Brief Note |  | STANDARD | REVIEW
10 | Candidate | dateAvailable | Date Available | YES | YES | Brief Note |  | STANDARD | REVIEW
11 | Candidate | description | CV | YES | YES | Brief Note |  | STANDARD | REVIEW
12 | Candidate | desiredLocations | Desired Locations | YES | YES | Brief Note |  | STANDARD | REVIEW
13 | Candidate | email | Email 1 | YES | YES | Primary Email |  | STANDARD | REVIEW
14 | Candidate | email2 | Email 2 | YES | YES | Personal Email |  | STANDARD | REVIEW | Non-chargeable
15 | Candidate | employeeType | Employee Type | YES | YES | Brief Note |  | STANDARD | REVIEW
16 | Candidate | employmentPreference | Employment Preference | YES | YES | Brief Note |  | STANDARD | REVIEW
17 | Candidate | fax | Fax | YES | YES | Brief Note |  | STANDARD | REVIEW
18 | Candidate | firstName | First Name | YES | YES | First Name |  | STANDARD | REVIEW
19 | Candidate | fullAddress | Address | YES | YES | Location Address |  | STANDARD | REVIEW
20 | Candidate | hourlyRate | Desired Pay Rate | YES | YES | Brief Note |  | STANDARD | REVIEW
21 | Candidate | hourlyRateLow | Current Pay Rate | YES | YES | Brief Note |  | STANDARD | REVIEW
22 | Candidate | last3Education | Last 3 Education | YES | YES | Education Summary |  | STANDARD | REVIEW
23 | Candidate | last3Reference | Last 3 Reference | YES | YES | Brief Note |  | STANDARD | REVIEW
24 | Candidate | last3workHistory | Last 3 Work History | YES | YES | Employment History |  | STANDARD | REVIEW
25 | Candidate | lastName | Last Name | YES | YES | Last Name |  | STANDARD | REVIEW
26 | Candidate | latestComment | Latest Comment | YES | YES | Brief Note |  | STANDARD | REVIEW
27 | Candidate | mobile | Mobile Phone | YES | YES | Primary Phone Mobile Phone |  | STANDARD | REVIEW
28 | Candidate | namePrefix | Candidate Name | YES | YES | Candidate First Name |  | STANDARD | REVIEW
29 | Candidate | nickName | Nick Name | YES | YES | Preferred Name |  | STANDARD | REVIEW
30 | Candidate | occupation | Title | YES | YES | Job Title |  | STANDARD | REVIEW
31 | Candidate | phone | Home Phone | YES | YES | Home Phone |  | STANDARD | REVIEW
32 | Candidate | phone2 | Other Phone | YES | YES | Work Phone |  | STANDARD | REVIEW
33 | Candidate | recruiterUserID | Ownership | NO | NO | Candidate Owners | Will need to map the owners to the user's email address | CUSTOM | PRODUCTION
34 | Candidate | referredBy | Referred By (Other) | YES | YES | Brief Note |  | STANDARD | REVIEW
35 | Candidate | referredByUserID | Referred By | YES | YES | Brief Note |  | STANDARD | REVIEW
36 | Candidate | salary | Desired Salary | YES | YES | Desired Salary |  | STANDARD | REVIEW
37 | Candidate | salaryLow | Current Salary | YES | YES | Current Salary |  | STANDARD | REVIEW
38 | Candidate | secondaryOwners | Secondary Owners | NO | NO | Candidate Owners | Will need to map the owners to the user's email address | CUSTOM | PRODUCTION
39 | Candidate | skillID | Skills | YES | YES | Skills |  | STANDARD | REVIEW
40 | Candidate | skillSet | Additonal Skills (CV parser) | YES | YES | Brief Note |  | STANDARD | REVIEW
41 | Candidate | source | Source | NO | NO | Candidate Source |  | CUSTOM | PRODUCTION
42 | Candidate | state | State | YES | YES | Location Address Location State Location Name |  | STANDARD | REVIEW
43 | Candidate | status | Status | YES | YES | Brief Note |  | STANDARD | REVIEW
44 | Candidate | willRelocate | Willing to Relocate | YES | YES | Brief Note |  | STANDARD | REVIEW
45 | Candidate | workPhone | Work Phone | YES | YES | Work Phone |  | STANDARD | REVIEW
46 | Candidate | zip | Postal Code | YES | YES | Location Address Location Zip (Postal) Code Location Name |  | STANDARD | REVIEW
47 | Candidate File Attachment | dateAdded | Date Added | YES | YES | FILES |  | STANDARD | REVIEW
48 | Candidate File Attachment | distribution | Distribution | YES | YES | FILES |  | STANDARD | REVIEW
49 | Candidate File Attachment | fileSize | File Size | YES | YES | FILES |  | STANDARD | REVIEW
50 | Candidate File Attachment | isPrivate | Is Private | YES | YES | FILES |  | STANDARD | REVIEW
51 | Candidate File Attachment | name | Name | YES | YES | FILES |  | STANDARD | REVIEW
52 | Candidate File Attachment | type | Type | YES | YES | FILES |  | STANDARD | REVIEW
53 | Candidate Tax Info | dateI9Expiration | I9 Expiration Date | YES | YES | Brief Note |  | STANDARD | REVIEW
54 | Candidate Tax Info | dateOfBirth | Birthday | YES | YES | Date of Birth |  | STANDARD | REVIEW
55 | Candidate Tax Info | federalAddtionalWitholdingsAmount | Federal Additional Withholdings Amount | YES | YES | Brief Note |  | STANDARD | REVIEW
56 | Candidate Tax Info | federalExemptions | Federal Exemptions | YES | YES | Brief Note |  | STANDARD | REVIEW
57 | Candidate Tax Info | federalFilingStatus | Federal Filing Status | YES | YES | Brief Note |  | STANDARD | REVIEW
58 | Candidate Tax Info | I9OnFile | I9 On File | YES | YES | Brief Note |  | STANDARD | REVIEW
59 | Candidate Tax Info | localAddtionalWitholdingsAmount | Local Additional Withholdings Amount | YES | YES | Brief Note |  | STANDARD | REVIEW
60 | Candidate Tax Info | localExemptions | Local Exemptions | YES | YES | Brief Note |  | STANDARD | REVIEW
61 | Candidate Tax Info | localFilingStatus | Local Filing Status | YES | YES | Brief Note |  | STANDARD | REVIEW
62 | Candidate Tax Info | localTaxCode | Local Tax Code | YES | YES | Brief Note |  | STANDARD | REVIEW
63 | Candidate Tax Info | ssn | SSN | YES | YES | Brief Note |  | STANDARD | REVIEW
64 | Candidate Tax Info | stateAddtionalWitholdingsAmount | State Additional Withholdings Amount | YES | YES | Brief Note |  | STANDARD | REVIEW
65 | Candidate Tax Info | stateExemptions | State Exemptions | YES | YES | Brief Note |  | STANDARD | REVIEW
66 | Candidate Tax Info | stateFilingStatus | State Filing Status | YES | YES | Brief Note |  | STANDARD | REVIEW
67 | Candidate Tax Info | taxID | Tax ID | YES | YES | Brief Note |  | STANDARD | REVIEW
68 | Candidate Tax Info | taxState | Tax State | YES | YES | Brief Note |  | STANDARD | REVIEW
69 | CandidateCertification | boardCertification | Board Certification | YES | YES | Brief Note |  | STANDARD | REVIEW
70 | CandidateCertification | candidateCredentialNote | Comments | YES | YES | Brief Note |  | STANDARD | REVIEW
71 | CandidateCertification | certificationID | Requirement Type | YES | YES | Brief Note |  | STANDARD | REVIEW
72 | CandidateCertification | compact | Compact | YES | YES | Brief Note |  | STANDARD | REVIEW
73 | CandidateCertification | dateCertified | Date Certified | YES | YES | Brief Note |  | STANDARD | REVIEW
74 | CandidateCertification | dateExpiration | Expiration Date | YES | YES | Brief Note |  | STANDARD | REVIEW
75 | CandidateCertification | issuingAuthority | Issuing Authority | YES | YES | Brief Note |  | STANDARD | REVIEW
76 | CandidateCertification | licenseNumber | License Number | YES | YES | Brief Note |  | STANDARD | REVIEW
77 | CandidateCertification | licenseType | License Type | YES | YES | Brief Note |  | STANDARD | REVIEW
78 | CandidateCertification | name | Credential | YES | YES | Brief Note |  | STANDARD | REVIEW
79 | CandidateCertification | onFile | On File | YES | YES | Brief Note |  | STANDARD | REVIEW
80 | CandidateCertification | results | Results | YES | YES | Brief Note |  | STANDARD | REVIEW
81 | CandidateCertification | status | Status | YES | YES | Brief Note |  | STANDARD | REVIEW
82 | CandidateCertification | validLocations | Locations | YES | YES | Brief Note |  | STANDARD | REVIEW
83 | Education | certification | Certification | YES | YES | Education Summary |  | STANDARD | REVIEW
84 | Education | city | City | YES | YES | Education Summary |  | STANDARD | REVIEW
85 | Education | comments | Comments | YES | YES | Education Summary |  | STANDARD | REVIEW
86 | Education | customText1 | Country | YES | YES | Education Summary |  | STANDARD | REVIEW
87 | Education | dateAdded | Date Added | YES | YES | Education Summary |  | STANDARD | REVIEW
88 | Education | degree | Degree | YES | YES | Education Summary |  | STANDARD | REVIEW
89 | Education | endDate | End Date | YES | YES | Education Summary |  | STANDARD | REVIEW
90 | Education | expirationDate | Expiration Date | YES | YES | Education Summary |  | STANDARD | REVIEW
91 | Education | gpa | GPA | YES | YES | Education Summary |  | STANDARD | REVIEW
92 | Education | graduationDate | Graduation Date | YES | YES | Education Summary |  | STANDARD | REVIEW
93 | Education | major | Major | YES | YES | Education Summary |  | STANDARD | REVIEW
94 | Education | school | School | YES | YES | Education Summary |  | STANDARD | REVIEW
95 | Education | startDate | Start Date | YES | YES | Education Summary |  | STANDARD | REVIEW
96 | Education | state | State | YES | YES | Education Summary |  | STANDARD | REVIEW
97 | Education | userEducationID | Education ID | YES | YES | Education Summary |  | STANDARD | REVIEW
98 | Job Submission | appointments | Appointments | YES | YES | Activities Comments |  | STANDARD | REVIEW
99 | Job Submission | billRate | Bill Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
100 | Job Submission | comments | Comments | YES | YES | Activities Comments |  | STANDARD | REVIEW
101 | Job Submission | dateAdded | Date Added | YES | YES | Activities Comments |  | STANDARD | REVIEW
102 | Job Submission | dateLastModified | Date Last Modified | YES | YES | Activities Comments |  | STANDARD | REVIEW
103 | Job Submission | dateWebResponse | Date Web Response | YES | YES | Activities Comments |  | STANDARD | REVIEW
104 | Job Submission | jobPostingID | Job Order | YES | YES | Activities Comments |  | STANDARD | REVIEW
105 | Job Submission | latestAppointmentID | Latest Appointment | YES | YES | Activities Comments |  | STANDARD | REVIEW
106 | Job Submission | migrateGUID | Migrate GUID | YES | YES | Activities Comments |  | STANDARD | REVIEW
107 | Job Submission | owners | Owners | YES | YES | Activities Comments |  | STANDARD | REVIEW
108 | Job Submission | payRate | Pay Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
109 | Job Submission | salary | Salary | YES | YES | Activities Comments |  | STANDARD | REVIEW
110 | Job Submission | sendingUserID | Added By | YES | YES | Activities Comments |  | STANDARD | REVIEW
111 | Job Submission | source | Source | YES | YES | Activities Comments |  | STANDARD | REVIEW
112 | Job Submission | status | Status | YES | YES | Activities Comments |  | STANDARD | REVIEW
113 | Job Submission | tasks | Task | YES | YES | Activities Comments |  | STANDARD | REVIEW
114 | Job Submission | userID | Candidate | YES | YES | Activities Comments |  | STANDARD | REVIEW
115 | Note | action | Action | YES | YES | Activities Comments |  | STANDARD | REVIEW
116 | Note | commentingUserID | Author | YES | YES | Activities Comments |  | STANDARD | REVIEW
117 | Note | comments | Comments | YES | YES | Activities Comments |  | STANDARD | REVIEW
118 | Note | dateAdded | Date Added | YES | YES | Activities Comments |  | STANDARD | REVIEW
119 | Note | userID | About | YES | YES | Activities Comments |  | STANDARD | REVIEW
120 | Placement | billingUserID | Billing Contact | YES | YES | Activities Comments |  | STANDARD | REVIEW
121 | Placement | billRateInfoHeader | Bill Rate Information | YES | YES | Activities Comments |  | STANDARD | REVIEW
122 | Placement | clientBillRate | Bill Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
123 | Placement | clientOverTimeRate | Over-time Bill Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
124 | Placement | comments | Comments | YES | YES | Activities Comments |  | STANDARD | REVIEW
125 | Placement | contractInfoHeader | Contract Employment Info | YES | YES | Activities Comments |  | STANDARD | REVIEW
126 | Placement | correlatedCustomText1 | Primary Timesheet Approver | YES | YES | Activities Comments |  | STANDARD | REVIEW
127 | Placement | correlatedCustomText2 | Secondary Timecard Approver | YES | YES | Activities Comments |  | STANDARD | REVIEW
128 | Placement | correlatedCustomText3 | Purchase Order Number | YES | YES | Activities Comments |  | STANDARD | REVIEW
129 | Placement | costCenter | Cost Center | YES | YES | Activities Comments |  | STANDARD | REVIEW
130 | Placement | customText1 | Insurance Reference | YES | YES | Activities Comments |  | STANDARD | REVIEW
131 | Placement | dateBegin | Start Date | YES | YES | Activities Comments |  | STANDARD | REVIEW
132 | Placement | dateClientEffective | Effective Date (Client) | YES | YES | Activities Comments |  | STANDARD | REVIEW
133 | Placement | dateEffective | Effective Date | YES | YES | Activities Comments |  | STANDARD | REVIEW
134 | Placement | dateEnd | Scheduled End | YES | YES | Activities Comments |  | STANDARD | REVIEW
135 | Placement | daysGuaranteed | Days Guaranteed | YES | YES | Activities Comments |  | STANDARD | REVIEW
136 | Placement | daysProRated | Days Pro-Rated | YES | YES | Activities Comments |  | STANDARD | REVIEW
137 | Placement | employmentType | Employment Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
138 | Placement | fee | Placement Fee (%) | YES | YES | Activities Comments |  | STANDARD | REVIEW
139 | Placement | flatFee | Placement Fee (Flat) | YES | YES | Activities Comments |  | STANDARD | REVIEW
140 | Placement | hoursOfOperation | Hours of Operation | YES | YES | Activities Comments |  | STANDARD | REVIEW
141 | Placement | hoursPerDay | Hours Per Day | YES | YES | Activities Comments |  | STANDARD | REVIEW
142 | Placement | isMultirate | Rate Entry Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
143 | Placement | markUpPercentage | Mark-up % | YES | YES | Activities Comments |  | STANDARD | REVIEW
144 | Placement | overtimeRate | Over-time Pay Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
145 | Placement | payRate | Pay Rate | YES | YES | Activities Comments |  | STANDARD | REVIEW
146 | Placement | payRateInfoHeader | Pay Rate Information | YES | YES | Activities Comments |  | STANDARD | REVIEW
147 | Placement | permanentInfoHeader | Permanent Employment Info | YES | YES | Activities Comments |  | STANDARD | REVIEW
148 | Placement | referralFeeType | Referral Fee Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
149 | Placement | reportTo | Reporting to | YES | YES | Activities Comments |  | STANDARD | REVIEW
150 | Placement | salary | Salary | YES | YES | Activities Comments |  | STANDARD | REVIEW
151 | Placement | salaryUnit | Pay Unit | YES | YES | Activities Comments |  | STANDARD | REVIEW
152 | Placement | status | Status | YES | YES | Activities Comments |  | STANDARD | REVIEW
153 | Placement File Attachment | dateAdded | Date Added | YES | YES | FILES |  | STANDARD | REVIEW
154 | Placement File Attachment | distribution | Distribution | YES | YES | FILES |  | STANDARD | REVIEW
155 | Placement File Attachment | fileSize | File Size | YES | YES | FILES |  | STANDARD | REVIEW
156 | Placement File Attachment | isPrivate | Is Private | YES | YES | FILES |  | STANDARD | REVIEW
157 | Placement File Attachment | name | Name | YES | YES | FILES |  | STANDARD | REVIEW
158 | Placement File Attachment | type | Type | YES | YES | FILES |  | STANDARD | REVIEW
159 | Reference | candidateTitle | Candidate Title | YES | YES | Brief Note |  | STANDARD | REVIEW
160 | Reference | clientCorporationID | Client Corporation | YES | YES | Brief Note |  | STANDARD | REVIEW
161 | Reference | companyName | Company | YES | YES | Brief Note |  | STANDARD | REVIEW
162 | Reference | dateAdded | Date Added | YES | YES | Brief Note |  | STANDARD | REVIEW
163 | Reference | employmentEnd | Employment End | YES | YES | Brief Note |  | STANDARD | REVIEW
164 | Reference | employmentStart | Employment Start | YES | YES | Brief Note |  | STANDARD | REVIEW
165 | Reference | jobPostingID | Job Posting | YES | YES | Brief Note |  | STANDARD | REVIEW
166 | Reference | referenceEmail | Reference Email | YES | YES | Brief Note |  | STANDARD | REVIEW
167 | Reference | referenceFirstName | Reference First Name | YES | YES | Brief Note |  | STANDARD | REVIEW
168 | Reference | referenceLastName | Reference Last Name | YES | YES | Brief Note |  | STANDARD | REVIEW
169 | Reference | referencePhone | Reference Phone | YES | YES | Brief Note |  | STANDARD | REVIEW
170 | Reference | referenceTitle | Reference Title | YES | YES | Brief Note |  | STANDARD | REVIEW
171 | Reference | referenceUserID | Reference | YES | YES | Brief Note |  | STANDARD | REVIEW
172 | Reference | status | Status | YES | YES | Brief Note |  | STANDARD | REVIEW
173 | Reference | userReferenceID | Reference ID | YES | YES | Brief Note |  | STANDARD | REVIEW
174 | Reference | yearsKnown | Years Known | YES | YES | Brief Note |  | STANDARD | REVIEW
175 | Task | candidateUserID | Candidate | YES | YES | Activities Comments |  | STANDARD | REVIEW
176 | Task | childTaskOwners | Assigned To | YES | YES | Activities Comments |  | STANDARD | REVIEW
177 | Task | clientUserID | Contact | YES | YES | Activities Comments |  | STANDARD | REVIEW
178 | Task | dateBegin | Due Date And Time | YES | YES | Activities Comments |  | STANDARD | REVIEW
179 | Task | dateEnd | Date End | YES | YES | Activities Comments |  | STANDARD | REVIEW
180 | Task | description | Description | YES | YES | Activities Comments |  | STANDARD | REVIEW
181 | Task | isPrivate | Visibility | YES | YES | Activities Comments |  | STANDARD | REVIEW
182 | Task | jobPostingID | Job | YES | YES | Activities Comments |  | STANDARD | REVIEW
183 | Task | leadUserID | Lead | YES | YES | Activities Comments |  | STANDARD | REVIEW
184 | Task | notificationMinutes | Reminder | YES | YES | Activities Comments |  | STANDARD | REVIEW
185 | Task | opportunityJobPostingID | Opportunity | YES | YES | Activities Comments |  | STANDARD | REVIEW
186 | Task | placementID | Placement | YES | YES | Activities Comments |  | STANDARD | REVIEW
187 | Task | priority | Priority | YES | YES | Activities Comments |  | STANDARD | REVIEW
188 | Task | recurrenceDayBits | Recurrence Day Bits | YES | YES | Activities Comments |  | STANDARD | REVIEW
189 | Task | recurrenceFrequency | Recurrence Frequency | YES | YES | Activities Comments |  | STANDARD | REVIEW
190 | Task | recurrenceMax | Recurrence Max | YES | YES | Activities Comments |  | STANDARD | REVIEW
191 | Task | recurrenceMonthBits | Recurrence Month Bits | YES | YES | Activities Comments |  | STANDARD | REVIEW
192 | Task | recurrenceStyle | Recurrence Style | YES | YES | Activities Comments |  | STANDARD | REVIEW
193 | Task | recurrenceType | Recurrence Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
194 | Task | subject | Subject | YES | YES | Activities Comments |  | STANDARD | REVIEW
195 | Task | type | Type | YES | YES | Activities Comments |  | STANDARD | REVIEW
196 | Task | userID | Owner | YES | YES | Activities Comments |  | STANDARD | REVIEW
197 | Work History | bonus | Bonus | YES | YES | Employment History |  | STANDARD | REVIEW
198 | Work History | clientCorporationID | Client Corporation | YES | YES | Employment History |  | STANDARD | REVIEW
199 | Work History | comments | Comments | YES | YES | Employment History |  | STANDARD | REVIEW
200 | Work History | commission | Commission | YES | YES | Employment History |  | STANDARD | REVIEW
201 | Work History | companyName | Company Name | YES | YES | Employment History |  | STANDARD | REVIEW
202 | Work History | dateAdded | Date Added | YES | YES | Employment History |  | STANDARD | REVIEW
203 | Work History | endDate | End Date | YES | YES | Employment History |  | STANDARD | REVIEW
204 | Work History | jobPostingID | Job Posting | YES | YES | Employment History |  | STANDARD | REVIEW
205 | Work History | placementID | Placement | YES | YES | Employment History |  | STANDARD | REVIEW
206 | Work History | salary1 | Salary Low | YES | YES | Employment History |  | STANDARD | REVIEW
207 | Work History | salary2 | Salary High | YES | YES | Employment History |  | STANDARD | REVIEW
208 | Work History | salaryType | Salary Type | YES | YES | Employment History |  | STANDARD | REVIEW
209 | Work History | startDate | Start Date | YES | YES | Employment History |  | STANDARD | REVIEW
210 | Work History | terminationReason | Termination Reason | YES | YES | Employment History |  | STANDARD | REVIEW
211 | Work History | title | Title | YES | YES | Employment History |  | STANDARD | REVIEW
212 | Work History | userWorkHistoryID | User Work History ID | YES | YES | Employment History |  | STANDARD | REVIEW

## 5. Job Application Stage Mappin
No | Bullhorn Stage | Required ? | Vincere Stage | Comments
1 | Candidate Interested | YES | SHORTLISTED
2 | Client Submission | YES | SENT
3 | Interview Scheduled | YES | FIRST_INTERVIEW
4 | New Lead | YES | SHORTLISTED
5 | Placed | YES | PLACED
6 | Sales Rep Rejected | YES | SHORTLISTED
7 | Submission | YES | SHORTLISTED
8 | Submitted | YES | SHORTLISTED
Note: At this stage any REJECTED state will not be mapped to REJECTED status in Vincere due to the difference in the data structure. So all REJECTED candidates will be moved to the PENDING state of the SHORTLISTED stage.
Job Types
No | Bullhorn Employment Type | Required ? | Vincere Job Type | Comments
1 | Permanent | YES | PERMANENT
2 | Temp | YES | TEMPORARY
| Job Placements (PLACED) | NOTE: All fields listed below are NON-CORE fields. They can be migrated only thru Custom Scripts.
No | Bullhorn DB Placement Fields | Bullhorn UI Placement Fields | Core | Required ? | Vincere Field | Comments | STANDARD / CUSTOM | REVIEW SITE / PRODUCTION SITE
1 | approvingUserID | Approving Client Contact | NO | NO | Placement Note | CUSTOM | PRODUCTION
2 | backupApprovingUserID | Backup Approving Client Contact | NO | NO | Placement Note | CUSTOM | PRODUCTION
3 | billingFrequency | Billing Frequency | NO | NO | Placement Note | CUSTOM | PRODUCTION
4 | billingUserID | Billing Contact | NO | NO | Placement Note | CUSTOM | PRODUCTION
5 | billRateInfoHeader | Bill Rate Information | NO | NO | Placement Note | CUSTOM | PRODUCTION
6 | bonusPackage | Bonus Package | NO | NO | Placement Note | CUSTOM | PRODUCTION
7 | branchID | Branch ID | NO | NO | Placement Note | CUSTOM | PRODUCTION
8 | candidateOwner | Candidate Owner | NO | NO | Placement Note | CUSTOM | PRODUCTION
9 | candidateSource | Candidate Source | NO | NO | Placement Note | CUSTOM | PRODUCTION
10 | canEnterTime | Can Enter Time | NO | NO | Placement Note | CUSTOM | PRODUCTION
11 | clientBillRate | Bill Rate | NO | NO | Placement Note | CUSTOM | PRODUCTION
12 | clientOverTimeRate | Over-time Bill Rate | NO | NO | Placement Note | CUSTOM | PRODUCTION
13 | comments | Comments | NO | NO | Placement Note | CUSTOM | PRODUCTION
14 | correlatedCustomText1 | Primary Timesheet Approver | NO | NO | Placement Note | CUSTOM | PRODUCTION
15 | correlatedCustomText10 | correlatedCustomText10 | NO | NO | Placement Note | CUSTOM | PRODUCTION
16 | correlatedCustomText2 | Secondary Timecard Approver | NO | NO | Placement Note | CUSTOM | PRODUCTION
17 | correlatedCustomText3 | Purchase Order Number | NO | NO | Placement Note | CUSTOM | PRODUCTION
18 | correlatedCustomText4 | Primary Approver's Email | NO | NO | Placement Note | CUSTOM | PRODUCTION
19 | correlatedCustomText5 | Secondary Approver's Email | NO | NO | Placement Note | CUSTOM | PRODUCTION
20 | costCenter | Cost Center | NO | NO | Placement Note | CUSTOM | PRODUCTION
21 | customBillRate1 | OT 12Hr | NO | NO | Placement Note | CUSTOM | PRODUCTION
22 | customBillRate10 | Custom 10 | NO | NO | Placement Note | CUSTOM | PRODUCTION
23 | customBillRate2 | Specialty | NO | NO | Placement Note | CUSTOM | PRODUCTION
24 | customBillRate3 | Holiday | NO | NO | Placement Note | CUSTOM | PRODUCTION
25 | customBillRate4 | Call Back | NO | NO | Placement Note | CUSTOM | PRODUCTION
26 | customBillRate5 | On Call | NO | NO | Placement Note | CUSTOM | PRODUCTION
27 | customBillRate6 | Charge | NO | NO | Placement Note | CUSTOM | PRODUCTION
28 | customBillRate7 | Shut Down | NO | NO | Placement Note | CUSTOM | PRODUCTION
29 | customBillRate8 | Flat | NO | NO | Placement Note | CUSTOM | PRODUCTION
30 | customBillRate9 | Long-Term | NO | NO | Placement Note | CUSTOM | PRODUCTION
31 | customPayRate1 | OT 12Hr | NO | NO | Placement Note | CUSTOM | PRODUCTION
32 | customPayRate10 | Custom 10 | NO | NO | Placement Note | CUSTOM | PRODUCTION
33 | customPayRate2 | Specialty | NO | NO | Placement Note | CUSTOM | PRODUCTION
34 | customPayRate3 | Holiday | NO | NO | Placement Note | CUSTOM | PRODUCTION
35 | customPayRate4 | Call Back | NO | NO | Placement Note | CUSTOM | PRODUCTION
36 | customPayRate5 | On Call | NO | NO | Placement Note | CUSTOM | PRODUCTION
37 | customPayRate6 | Charge | NO | NO | Placement Note | CUSTOM | PRODUCTION
38 | customPayRate7 | Shut Down | NO | NO | Placement Note | CUSTOM | PRODUCTION
39 | customPayRate8 | Flat | NO | NO | Placement Note | CUSTOM | PRODUCTION
40 | customPayRate9 | Long-Term | NO | NO | Placement Note | CUSTOM | PRODUCTION
41 | customText1 | Insurance Reference | NO | NO | Placement Note | CUSTOM | PRODUCTION
42 | dateAdded | Date Added | NO | NO | Placement Note | CUSTOM | PRODUCTION
43 | dateBegin | Start Date | NO | NO | Placement Note | CUSTOM | PRODUCTION
44 | dateClientEffective | Effective Date (Client) | NO | NO | Placement Note | CUSTOM | PRODUCTION
45 | dateEffective | Effective Date | NO | NO | Placement Note | CUSTOM | PRODUCTION
46 | dateEnd | Scheduled End | NO | NO | Placement Note | CUSTOM | PRODUCTION
47 | DateLastModified | Date Last Modified | NO | NO | Placement Note | CUSTOM | PRODUCTION
48 | daysGuaranteed | Days Guaranteed | NO | NO | Placement Note | CUSTOM | PRODUCTION
49 | daysProRated | Days Pro-Rated | NO | NO | Placement Note | CUSTOM | PRODUCTION
50 | durationWeeks | Job Duration | NO | NO | Placement Note | CUSTOM | PRODUCTION
51 | employeeType | Employee Type | NO | NO | Placement Note | CUSTOM | PRODUCTION
52 | employmentType | Employment Type | NO | NO | Placement Note | CUSTOM | PRODUCTION
53 | expiringCredentials | # Expiring Credentials | NO | NO | Placement Note | CUSTOM | PRODUCTION
54 | fee | Placement Fee (%) | NO | NO | Placement Note | CUSTOM | PRODUCTION
55 | flatFee | Placement Fee (Flat) | NO | NO | Placement Note | CUSTOM | PRODUCTION
56 | hoursOfOperation | Hours of Operation | NO | NO | Placement Note | CUSTOM | PRODUCTION
57 | hoursPerDay | Hours Per Day | NO | NO | Placement Note | CUSTOM | PRODUCTION
58 | housingAmenityID | Housing Amenities | NO | NO | Placement Note | CUSTOM | PRODUCTION
59 | housingManagerID | Housing Manager | NO | NO | Placement Note | CUSTOM | PRODUCTION
60 | housingStatus | Housing Status | NO | NO | Placement Note | CUSTOM | PRODUCTION
61 | incompleteRequirements | # Incomplete Requirements | NO | NO | Placement Note | CUSTOM | PRODUCTION
62 | invoiceGroup | Invoice Grouping | NO | NO | Placement Note | CUSTOM | PRODUCTION
63 | isMultirate | Rate Entry Type | NO | NO | Placement Note | CUSTOM | PRODUCTION
64 | jobAssignments | Assigned to | NO | NO | Placement Note | CUSTOM | PRODUCTION
65 | jobClientCorporationID | Client Company | NO | NO | Placement Note | CUSTOM | PRODUCTION
66 | jobClientUserID | Contact | NO | NO | Placement Note | CUSTOM | PRODUCTION
67 | jobPostingID | Job # | NO | NO | Placement Note | CUSTOM | PRODUCTION
68 | jobResponseID | Submission | NO | NO | Placement Note | CUSTOM | PRODUCTION
69 | jobResponseStatus | Submission Status | NO | NO | Placement Note | CUSTOM | PRODUCTION
70 | jobTitle | Job Title | NO | NO | Placement Note | CUSTOM | PRODUCTION
71 | jobUserID | Owner | NO | NO | Placement Note | CUSTOM | PRODUCTION
72 | lastApprovedPlacementChangeRequestID | Last Approved Placement Change Request | NO | NO | Placement Note | CUSTOM | PRODUCTION
73 | markUpPercentage | Mark-up % | NO | NO | Placement Note | CUSTOM | PRODUCTION
74 | migrateGUID | Migrate GUID | NO | NO | Placement Note | CUSTOM | PRODUCTION
75 | modifyingUser | Modifying User | NO | NO | Placement Note | CUSTOM | PRODUCTION
76 | numApprovedChangeRequests | # Changes Approved | NO | NO | Placement Note | CUSTOM | PRODUCTION
77 | numSubmittedChangeRequests | # Changes Waiting Approval | NO | NO | Placement Note | CUSTOM | PRODUCTION
78 | optionsPackage | Options Package | NO | NO | Placement Note | CUSTOM | PRODUCTION
79 | otExemption | Overtime Exemption | NO | NO | Placement Note | CUSTOM | PRODUCTION
80 | overtimeMarkUpPercentage | OT Mark-up % | NO | NO | Placement Note | CUSTOM | PRODUCTION
81 | overtimeRate | Over-time Pay Rate | NO | NO | Placement Note | CUSTOM | PRODUCTION
82 | owners | Owners | NO | NO | Placement Note | CUSTOM | PRODUCTION
83 | payRate | Pay Rate | NO | NO | Placement Note | CUSTOM | PRODUCTION
84 | placementCertifications | Requirement | NO | NO | Placement Note | CUSTOM | PRODUCTION
85 | placementID | Placement # | NO | NO | Placement Note | CUSTOM | PRODUCTION
86 | projectCodeList | Project Code List | NO | NO | Placement Note | CUSTOM | PRODUCTION
87 | quitJob | Quit Job | NO | NO | Placement Note | CUSTOM | PRODUCTION
88 | recruitingManagerPercentGrossMargin | Recruiting Manager Commission Over-ride % | NO | NO | Placement Note | CUSTOM | PRODUCTION
89 | referralFeeType | Referral Fee Type | NO | NO | Placement Note | CUSTOM | PRODUCTION
90 | reportedMargin | Reported Margin | NO | NO | Placement Note | CUSTOM | PRODUCTION
91 | reportTo | Reporting to | NO | NO | Placement Note | CUSTOM | PRODUCTION
92 | salary | Salary | NO | NO | Placement Note | CUSTOM | PRODUCTION
93 | salaryUnit | Pay Unit | NO | NO | Placement Note | CUSTOM | PRODUCTION
94 | salesManagerPercentGrossMargin | Sales Manager Commission Over-ride % | NO | NO | Placement Note | CUSTOM | PRODUCTION
95 | shiftID | Shift | NO | NO | Placement Note | CUSTOM | PRODUCTION
96 | statementUserID | Statement Contact | NO | NO | Placement Note | CUSTOM | PRODUCTION
97 | status | Status | NO | NO | Placement Note | CUSTOM | PRODUCTION
98 | taxRate | Tax % | NO | NO | Placement Note | CUSTOM | PRODUCTION
99 | taxState | Tax State | NO | NO | Placement Note | CUSTOM | PRODUCTION
100 | terminationReason | Termination Reason | NO | NO | Placement Note | CUSTOM | PRODUCTION
101 | timeUnitID | Time Units | NO | NO | Placement Note | CUSTOM | PRODUCTION
102 | userID | Candidate | NO | NO | Placement Note | CUSTOM | PRODUCTION
103 | vendorClientCorporationID | Umbrella Company | NO | NO | Placement Note | CUSTOM | PRODUCTION
104 | workersCompRateID | Workers Comp Code | NO | NO | Placement Note | CUSTOM | PRODUCTION
105 | workWeekStart | Work Week Begin | NO | NO | Placement Note | CUSTOM | PRODUCTION

## 6. CUSTOM FIELD Industry Mappin
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Business Sector Field | Required ? | Vincere Industry Field | Comments
1 |  |  | TBD by Vincere | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
23
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
25
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM FIELD Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment
|  |  | TBD by Vincere | TBD by Vincere | TBD by Vincere

## 8. CUSTOM FIELD Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM FIELD Candidate Sour
Candidate Source Field
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SOURCE Field values | Required ? | Vincere Candidate Source values | Comment

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
[5 empty] | Total : | 0
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.