## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Bullhorn CRM
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
No | Date | Category | Customer Questions | Sample Data | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference

## 1. Company Fields Mapping
FinTop to Vincere Fields Mapping (COMPANY) |  |  |  | Status: | Completed |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn DB Tablename | Bullhorn CRM DB Fieldname | Bullhorn CRM UI Fieldname | Required ? | Vincere Field | CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client | address1 | Main Address | Yes | Location Address | YES |  | STANDARD | REVIEW
2 | Client | address2 |  | Yes | Location Address | YES |  | STANDARD | REVIEW
3 | Client | billingAddress1 | Billing Address | No | Location Address | YES | Prefix the keyword "Billing" to the Location Name | STANDARD | REVIEW
4 | Client | billingAddress2 |  | No | Location Address | YES |  | STANDARD | REVIEW
5 | Client | billingCity | Billing City | No | Location Address Location City Location Name | YES | Prefix the keyword "Billing" to the Location Name | STANDARD | REVIEW
6 | Client | billingContact | Billing Contact | Yes | NOTE | YES |  | STANDARD | REVIEW
7 | Client | billingPhone | Billing Phone | Yes | NOTE | YES |  | STANDARD | REVIEW
8 | Client | billingState | Billing County | No | Location Address Location County Location Name | YES | Prefix the keyword "Billing" to the Location Name | STANDARD | REVIEW
9 | Client | billingZip | Billing Post Code | No | Location Address Location Postal / Zip Code Location Name | YES | Prefix the keyword "Billing" to the Location Name | STANDARD | REVIEW
10 | Client | businessSectorList | Industries | Yes | INDUSTRY | NO |  | CUSTOM | PRODUCTION
11 | Client | city | City | Yes | Location Address Location City Location Name | YES |  | STANDARD | REVIEW
12 | Client | companyDescription | Company Description | Yes | NOTE | YES |  | STANDARD | REVIEW
13 | Client | companyURL | Company Website | Yes | Website | YES |  | STANDARD | REVIEW
14 | Client | countryID | Country | Yes | Location Address Location Country Location Name | YES |  | STANDARD | REVIEW
15 | Client | fax | Main Fax | No | NOTE | YES |  | STANDARD | REVIEW
16 | Client | feeArrangement | Standard Fee Arrangement (%) | Yes | NOTE | YES |  | STANDARD | REVIEW
17 | Client | fullAddress | Address | Yes | NOTE | YES |  | STANDARD | REVIEW
18 | Client | fullBillingAddress | Billing Address | NO | NOTE | YES |  | STANDARD | REVIEW
19 | Client | invoiceFormat | Invoice Format Information | NO | NOTE | YES |  | STANDARD | REVIEW
20 | Client | name | Company Name | Yes | Company Name | YES |  | STANDARD | REVIEW
21 | Client | notes | Company Comments | Yes | Activities Comments | YES |  | STANDARD | REVIEW
22 | Client | numEmployees | # of Employees | Yes | No. of Employees | YES |  | STANDARD | REVIEW
23 | Client | numOffices | # of Offices | Yes | NOTE | YES |  | STANDARD | REVIEW
24 | Client | parentClientCorporationID | Parent Company | No | NOTE | YES |  | STANDARD | REVIEW
25 | Client | phone | Main Phone | Yes | Phone | YES |  | STANDARD | REVIEW
26 | Client | state | County | NO | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
27 | Client | status | Status | NO | NOTE | YES |  | STANDARD | REVIEW
28 | Client | taxRate | Tax % | Yes | NOTE | YES |  | STANDARD | REVIEW
29 | Client | zip | Post Code | Yes | Location Address Location Postal / Zip Code Location Name | YES |  | STANDARD | REVIEW
30 | Company File Attachment | name | Name | Yes | FILES | YES |  | STANDARD | REVIEW
31 | Company File Attachment | type | Type | NO | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 2. Contact Fields Mapping
Bullhorn CRM to Vincere Fields Mapping (CONTACTS) |  |  |  | Status: | Completed |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn DB Tablename | Bullhorn CRM DB Field Name | Bullhorn CRM UI Field Name | Required ? | Vincere Field | CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client Contact | address1 | Address | No | Personal Location Address | YES | Contact Location note would need to be selected manually from the Company Locations. During data migration, the location information stored in the contact will be migrated to Contact's Personal Location fields. | STANDARD | REVIEW
2 | Client Contact | address2 |  | NO | Personal Location Address | YES |  | STANDARD | REVIEW
3 | Client Contact | businessSectorID | Desired Industry Experience | Yes | INDUSTRY | YES |  | CUSTOM | PRODUCTION
4 | Client Contact | categoryID | Desired Categories | Yes | FUNCTIONAL EXPERTISE | YES |  | CUSTOM | PRODUCTION
5 | Client Contact | city | City | No | Personal Location Address Personal Location City Personal Location Name | YES |  | STANDARD | REVIEW
6 | Client Contact | clientCorporationID | Company | Yes | Company External ID | YES |  | STANDARD | REVIEW
7 | Client Contact | comments | General Comments | Yes | NOTE | YES |  | STANDARD | REVIEW
8 | Client Contact | countryID | Country | No | Personal Location Address Personal Location Country Personal Location Name | YES |  | STANDARD | REVIEW
9 | Client Contact | customText1 | LinkedIn Profile | Yes | LinkedIn | YES |  | STANDARD | REVIEW
10 | Client Contact | division | Department | Yes | Department | YES |  | STANDARD | REVIEW
11 | Client Contact | email | Work Email | Yes | Primary Email | YES |  | STANDARD | REVIEW
12 | Client Contact | email2 | Personal Email | Yes | Personal Email | YES |  | STANDARD | REVIEW
13 | Client Contact | fax | Fax | NO | NOTE | YES |  | STANDARD | REVIEW
14 | Client Contact | firstName | First Name | Yes | First Name | YES |  | STANDARD | REVIEW
15 | Client Contact | fullAddress | Address | No | NOTE | YES |  | STANDARD | REVIEW
16 | Client Contact | lastName | Surname | Yes | Last Name | YES |  | STANDARD | REVIEW
17 | Client Contact | middleName | Middle Name | Yes | Middle Name | YES |  | STANDARD | REVIEW
18 | Client Contact | mobile | Mobile Phone | Yes | Mobile Phone | YES |  | STANDARD | REVIEW
19 | Client Contact | namePrefix | Title | Yes | Title | YES |  | STANDARD | REVIEW
20 | Client Contact | nickName | Known As | Yes | Preferred Name | YES |  | STANDARD | REVIEW
21 | Client Contact | npsIsEnrolled | Enrolled in NPS | NO | NOTE | YES |  | STANDARD | REVIEW
22 | Client Contact | occupation | Job Title | Yes | Job Title | YES |  | STANDARD | REVIEW
23 | Client Contact | phone | Work Phone | Yes | Primary Phone | YES |  | STANDARD | REVIEW
24 | Client Contact | phone2 | Other Phone | Yes | Personal Phone | YES |  | STANDARD | REVIEW
25 | Client Contact | recruiterUserID | Consultant | Yes | Contact Owners | YES |  | STANDARD | REVIEW
26 | Client Contact | referredByUserID | Referred By | Yes | NOTE | YES |  | STANDARD | REVIEW
27 | Client Contact | reportToUserID | Reports to | Yes | NOTE | YES |  | STANDARD | REVIEW
28 | Client Contact | skillID | Desired Skills | NO | SUB FUNCTIONAL EXPERTISE | YES |  | CUSTOM | PRODUCTION
29 | Client Contact | state | County | NO | Personal Location Address Personal Location county Personal Location Name | YES |  | STANDARD | REVIEW
30 | Client Contact | status | Status | NO | NOTE | YES |  | STANDARD | REVIEW
31 | Client Contact | type | Type | Yes | NOTE | YES |  | STANDARD | REVIEW
32 | Client Contact | zip | Post Code | NO | Personal Location Address Personal Location ZIP (Postal) Code Personal Location Name | YES |  | STANDARD | REVIEW
33 | Contact File Attachment | name | Name | Yes | FILES | YES |  | STANDARD | REVIEW
34 | Contact File Attachment | type | Type | Yes | FILES | YES |  | STANDARD | REVIEW
35 | Note | action | Action | Yes | Activities Comments | YES |  | STANDARD | REVIEW
36 | Note | commentingUserID | Created by | Yes | Activities Comments | YES |  | STANDARD | REVIEW
37 | Note | comments | Comments | Yes | Activities Comments | YES |  | STANDARD | REVIEW
38 | Note | dateAdded | Date Added | Yes | Activities Comments | YES |  | STANDARD | REVIEW
39 | Note | userID | About Who | Yes | Activities Comments | YES |  | STANDARD | REVIEW
40 | Task | candidateUserID | Candidate | Yes | Activities Comments | YES |  | STANDARD | REVIEW
41 | Task | childTaskOwners | Assigned To | Yes | Activities Comments | YES |  | STANDARD | REVIEW
42 | Task | clientUserID | Contact | Yes | Activities Comments | YES |  | STANDARD | REVIEW
43 | Task | dateBegin | Due Date And Time | Yes | Activities Comments | YES |  | STANDARD | REVIEW
44 | Task | dateEnd | Date End | Yes | Activities Comments | YES |  | STANDARD | REVIEW
45 | Task | description | Description | Yes | Activities Comments | YES |  | STANDARD | REVIEW
46 | Task | jobPostingID | Job | Yes | Activities Comments | YES |  | STANDARD | REVIEW
47 | Task | priority | Priority | Yes | Activities Comments | YES |  | STANDARD | REVIEW
48 | Task | subject | Subject | Yes | Activities Comments | YES |  | STANDARD | REVIEW
49 | Task | type | Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
50 | Task | userID | Owner | Yes | Activities Comments | YES |  | STANDARD | REVIEW
51 | Appointment | candidateUserID | Candidate | Yes | Activities Comments | YES |  | STANDARD | REVIEW
52 | Appointment | clientUserID | Contact | Yes | Activities Comments | YES |  | STANDARD | REVIEW
53 | Appointment | communicationMethod | Communication Method | Yes | Activities Comments | YES |  | STANDARD | REVIEW
54 | Appointment | dateBegin | Start Date | Yes | Activities Comments | YES |  | STANDARD | REVIEW
55 | Appointment | dateEnd | End Date | Yes | Activities Comments | YES |  | STANDARD | REVIEW
56 | Appointment | description | Description | Yes | Activities Comments | YES |  | STANDARD | REVIEW
57 | Appointment | guests | Attendees | Yes | Activities Comments | YES |  | STANDARD | REVIEW
58 | Appointment | isPrivate | Visibility | Yes | Activities Comments | YES |  | STANDARD | REVIEW
59 | Appointment | jobPostingID | Job | Yes | Activities Comments | YES |  | STANDARD | REVIEW
60 | Appointment | location | Location | Yes | Activities Comments | YES |  | STANDARD | REVIEW
61 | Appointment | subject | Subject | Yes | Activities Comments | YES |  | STANDARD | REVIEW
62 | Appointment | type | Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
63 | Appointment | userID | Owner | Yes | Activities Comments | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 3. Candidate Fields Mapping
Bullhorn CRMto Vincere Fields Mapping (Candidates) |  |  |  | Status: | Completed |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn CRM Section | Bullhorn CRM DB Field | Bullhorn CRM UI Field | Required ? | Vincere Field | Core Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Candidate | address1 | Home Address | Yes | Current Location Address | YES |  | STANDARD | REVIEW
2 | Candidate | address2 |  | Yes | Current Location Address | YES |  | STANDARD | REVIEW
3 | Candidate | businessSectorID | Industries | Yes | INDUSTRY | YES |  | CUSTOM | PRODUCTION
4 | Candidate | categoryID | Job Categories | Yes | FUNCTIONAL EXPERTISE | YES |  | CUSTOM | PRODUCTION
5 | Candidate | city | City | Yes | Current Location Address Current Location City Current Location Name | YES |  | STANDARD | REVIEW
6 | Candidate | comments | General Comments | Yes | Brief Note | YES |  | STANDARD | REVIEW
7 | Candidate | companyName | Current Company | Yes | Current Employer | YES |  | STANDARD | REVIEW
8 | Candidate | companyURL | LinkedIn Profile | Yes | LinkedIn URL | YES |  | STANDARD | REVIEW
9 | Candidate | countryID | Country | Yes | Current Location Address Current Location Country Current Location Name | YES |  | STANDARD | REVIEW
10 | Candidate | customText1 | LTD Company Name | Yes | Brief Note | YES |  | STANDARD | REVIEW
11 | Candidate | customText2 | LTD Company No. | Yes | Brief Note | YES |  | STANDARD | REVIEW
12 | Candidate | customText3 | LTD Company Phone | NO | Brief Note | YES |  | STANDARD | REVIEW
13 | Candidate | customText4 | Notice Period | Yes | Brief Note | YES |  | STANDARD | REVIEW
14 | Candidate | dateAvailable | Date Available | Yes | Brief Note | YES |  | STANDARD | REVIEW
15 | Candidate | dateAvailableEnd | Available Until | Yes | Brief Note | YES |  | STANDARD | REVIEW
16 | Candidate | dayRate | Desired Daily Rate | Yes | Desired Rate Desired Rate Type (Daily) | YES |  | STANDARD | REVIEW
17 | Candidate | dayRateLow | Current Daily Rate | Yes | Current Rate Current Rate Type (Daily) | YES |  | STANDARD | REVIEW
18 | Candidate | description | CV | Yes | Current CV | YES |  | STANDARD | REVIEW
19 | Candidate | email | Personal Email | Yes | Primary Email | YES |  | STANDARD | REVIEW
20 | Candidate | email2 | Work Email | Yes | Work Email | YES |  | STANDARD | REVIEW
21 | Candidate | employeeType | Employee Payment Type | Yes | Brief Note | YES |  | STANDARD | REVIEW
22 | Candidate | employmentPreference | Employment Preference | Yes | Brief Note | YES |  | STANDARD | REVIEW
23 | Candidate | firstName | First Name | Yes | First Name | YES |  | STANDARD | REVIEW
24 | Candidate | fullAddress | Address | Yes | Current Location Address | YES |  | STANDARD | REVIEW
25 | Candidate | hourlyRate | Desired Hourly Rate | Yes | Brief Note | YES |  | STANDARD | REVIEW
26 | Candidate | hourlyRateLow | Current Hourly Rate | Yes | Brief Note | YES |  | STANDARD | REVIEW
27 | Candidate | lastName | Surname | Yes | Last Name | YES |  | STANDARD | REVIEW
28 | Candidate | latestComment | Latest Comment | Yes | Brief Note | YES |  | STANDARD | REVIEW
29 | Candidate | middleName | Middle Name | Yes | Middle Name | YES |  | STANDARD | REVIEW
30 | Candidate | mobile | Mobile Phone | Yes | Mobile Phone | YES |  | STANDARD | REVIEW
31 | Candidate | namePrefix | Title | Yes | Title | YES |  | STANDARD | REVIEW
32 | Candidate | nickName | Known As | Yes | Preferred Name | YES |  | STANDARD | REVIEW
33 | Candidate | occupation | Current Job Title | Yes | Job Title | YES |  | STANDARD | REVIEW
34 | Candidate | phone | Home Phone | Yes | Home Phone | YES |  | STANDARD | REVIEW
35 | Candidate | recruiterUserID | Consultant | Yes | Candidate Owners | YES |  | STANDARD | REVIEW
36 | Candidate | referredByUserID | Referred by | Yes | Brief Note | YES |  | STANDARD | REVIEW
37 | Candidate | salary | Desired Annual Salary | Yes | Desired Salary Salary Type (Annual) | YES |  | STANDARD | REVIEW
38 | Candidate | salaryLow | Current Annual Salary | Yes | Current Salary Salary Type (Annual) | YES |  | STANDARD | REVIEW
39 | Candidate | secondaryAddress1 | LTD Company Address | NO | Brief Note | YES |  | STANDARD | REVIEW
40 | Candidate | secondaryAddress2 |  | NO | Brief Note | YES |  | STANDARD | REVIEW
41 | Candidate | secondaryCity | LTD Company City | NO | Brief Note | YES |  | STANDARD | REVIEW
42 | Candidate | secondaryCountryID | LTD Company Country | NO | Brief Note | YES |  | STANDARD | REVIEW
43 | Candidate | secondaryState | LTD Company County | NO | Brief Note | YES |  | STANDARD | REVIEW
44 | Candidate | secondaryZip | LTD Company Post Code | NO | Brief Note | YES |  | STANDARD | REVIEW
45 | Candidate | skillID | Skills | Yes | SUB FUNCTIONAL EXPERTSE | YES |  | CUSTOM | PRODUCTION
46 | Candidate | source | Source | Yes | CANDIDATE SOURCE | YES |  | CUSTOM | PRODUCTION
47 | Candidate | specialtyCategoryID | Specialties | Yes | Skills | YES |  | STANDARD | REVIEW
48 | Candidate | state | County | Yes | Current Location Address Current Location Country Current Location Name | YES |  | STANDARD | REVIEW
49 | Candidate | status | Status | yes | Brief Note | YES |  | STANDARD | REVIEW
50 | Candidate | willRelocate | Willing to Relocate | yes | Brief Note | YES |  | STANDARD | REVIEW
51 | Candidate | workPhone | Work Phone | No | Work Phone | YES |  | STANDARD | REVIEW
52 | Candidate | zip | Post Code | yes | Current Location Address Current Location ZIP (Postal) Code Current Location Name | YES |  | STANDARD | REVIEW
53 | Candidate File Attachment | name | Name | yes | FILES | YES |  | STANDARD | REVIEW
54 | Candidate File Attachment | type | Type | Yes | FILES | YES |  | STANDARD | REVIEW
55 | CandidateCertification | boardCertification | Board Certification | No | Education Summary | YES |  | STANDARD | REVIEW
56 | CandidateCertification | candidateCredentialNote | Comments | No | Education Summary | YES |  | STANDARD | REVIEW
57 | CandidateCertification | certificationID | Requirement Type | No | Education Summary | YES |  | STANDARD | REVIEW
58 | CandidateCertification | compact | Compact | No | Education Summary | YES |  | STANDARD | REVIEW
59 | CandidateCertification | dateCertified | Date Certified | No | Education Summary | YES |  | STANDARD | REVIEW
60 | CandidateCertification | dateExpiration | Expiration Date | No | Education Summary | YES |  | STANDARD | REVIEW
61 | CandidateCertification | issuingAuthority | Issuing Authority | No | Education Summary | YES |  | STANDARD | REVIEW
62 | CandidateCertification | licenseNumber | License Number | No | Education Summary | YES |  | STANDARD | REVIEW
63 | CandidateCertification | licenseType | License Type | No | Education Summary | YES |  | STANDARD | REVIEW
64 | CandidateCertification | name | Credential | No | Education Summary | YES |  | STANDARD | REVIEW
65 | CandidateCertification | onFile | On File | No | Education Summary | YES |  | STANDARD | REVIEW
66 | CandidateCertification | results | Results | No | Education Summary | YES |  | STANDARD | REVIEW
67 | CandidateCertification | status | Status | NO | Education Summary | YES |  | STANDARD | REVIEW
68 | CandidateCertification | validLocations | Locations | NO | Education Summary | YES |  | STANDARD | REVIEW
69 | Education | certification | Certification | NO | Education Summary | YES |  | STANDARD | REVIEW
70 | Education | city | City | NO | Education Summary | YES |  | STANDARD | REVIEW
71 | Education | comments | Comments | NO | Education Summary | YES |  | STANDARD | REVIEW
72 | Education | dateAdded | Date Added | NO | Education Summary | YES |  | STANDARD | REVIEW
73 | Education | degree | Degree | NO | Education Summary | YES |  | STANDARD | REVIEW
74 | Education | endDate | End Date | NO | Education Summary | YES |  | STANDARD | REVIEW
75 | Education | expirationDate | Certification Expiration Date | NO | Education Summary | YES |  | STANDARD | REVIEW
76 | Education | graduationDate | Graduation Date | NO | Education Summary | YES |  | STANDARD | REVIEW
77 | Education | school | School | NO | Education Summary | YES |  | STANDARD | REVIEW
78 | Education | startDate | Start Date | NO | Education Summary | YES |  | STANDARD | REVIEW
79 | Education | state | County | NO | Education Summary | YES |  | STANDARD | REVIEW
80 | Education | userEducationID | Education ID | NO | Education Summary | YES |  | STANDARD | REVIEW
81 | Note | action | Action | Yes | Activities Comments | YES |  | STANDARD | REVIEW
82 | Note | commentingUserID | Created by | Yes | Activities Comments | YES |  | STANDARD | REVIEW
83 | Note | comments | Comments | Yes | Activities Comments | YES |  | STANDARD | REVIEW
84 | Note | dateAdded | Date Added | Yes | Activities Comments | YES |  | STANDARD | REVIEW
85 | Note | userID | About Who | Yes | Activities Comments | YES |  | STANDARD | REVIEW
86 | Reference | candidateTitle | Candidate Title | Yes | Brief Note | YES |  | STANDARD | REVIEW
87 | Reference | clientCorporationID | Client Corporation | Yes | Brief Note | YES |  | STANDARD | REVIEW
88 | Reference | companyName | Company | Yes | Brief Note | YES |  | STANDARD | REVIEW
89 | Reference | dateAdded | Date Added | Yes | Brief Note | YES |  | STANDARD | REVIEW
90 | Reference | employmentEnd | Employment End | Yes | Brief Note | YES |  | STANDARD | REVIEW
91 | Reference | employmentStart | Employment Start | Yes | Brief Note | YES |  | STANDARD | REVIEW
92 | Reference | jobPostingID | Job Posting | Yes | Brief Note | YES |  | STANDARD | REVIEW
93 | Reference | referenceEmail | Reference Email | Yes | Brief Note | YES |  | STANDARD | REVIEW
94 | Reference | referenceFirstName | Reference First Name | Yes | Brief Note | YES |  | STANDARD | REVIEW
95 | Reference | referenceLastName | Reference Last Name | Yes | Brief Note | YES |  | STANDARD | REVIEW
96 | Reference | referencePhone | Reference Phone | Yes | Brief Note | YES |  | STANDARD | REVIEW
97 | Reference | referenceTitle | Reference Title | Yes | Brief Note | YES |  | STANDARD | REVIEW
98 | Reference | referenceUserID | Reference | Yes | Brief Note | YES |  | STANDARD | REVIEW
99 | Reference | status | Status | Yes | Brief Note | YES |  | STANDARD | REVIEW
100 | Reference | userReferenceID | Reference ID | Yes | Brief Note | YES |  | STANDARD | REVIEW
101 | Reference | yearsKnown | Years Known | Yes | Brief Note | YES |  | STANDARD | REVIEW
102 | Task | candidateUserID | Candidate | Yes | Activities Comments | YES |  | STANDARD | REVIEW
103 | Task | childTaskOwners | Assigned To | Yes | Activities Comments | YES |  | STANDARD | REVIEW
104 | Task | clientUserID | Contact | Yes | Activities Comments | YES |  | STANDARD | REVIEW
105 | Task | dateBegin | Due Date And Time | Yes | Activities Comments | YES |  | STANDARD | REVIEW
106 | Task | dateEnd | Date End | Yes | Activities Comments | YES |  | STANDARD | REVIEW
107 | Task | description | Description | Yes | Activities Comments | YES |  | STANDARD | REVIEW
108 | Task | isPrivate | Visibility | Yes | Activities Comments | YES |  | STANDARD | REVIEW
109 | Task | jobPostingID | Job | Yes | Activities Comments | YES |  | STANDARD | REVIEW
110 | Task | leadUserID | Lead | Yes | Activities Comments | YES |  | STANDARD | REVIEW
111 | Task | notificationMinutes | Reminder | Yes | Activities Comments | YES |  | STANDARD | REVIEW
112 | Task | opportunityJobPostingID | Opportunity | Yes | Activities Comments | YES |  | STANDARD | REVIEW
113 | Task | placementID | Placement | Yes | Activities Comments | YES |  | STANDARD | REVIEW
114 | Task | priority | Priority | Yes | Activities Comments | YES |  | STANDARD | REVIEW
115 | Task | recurrenceDayBits | Recurrence Day Bits | Yes | Activities Comments | YES |  | STANDARD | REVIEW
116 | Task | recurrenceFrequency | Recurrence Frequency | Yes | Activities Comments | YES |  | STANDARD | REVIEW
117 | Task | recurrenceMax | Recurrence Max | Yes | Activities Comments | YES |  | STANDARD | REVIEW
118 | Task | recurrenceMonthBits | Recurrence Month Bits | Yes | Activities Comments | YES |  | STANDARD | REVIEW
119 | Task | recurrenceStyle | Recurrence Style | Yes | Activities Comments | YES |  | STANDARD | REVIEW
120 | Task | recurrenceType | Recurrence Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
121 | Task | subject | Subject | Yes | Activities Comments | YES |  | STANDARD | REVIEW
122 | Task | type | Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
123 | Task | userID | Owner | Yes | Activities Comments | YES |  | STANDARD | REVIEW
124 | Work History | bonus | Bonus | NO | Work History Summary | YES |  | STANDARD | REVIEW
125 | Work History | clientCorporationID | Company Name | NO | Work History Summary | YES |  | STANDARD | REVIEW
126 | Work History | comments | Comments | NO | Work History Summary | YES |  | STANDARD | REVIEW
127 | Work History | commission | Commission | NO | Work History Summary | YES |  | STANDARD | REVIEW
128 | Work History | companyName | Company Name | NO | Work History Summary | YES |  | STANDARD | REVIEW
129 | Work History | endDate | End Date | NO | Work History Summary | YES |  | STANDARD | REVIEW
130 | Work History | jobPostingID | Job Posting | NO | Work History Summary | YES |  | STANDARD | REVIEW
131 | Work History | salary1 | Salary Low | NO | Work History Summary | YES |  | STANDARD | REVIEW
132 | Work History | salary2 | Salary High | NO | Work History Summary | YES |  | STANDARD | REVIEW
133 | Work History | salaryType | Salary Type | NO | Work History Summary | YES |  | STANDARD | REVIEW
134 | Work History | startDate | Start Date | NO | Work History Summary | YES |  | STANDARD | REVIEW
135 | Work History | terminationReason | Termination Reason | NO | Work History Summary | YES |  | STANDARD | REVIEW
136 | Work History | title | Job Title | NO | Work History Summary | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 4. Job Fields Mapping
Bullhorn CRM to Vincere Fields Mapping (JOB) |  |  |  | Status: | Completed |  |  | 3 Custom Scripts are inclusive to the Data Migration Prohect.
1 Additional Custom Script = 200 USD one time fee
No | Bullhorn CRM Section | Bullhorn CRM DB Field Name | Bullhorn CRM UI Field Name | Required ? | Vincere Field | Core Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Job Posting | address | Address | Yes | Note | YES | Job Location note would need to be selected manually from the selected Contact Locations. During data migration, the location information stored in the job will be migrated to Job's Note fields. | STANDARD | REVIEW
2 | Job Posting | businessSectorID | Industries | Yes | INDUSTRY | YES |  | CUSTOM | PRODUCTION
3 | Job Posting | categoryID | Job Category | Yes | FUNCTIONAL EXPERTISE | YES |  | CUSTOM | PRODUCTION
4 | Job Posting | city | City | Yes | Note | YES |  | STANDARD | REVIEW
5 | Job Posting | clientBillRate | Bill Rate | Yes | Note | YES |  | STANDARD | REVIEW
6 | Job Posting | clientCorporationID | Client | Yes | Company External ID | YES |  | STANDARD | REVIEW
7 | Job Posting | clientUserID | Contact | Yes | Contact External ID | YES |  | STANDARD | REVIEW
9 | Job Posting | countryID | Country | Yes | Note | YES |  | STANDARD | REVIEW
10 | Job Posting | dateEnd | Scheduled End Date | Yes | Closed Date | YES |  | STANDARD | REVIEW
11 | Job Posting | description | Internal Description | Yes | Internal Job Description | YES |  | STANDARD | REVIEW
13 | Job Posting | employmentType | Employment Type | Yes | Job Type | YES |  | STANDARD | REVIEW
14 | Job Posting | feeArrangement | Perm Fee (%) | Yes | Note | YES |  | STANDARD | REVIEW
15 | Job Posting | fullAddress | Address | Yes | Note | YES |  | STANDARD | REVIEW
16 | Job Posting | isOpen | Open/Closed | Yes | N/A | YES | If the flag is OPEN, the closed date will be set to 1 year from now. | STANDARD | REVIEW
18 | Job Posting | markUpPercentage | Mark-up % | Yes | Note | YES |  | STANDARD | REVIEW
19 | Job Posting | numOpenings | # of Openings | Yes | Headcount | YES |  | STANDARD | REVIEW
21 | Job Posting | payRate | Pay Rate | Yes | Job Type : Contract Pay Rate Rate Type: Hourly | YES |  | STANDARD | REVIEW
22 | Job Posting | publicDescription | Published Description | Yes | Public Job Description | YES |  | STANDARD | REVIEW
23 | Job Posting | salary | Salary | Yes | Annual Salary | YES |  | STANDARD | REVIEW
24 | Job Posting | salaryUnit | Pay Unit | Yes | Note | YES |  | STANDARD | REVIEW
25 | Job Posting | skillID | Required Skills | Yes | SUB FUNCTIONAL EXPERTISE | YES |  | CUSTOM | PRODUCTION
27 | Job Posting | source | Source | Yes | CANDIDATE SOURCES | YES |  | CUSTOM | PRODUCTION
28 | Job Posting | startDate | Start Date | Yes | Open Date | YES |  | STANDARD | REVIEW
29 | Job Posting | state | County | Yes | Note | YES |  | STANDARD | REVIEW
30 | Job Posting | status | Status | Yes | Note | YES |  | STANDARD | REVIEW
31 | Job Posting | title | Job Title | Yes | Job Title | YES |  | STANDARD | REVIEW
32 | Job Posting | userID | Consultant | Yes | Job Owners | YES |  | STANDARD | REVIEW
33 | Job Posting | zip | Postcode | Yes | Note | YES |  | STANDARD | REVIEW
34 | Appointment | candidateUserID | Candidate | Yes | Activities Comments | YES |  | STANDARD | REVIEW
35 | Appointment | clientUserID | Contact | Yes | Activities Comments | YES |  | STANDARD | REVIEW
36 | Appointment | communicationMethod | Communication Method | Yes | Activities Comments | YES |  | STANDARD | REVIEW
37 | Appointment | dateBegin | Start Date | Yes | Activities Comments | YES |  | STANDARD | REVIEW
38 | Appointment | dateEnd | End Date | Yes | Activities Comments | YES |  | STANDARD | REVIEW
39 | Appointment | description | Description | Yes | Activities Comments | YES |  | STANDARD | REVIEW
40 | Appointment | guests | Attendees | Yes | Activities Comments | YES |  | STANDARD | REVIEW
42 | Appointment | jobPostingID | Job | Yes | Activities Comments | YES |  | STANDARD | REVIEW
43 | Appointment | leadUserID | Lead | Yes | Activities Comments | YES |  | STANDARD | REVIEW
44 | Appointment | location | Location | Yes | Activities Comments | YES |  | STANDARD | REVIEW
45 | Appointment | notificationMinutes | Reminder | Yes | Activities Comments | YES |  | STANDARD | REVIEW
46 | Appointment | opportunityJobPostingID | Opportunity | Yes | Activities Comments | YES |  | STANDARD | REVIEW
53 | Appointment | subject | Subject | Yes | Activities Comments | YES |  | STANDARD | REVIEW
54 | Appointment | type | Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
55 | Appointment | userID | Owner | Yes | Activities Comments | YES |  | STANDARD | REVIEW
60 | Job Order File Attachment | name | Name | Yes | FILES | YES |  | STANDARD | REVIEW
61 | Job Order File Attachment | type | Type | Yes | FILES | YES |  | STANDARD | REVIEW
62 | Note | action | Action | Yes | Activities Comments | YES |  | STANDARD | REVIEW
63 | Note | commentingUserID | Created by | Yes | Activities Comments | YES |  | STANDARD | REVIEW
64 | Note | comments | Comments | Yes | Activities Comments | YES |  | STANDARD | REVIEW
65 | Note | dateAdded | Date Added | Yes | Activities Comments | YES |  | STANDARD | REVIEW
66 | Note | userID | About Who | Yes | Activities Comments | YES |  | STANDARD | REVIEW
67 | Task | candidateUserID | Candidate | Yes | Activities Comments | YES |  | STANDARD | REVIEW
68 | Task | childTaskOwners | Assigned To | Yes | Activities Comments | YES |  | STANDARD | REVIEW
69 | Task | clientUserID | Contact | Yes | Activities Comments | YES |  | STANDARD | REVIEW
70 | Task | dateBegin | Due Date And Time | Yes | Activities Comments | YES |  | STANDARD | REVIEW
71 | Task | dateEnd | Date End | Yes | Activities Comments | YES |  | STANDARD | REVIEW
72 | Task | description | Description | Yes | Activities Comments | YES |  | STANDARD | REVIEW
73 | Task | isPrivate | Visibility | Yes | Activities Comments | YES |  | STANDARD | REVIEW
74 | Task | jobPostingID | Job | Yes | Activities Comments | YES |  | STANDARD | REVIEW
79 | Task | priority | Priority | Yes | Activities Comments | YES |  | STANDARD | REVIEW
86 | Task | subject | Subject | Yes | Activities Comments | YES |  | STANDARD | REVIEW
87 | Task | type | Type | Yes | Activities Comments | YES |  | STANDARD | REVIEW
88 | Task | userID | Owner | Yes | Activities Comments | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 5. Job Application Stage Mappin
|  | Status: | Completed
No | Bullhorn CRM Stage | Required ? | Vincere Stage | Comments | STANDARD / CUSTOM | TARGET INSTANCE
1 | 1st Interview | Yes | FIRST_INTERVIEW |  | STANDARD | REVIEW
2 | 2nd Interview | Yes | SECOND_INTERVIEW |  | STANDARD | REVIEW
3 | 3rd Interview | Yes | SECOND_INTERVIEW |  | STANDARD | REVIEW
4 | Candidate Rejected | Yes | SHORTLISTED > REJECTED |  | CUSTOM | PRODUCTION
5 | Client Rejected | Yes | SHORTLISTED > REJECTED |  | CUSTOM | PRODUCTION
6 | CV Sent | Yes | SENT |  | STANDARD | REVIEW
7 | Final Interview | Yes | SECOND_INTERVIEW |  | STANDARD | REVIEW
8 | Placed | Yes | PLACED |  | STANDARD | REVIEW
9 | Shortlisted | Yes | SHORTLISTED |  | STANDARD | REVIEW
10 | Submitted | No | SHORTLISTED |  | STANDARD | REVIEW
Note: REJECTED state can only be mapped to SHORTLISTED > Rejected stage thru CUSTOM SCRIPT. SUB-STATUS could also be mapped thru CUSTOM SCRIPT if required. SUB-STATUS is configurable status field in Vincere where user can configure the definition accordingly.
Job Types
No | Bullhorn CRM Employment Type | Required ? | Vincere Job Type | Comments
1 | Contract | Yes | CONTRACT
2 | Permanent | Yes | PERMANENT
3 | Temporary | NO | TEMPORARY

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
1 | Company | businessSectorList | INDUSTRY | PRODUCTION | 1 Custom Script is required to migrate the industry list and populate each tags accordingly to each records. | 1
2 | Contact | businessSectorID | INDUSTRY | PRODUCTION | Covered by item 1 | 0
3 | Contact | categoryID | FUNCTIONAL EXPERTISE | PRODUCTION | 1 Custom Script is required to migrate the Functional Expertise List and populate each tags accordingly to each records. | 1
4 | Candidate | businessSectorID | INDUSTRY | PRODUCTION | Covered by item 1 | 0
5 | Candidate | categoryID | FUNCTIONAL EXPERTISE | PRODUCTION | Covered by item 3 | 0
6 | Candidate | skillID | SUB FUNCTIONAL EXPERTISE | PRODUCTION | 1 Custom Script is required to migrate the Sub Functional Expertise List and populate each tags accordingly to each records. | 1
7 | Candidate | source | CANDIDATE SOURCES | PRODUCTION | 1 Custom Script is required to migrate the Candidate Sources and populate each tags accordingly to each records. | 1
8 | Job | Candidate Rejected Client Rejected | Job Application > Shortlisted > Rejected |  | 1 Custom Script is required to migrate the Rejected status of the Job Application stage on each of the Job Application records | 1
[5 empty] | Total : | 5
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.

## 6. CUSTOM SCRIPT Industry Mappi
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM Business Sector Field | Required ? | Vincere Industry Field | Comments
1 |  |  | TBD by Vincere | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
23
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
25
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM SCRIPT Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment

## 8. CUSTOM SCRIPT Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD by Vincere
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM SCRIPT Candidate Sou
Candidate Source Field
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn CRM SOURCE Field values | Required ? | Vincere Candidate Source values | Comment