## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Bullhorn
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
Date | Category | Customer Questions | Sample Data | Migration Issue ? | Issue Type | Can be fixed by Migration ? | When fix is applied ? | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference
2018-09-20 | CONTACT & CANDIDATES | Listing as candidate: Rob Turner - First Solar: no mobile listed on Vincere, half notes not pulled accross - screenshot in sample data. ALSO not listed as contact at all notes ect all missing | https://ibb.co/cJ9L4z | YES | MIGRATION SCRIPT | YES | PRODUCTION | 2018-09-20 | 1. The Activities Comments --> The comments was found in the database but it is currently linking to different contact. Could be due to the different database cut over date. Will include this with the final migration with the 2nd database backup. 2. Mobile Phone --> The phone is found in the CONTACT > Mobile Phone on the 2nd Database not 1st Database.
2018-09-20 | CANDIDATES | Matthew Christian - not listed anywhere on test system - added to BH 08/05/2018, candidate ID is 1227 |  | NO | NO ISSUE | NOT APPLICABLE | NOT APPLICABLE | 2018-09-20 | The Candidate exist in Vincere. The ID is 63213

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
1 | Company | businessSectorList | INDUSTRY | PRODUCTION | 1 Custom Script is required to map it to the INDUSTRY list of values for Company, Contacts, Jobs and Candidates. | 1
2 | Contact | Desired Industry Experience | INDUSTRY | PRODUCTION | Covered under item 1. | 0
3 | Contact | Desired Category | FUNCTIONAL EXPERTISE | PRODUCTION | 1 Custom Script is required to map it to the FUNCTIONAL EXPERTISE Contacts, Jobs and Candidates. | 1
4 | Candidate | Industries | INDUSTRY | PRODUCTION | Covered under item 1. | 0
5 | Candidate | Job Categories | FUNCTIONAL EXPERTISE | PRODUCTION | Covered under item 3. | 0
6 | Candidate | Skills | SUB FUNCTIONAL EXPERTISE | PRODUCTION | 1 Custom Script is required to map it to the SUB FUNCTIONAL EXPERTISE of the Candidates. | 1
7 | Candidate | Sources | CANDIDATE SOURCES | PRODUCTION | 1 Custom Script is required to map it to the CANDIDATE SOURCES of the Candidates. | 1
8 | Job | Industries | INDUSTRY | PRODUCTION | Covered under item 1. | 0
9 | Job | Job Category | FUNCTIONAL EXPERTISE | PRODUCTION | Covered under item 3. | 0
10 | Job | skillID | SUB FUNCTIONAL EXPERTISE | PRODUCTION | Covered under item 6. | 0
[5 empty] | Total : | 4
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.

## 1. Company Fields Mapping
Bullhorn to Vincere Fields Mapping (COMPANY) |  |  | STATUS : | In Progress |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client | ClientCorporationID | Company ID | Yes | Company External ID | YES |  | STANDARD | REVIEW
2 | Client | address1 | Main Address | Yes | Location Address | YES |  | STANDARD | REVIEW
3 | Client | address2 |  | Yes | Location Address | YES |  | STANDARD | REVIEW
4 | Client | billingAddress1 | Billing Address | Yes | Location Address | YES | Append the word "Billing" to Location Name | STANDARD | REVIEW
5 | Client | billingAddress2 |  | Yes | Location Address | YES | Append the word "Billing" to Location Name | STANDARD | REVIEW
6 | Client | billingCity | Billing City | Yes | Location Address Location City Location Name | YES |  | STANDARD | REVIEW
7 | Client | billingContact | Billing Contact | Yes | NOTE | YES |  | STANDARD | REVIEW
8 | Client | billingPhone | Billing Phone | Yes | NOTE | YES |  | STANDARD | REVIEW
9 | Client | billingState | Billing County | Yes | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
10 | Client | billingZip | Billing Post Code | Yes | Location Address Location ZIP (Postal) Code Location Name | YES |  | STANDARD | REVIEW
11 | Client | businessSectorList | Industries | Yes | INDUSTRY | NO |  | CUSTOM | PRODUCTION
12 | Client | city | City | Yes | Location Address Location Town / City Location Name | YES |  | STANDARD | REVIEW
13 | Client | companyDescription | Company Description | Yes | NOTE | YES |  | STANDARD | REVIEW
14 | Client | companyURL | Company Website | Yes | Website | YES |  | STANDARD | REVIEW
15 | Client | countryID | Country | Yes | Location Address Location Country Location Name | YES |  | STANDARD | REVIEW
16 | Client | fax | Main Fax | Yes | NOTE | YES |  | STANDARD | REVIEW
17 | Client | feeArrangement | Standard Fee Arrangement (%) | Yes | NOTE | YES |  | STANDARD | REVIEW
18 | Client | fullAddress | Address | Yes | NOTE | YES |  | STANDARD | REVIEW
19 | Client | fullBillingAddress | Billing Address | Yes | NOTE | YES |  | STANDARD | REVIEW
20 | Client | invoiceFormat | Invoice Format Information | Yes | NOTE | YES |  | STANDARD | REVIEW
21 | Client | name | Company Name | Yes | Company Name | YES |  | STANDARD | REVIEW
22 | Client | notes | Company Comments | Yes | Activities Comments | YES |  | STANDARD | REVIEW
23 | Client | numEmployees | # of Employees | Yes | No. of Employees | YES |  | STANDARD | REVIEW
24 | Client | numOffices | # of Offices | Yes | NOTE | YES |  | STANDARD | REVIEW
25 | Client | parentClientCorporationID | Parent Company | Yes | NOTE | YES |  | STANDARD | REVIEW
26 | Client | phone | Main Phone | Yes | Phone | YES |  | STANDARD | REVIEW
27 | Client | state | County | Yes | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
28 | Client | status | Status | Yes | NOTE | YES |  | STANDARD | REVIEW
29 | Client | taxRate | Tax % | Yes | Location Address Location ZIP (Postal) Code Location Name | YES |  | STANDARD | REVIEW
30 | Client | zip | Post Code | Yes | Location Address Location ZIP (Postal) Code Location Name | YES |  | STANDARD | REVIEW
31 | Company File Attachment | name | Name | Yes | FILES | YES |  | STANDARD | REVIEW
32 | Company File Attachment | type | Type | Yes | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 2. Contact Fields Mapping
Bullhorn to Vincere Fields Mapping (CONTACTS) |  |  | STATUS : | In Progress |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client Contact | address1 | Address | yes | Location Address | YES | This is the record ID of Bullhorn. Vincere will need to migrate it and populate it to the Contact External ID to identify the correct Contact records to be migrated. | STANDARD | REVIEW
2 | Client Contact | address2 |  | yes | Location Address | YES |  | STANDARD | REVIEW
3 | Client Contact | businessSectorID | Desired Industry Experience | NO | INDUSTRY | NO |  | CUSTOM | PRODUCTION
4 | Client Contact | categoryID | Desired Categories | NO | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
5 | Client Contact | city | City | yes | Location Address Location City / Town Location Name | YES |  | STANDARD | REVIEW
6 | Client Contact | clientCorporationID | Company | yes | Company External ID | YES |  | STANDARD | REVIEW
7 | Client Contact | comments | General Comments | yes | NOTE | YES |  | STANDARD | REVIEW
8 | Client Contact | countryID | Country | yes | Location Address Location Country Location Name | YES |  | STANDARD | REVIEW
9 | Client Contact | division | Department | yes | Department | YES |  | STANDARD | REVIEW
10 | Client Contact | email | Work Email | yes | Primary Email | YES |  | STANDARD | REVIEW
11 | Client Contact | email2 | Personal Email | yes | Personal Email | YES |  | STANDARD | REVIEW
12 | Client Contact | fax | Fax | yes | NOTE | YES |  | STANDARD | REVIEW
13 | Client Contact | firstName | First Name | yes | Contact First Name | YES |  | STANDARD | REVIEW
14 | Client Contact | fullAddress | Address | yes | NOTE | YES |  | STANDARD | REVIEW
15 | Client Contact | lastName | Surname | yes | Last Name | YES |  | STANDARD | REVIEW
16 | Client Contact | middleName | Middle Name | yes | Middle Name | YES |  | STANDARD | REVIEW
17 | Client Contact | mobile | Mobile Phone | yes | Mobile Phone | YES |  | STANDARD | REVIEW
18 | Client Contact | namePrefix | Title | yes | Title | YES |  | STANDARD | REVIEW
19 | Client Contact | nickName | Known As | yes | Preferred Name | YES |  | STANDARD | REVIEW
20 | Client Contact | npsIsEnrolled | Enrolled in NPS | yes | NOTE | YES | Not Found | STANDARD | REVIEW
21 | Client Contact | occupation | Job Title | yes | Job Title | YES |  | STANDARD | REVIEW
22 | Client Contact | phone | Work Phone | yes | Work Phone | YES |  | STANDARD | REVIEW
23 | Client Contact | phone2 | Other Phone | yes | NOTE | YES |  | STANDARD | REVIEW
24 | Client Contact | recruiterUserID | Consultant | yes | Contact Owners | YES |  | STANDARD | REVIEW
25 | Client Contact | referredByUserID | Referred By | yes | NOTE | YES |  | STANDARD | REVIEW
26 | Client Contact | reportToUserID | Reports to | yes | NOTE | YES |  | STANDARD | REVIEW
27 | Client Contact | secondaryOwners | Secondary Owners | yes | Contact Owners | YES |  | STANDARD | REVIEW
28 | Client Contact | skillID | Desired Skills | yes | NOTE | YES |  | STANDARD | REVIEW
29 | Client Contact | state | County | yes | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
30 | Client Contact | status | Status | yes | NOTE | YES |  | STANDARD | REVIEW
31 | Client Contact | type | Type | yes | NOTE | YES |  | STANDARD | REVIEW
32 | Client Contact | zip | Post Code | yes | Location Address Location ZIP (Postal) Code Location Name | YES |  | STANDARD | REVIEW
33 | Contact File Attachment | name | Name | yes | FILES | YES |  | STANDARD | REVIEW
34 | Contact File Attachment | type | Type | yes | FILES | YES |  | STANDARD | REVIEW
35 | Note | action | Action | yes | Activities Comments | YES |  | STANDARD | REVIEW
36 | Note | commentingUserID | Created by | yes | Activities Comments | YES |  | STANDARD | REVIEW
37 | Note | comments | Comments | yes | Activities Comments | YES |  | STANDARD | REVIEW
38 | Note | dateAdded | Date Added | yes | Activities Comments | YES |  | STANDARD | REVIEW
39 | Note | userID | About Who | yes | Activities Comments | YES |  | STANDARD | REVIEW
40 | JOBS | JOBS | JOBS | yes | JOBS | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 3. Candidate Fields Mapping
Bullhorn to Vincere Fields Mapping (Candidates) |  |  | STATUS : | In Progress |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Candidate | address1 | Home Address | yes | Current Address > Location Address | YES |  | STANDARD | REVIEW
2 | Candidate | address2 |  | yes | Current Address > Location Address | YES |  | STANDARD | REVIEW
3 | Candidate | businessSectorID | Industries | NO | INDUSTRY | NO |  | CUSTOM | PRODUCTION
4 | Candidate | categoryID | Job Categories | NO | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
5 | Candidate | city | City | yes | Current Address > Location Address Current Address > Location City Current Address > Location Name | YES |  | STANDARD | REVIEW
6 | Candidate | comments | General Comments | yes | Brief Note | YES |  | STANDARD | REVIEW
7 | Candidate | companyName | Current Company | yes | Company Name | YES |  | STANDARD | REVIEW
8 | Candidate | countryID | Country | yes | Current Address > Location Address Current Address > Location Country Current Address > Location Name | YES |  | STANDARD | REVIEW
9 | Candidate | customText1 | LTD Company Name | yes | Brief Note | YES |  | STANDARD | REVIEW
10 | Candidate | customText2 | LTD Company No. | yes | Brief Note | YES |  | STANDARD | REVIEW
11 | Candidate | customText3 | LTD Company Phone | yes | Brief Note | YES |  | STANDARD | REVIEW
12 | Candidate | customText4 | Notice Period | yes | Brief Note | YES |  | STANDARD | REVIEW
13 | Candidate | dateAvailable | Date Available | yes | Brief Note | YES |  | STANDARD | REVIEW
14 | Candidate | dateAvailableEnd | Available Until | yes | Brief Note | YES |  | STANDARD | REVIEW
15 | Candidate | dayRate | Desired Daily Rate | yes | Brief Note | YES |  | STANDARD | REVIEW
16 | Candidate | dayRateLow | Current Daily Rate | yes | Brief Note | YES |  | STANDARD | REVIEW
17 | Candidate | description | CV | yes | Brief Note | YES |  | STANDARD | REVIEW
18 | Candidate | email | Personal Email | yes | Personal Email | YES |  | STANDARD | REVIEW
19 | Candidate | email2 | Work Email | yes | Work Email | YES |  | STANDARD | REVIEW
20 | Candidate | employeeType | Employee Payment Type | yes | Brief Note | YES |  | STANDARD | REVIEW
21 | Candidate | employmentPreference | Employment Preference | yes | Brief Note | YES |  | STANDARD | REVIEW
22 | Candidate | firstName | First Name | yes | First Name | YES |  | STANDARD | REVIEW
23 | Candidate | fullAddress | Address | yes | Brief Note | YES |  | STANDARD | REVIEW
24 | Candidate | hourlyRate | Desired Hourly Rate | yes | Brief Note | YES |  | STANDARD | REVIEW
25 | Candidate | hourlyRateLow | Current Hourly Rate | yes | Brief Note | YES |  | STANDARD | REVIEW
26 | Candidate | lastName | Surname | yes | Last Name | YES |  | STANDARD | REVIEW
27 | Candidate | latestComment | Latest Comment | yes | Brief Note | YES |  | STANDARD | REVIEW
28 | Candidate | middleName | Middle Name | yes | Middle Name | YES |  | STANDARD | REVIEW
29 | Candidate | mobile | Mobile Phone | yes | Primary Phone Mobile Phone | YES |  | STANDARD | REVIEW
30 | Candidate | namePrefix | Title | yes | Title | YES |  | STANDARD | REVIEW
31 | Candidate | nickName | Known As | yes | Preferred Name | YES |  | STANDARD | REVIEW
32 | Candidate | occupation | Current Job Title | yes | Job Title | YES |  | STANDARD | REVIEW
33 | Candidate | phone | Home Phone | yes | Home Phone | YES |  | STANDARD | REVIEW
34 | Candidate | recruiterUserID | Consultant | yes | Candidate Owners | YES |  | STANDARD | REVIEW
35 | Candidate | referredByUserID | Referred by | yes | Brief Note | YES |  | STANDARD | REVIEW
36 | Candidate | salary | Desired Annual Salary | yes | Desired Annual Salary | YES |  | STANDARD | REVIEW
37 | Candidate | salaryLow | Current Annual Salary | yes | Current Annual Salary | YES |  | STANDARD | REVIEW
38 | Candidate | secondaryAddress1 | LTD Company Address | yes | Brief Note | YES |  | STANDARD | REVIEW
39 | Candidate | secondaryAddress2 |  | yes | Brief Note | YES |  | STANDARD | REVIEW
40 | Candidate | secondaryCity | LTD Company City | yes | Brief Note | YES |  | STANDARD | REVIEW
41 | Candidate | secondaryCountryID | LTD Company Country | yes | Brief Note | YES |  | STANDARD | REVIEW
42 | Candidate | secondaryState | LTD Company County | yes | Brief Note | YES |  | STANDARD | REVIEW
43 | Candidate | secondaryZip | LTD Company Post Code | yes | Brief Note | YES |  | STANDARD | REVIEW
44 | Candidate | skillID | Skills | NO | SUB FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
45 | Candidate | source | Source | NO | CANDIDATE SOURCES | NO |  | CUSTOM | PRODUCTION
46 | Candidate | state | County | yes | Current Address > Location Address Current Address > Location State / County Current Address > Location Name | YES |  | STANDARD | REVIEW
47 | Candidate | status | Status | yes | Brief Note | YES |  | STANDARD | REVIEW
48 | Candidate | willRelocate | Willing to Relocate | yes | Brief Note | YES |  | STANDARD | REVIEW
49 | Candidate | workPhone | Work Phone | yes | Work Phone | YES |  | STANDARD | REVIEW
50 | Candidate | zip | Post Code | yes | Current Address > Location Address Current Address > ZIP (Postal) Code Current Address > Location Name | YES |  | STANDARD | REVIEW
51 | Candidate File Attachment | name | Name | yes | FILES | YES |  | STANDARD | REVIEW
52 | Candidate File Attachment | type | Type | yes | FILES | YES |  | STANDARD | REVIEW
53 | CandidateCertification | boardCertification | Board Certification | yes | Education Summary | YES |  | STANDARD | REVIEW
54 | CandidateCertification | candidateCredentialNote | Comments | yes | Education Summary | YES |  | STANDARD | REVIEW
55 | CandidateCertification | certificationID | Requirement Type | yes | Education Summary | YES |  | STANDARD | REVIEW
56 | CandidateCertification | compact | Compact | yes | Education Summary | YES |  | STANDARD | REVIEW
57 | CandidateCertification | dateCertified | Date Certified | yes | Education Summary | YES |  | STANDARD | REVIEW
58 | CandidateCertification | dateExpiration | Expiration Date | yes | Education Summary | YES |  | STANDARD | REVIEW
59 | CandidateCertification | issuingAuthority | Issuing Authority | yes | Education Summary | YES |  | STANDARD | REVIEW
60 | CandidateCertification | licenseNumber | License Number | yes | Education Summary | YES |  | STANDARD | REVIEW
61 | CandidateCertification | licenseType | License Type | yes | Education Summary | YES |  | STANDARD | REVIEW
62 | CandidateCertification | name | Credential | yes | Education Summary | YES |  | STANDARD | REVIEW
63 | CandidateCertification | onFile | On File | yes | Education Summary | YES |  | STANDARD | REVIEW
64 | CandidateCertification | results | Results | yes | Education Summary | YES |  | STANDARD | REVIEW
65 | CandidateCertification | status | Status | yes | Education Summary | YES |  | STANDARD | REVIEW
66 | CandidateCertification | validLocations | Locations | yes | Education Summary | YES |  | STANDARD | REVIEW
67 | Education | certification | Certification | yes | Education Summary | YES |  | STANDARD | REVIEW
68 | Education | city | City | yes | Education Summary | YES |  | STANDARD | REVIEW
69 | Education | comments | Comments | yes | Education Summary | YES |  | STANDARD | REVIEW
70 | Education | dateAdded | Date Added | yes | Education Summary | YES |  | STANDARD | REVIEW
71 | Education | degree | Degree | yes | Education Summary | YES |  | STANDARD | REVIEW
72 | Education | endDate | End Date | yes | Education Summary | YES |  | STANDARD | REVIEW
73 | Education | expirationDate | Certification Expiration Date | yes | Education Summary | YES |  | STANDARD | REVIEW
74 | Education | graduationDate | Graduation Date | yes | Education Summary | YES |  | STANDARD | REVIEW
75 | Education | school | School | yes | Education Summary | YES |  | STANDARD | REVIEW
76 | Education | startDate | Start Date | yes | Education Summary | YES |  | STANDARD | REVIEW
77 | Education | state | County | yes | Education Summary | YES |  | STANDARD | REVIEW
78 | Education | userEducationID | Education ID | yes | Education Summary | YES |  | STANDARD | REVIEW
79 | Note | action | Action | yes | Activities Comments | YES |  | STANDARD | REVIEW
80 | Note | commentingUserID | Created by | yes | Activities Comments | YES |  | STANDARD | REVIEW
81 | Note | comments | Comments | yes | Activities Comments | YES |  | STANDARD | REVIEW
82 | Note | dateAdded | Date Added | yes | Activities Comments | YES |  | STANDARD | REVIEW
83 | Note | userID | About Who | yes | Activities Comments | YES |  | STANDARD | REVIEW
84 | Reference | candidateTitle | Candidate Title | yes | Brief Note | YES |  | STANDARD | REVIEW
85 | Reference | clientCorporationID | Client Corporation | yes | Brief Note | YES |  | STANDARD | REVIEW
86 | Reference | companyName | Company | yes | Brief Note | YES |  | STANDARD | REVIEW
87 | Reference | dateAdded | Date Added | yes | Brief Note | YES |  | STANDARD | REVIEW
88 | Reference | employmentEnd | Employment End | yes | Brief Note | YES |  | STANDARD | REVIEW
89 | Reference | employmentStart | Employment Start | yes | Brief Note | YES |  | STANDARD | REVIEW
90 | Reference | jobPostingID | Job Posting | yes | Brief Note | YES |  | STANDARD | REVIEW
91 | Reference | referenceEmail | Reference Email | yes | Brief Note | YES |  | STANDARD | REVIEW
92 | Reference | referenceFirstName | Reference First Name | yes | Brief Note | YES |  | STANDARD | REVIEW
93 | Reference | referenceLastName | Reference Last Name | yes | Brief Note | YES |  | STANDARD | REVIEW
94 | Reference | referencePhone | Reference Phone | yes | Brief Note | YES |  | STANDARD | REVIEW
95 | Reference | referenceTitle | Reference Title | yes | Brief Note | YES |  | STANDARD | REVIEW
96 | Reference | referenceUserID | Reference | yes | Brief Note | YES |  | STANDARD | REVIEW
97 | Reference | status | Status | yes | Brief Note | YES |  | STANDARD | REVIEW
98 | Reference | userReferenceID | Reference ID | yes | Brief Note | YES |  | STANDARD | REVIEW
99 | Reference | yearsKnown | Years Known | yes | Brief Note | YES |  | STANDARD | REVIEW
100 | Work History | bonus | Bonus | yes | Work History Summary | YES |  | STANDARD | REVIEW
101 | Work History | clientCorporationID | Company Name | yes | Work History Summary | YES |  | STANDARD | REVIEW
102 | Work History | comments | Comments | yes | Work History Summary | YES |  | STANDARD | REVIEW
103 | Work History | commission | Commission | yes | Work History Summary | YES |  | STANDARD | REVIEW
104 | Work History | companyName | Company Name | yes | Work History Summary | YES |  | STANDARD | REVIEW
105 | Work History | endDate | End Date | yes | Work History Summary | YES |  | STANDARD | REVIEW
106 | Work History | jobPostingID | Job Posting | yes | Work History Summary | YES |  | STANDARD | REVIEW
107 | Work History | salary1 | Salary Low | yes | Work History Summary | YES |  | STANDARD | REVIEW
108 | Work History | salary2 | Salary High | yes | Work History Summary | YES |  | STANDARD | REVIEW
109 | Work History | salaryType | Salary Type | yes | Work History Summary | YES |  | STANDARD | REVIEW
110 | Work History | startDate | Start Date | yes | Work History Summary | YES |  | STANDARD | REVIEW
111 | Work History | terminationReason | Termination Reason | yes | Work History Summary | YES |  | STANDARD | REVIEW
112 | Work History | title | Job Title | yes | Work History Summary | YES |  | STANDARD | REVIEW
113 | Candidate | userID | User ID | yes | Candidate External ID | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 4. Job Fields Mapping
Bullhorn to Vincere Fields Mapping (JOB) |  |  | STATUS : | In Progress |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Job Posting | address | Address | yes | NOTE | YES |  | STANDARD | REVIEW
2 | Job Posting | businessSectorID | Industries | NO | INDUSTRY | NO |  | CUSTOM | PRODUCTION
3 | Job Posting | categoryID | Job Category | NO | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
4 | Job Posting | city | City | yes | NOTE | YES |  | STANDARD | REVIEW
5 | Job Posting | clientBillRate | Bill Rate | yes | NOTE | YES |  | STANDARD | REVIEW
6 | Job Posting | clientCorporationID | Client | yes | Company External ID | YES |  | STANDARD | REVIEW
7 | Job Posting | clientUserID | Contact | yes | Contact External ID | YES |  | STANDARD | REVIEW
8 | Job Posting | countryID | Country | yes | NOTE | YES |  | STANDARD | REVIEW
9 | Job Posting | dateEnd | Scheduled End Date | yes | Job Closed Date | YES |  | STANDARD | REVIEW
10 | Job Posting | description | Internal Description | yes | Internal Job Description | YES |  | STANDARD | REVIEW
11 | Job Posting | employmentType | Employment Type | yes | Job Type | YES |  | STANDARD | REVIEW
12 | Job Posting | feeArrangement | Perm Fee (%) | yes | NOTE | YES |  | STANDARD | REVIEW
13 | Job Posting | fullAddress | Address | yes | NOTE | YES |  | STANDARD | REVIEW
14 | Job Posting | isOpen | Open/Closed | yes | Job Status | YES | If OPEN, the closed date will be set 1 year from the open date. If it is CLOSED, the end date will be set to yesterday OR the date of the Job Closed Date if it is in the past. | STANDARD | REVIEW
15 | Job Posting | markUpPercentage | Mark-up % | yes | NOTE | YES |  | STANDARD | REVIEW
16 | Job Posting | numOpenings | # of Openings | yes | Headcount | YES |  | STANDARD | REVIEW
17 | Job Posting | payRate | Pay Rate | yes | NOTE | YES |  | STANDARD | REVIEW
18 | Job Posting | publicDescription | Published Description | yes | Public Job Application | YES |  | STANDARD | REVIEW
19 | Job Posting | salary | Salary | yes | Annual Salary | YES |  | STANDARD | REVIEW
20 | Job Posting | salaryUnit | Pay Unit | yes | NOTE | YES |  | STANDARD | REVIEW
21 | Job Posting | skillID | Required Skills | NO | SUB FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
22 | Job Posting | source | Source | yes | NOTE | NO |  | STANDARD | REVIEW
23 | Job Posting | startDate | Start Date | yes | Job Open Date | YES |  | STANDARD | REVIEW
24 | Job Posting | state | County | yes | NOTE | YES |  | STANDARD | REVIEW
25 | Job Posting | status | Status | yes | NOTE | YES |  | STANDARD | REVIEW
26 | Job Posting | title | Job Title | yes | Job Title | YES |  | STANDARD | REVIEW
27 | Job Posting | userID | Consultant | yes | Job Owners | YES |  | STANDARD | REVIEW
28 | Job Posting | zip | Postcode | yes | NOTE | YES |  | STANDARD | REVIEW
29 | Job Order File Attachment | name | Name | yes | FILES | YES |  | STANDARD | REVIEW
30 | Job Order File Attachment | type | Type | yes | FILES | YES |  | STANDARD | REVIEW
31 | Placement | billingFrequency | Billing Frequency | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
32 | Placement | billingUserID | Billing Contact | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
33 | Placement | clientBillRate | Bill Rate | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
34 | Placement | clientOverTimeRate | Bill Rate (Over-time) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
35 | Placement | comments | Comments | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
36 | Placement | customBillRate1 | Bill Rate (Weekend Rate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
37 | Placement | customBillRate2 | Bill Rate (International) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
38 | Placement | customInt3 | Number Previous Weeks | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
39 | Placement | customPayRate1 | Pay Rate (Weekend Rate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
40 | Placement | customPayRate2 | Pay Rate (International) | yes | FILES | YES |  | STANDARD | REVIEW
41 | Placement | customText5 | Other | yes | FILES | YES |  | STANDARD | REVIEW
42 | Placement | customText6 | Referral Fee | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
43 | Placement | customText7 | Travelling Expenses | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
44 | Placement | customTextBlock1 | Specific Contract Terms | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
45 | Placement | dateBegin | Start Date | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
46 | Placement | dateClientEffective | Bill Effective Date (Client) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
47 | Placement | dateEffective | Pay Effective Date (Candidate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
48 | Placement | dateEnd | End Date | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
49 | Placement | employeeType | Employee Payment Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
50 | Placement | employmentType | Employment Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
51 | Placement | fee | Placement Fee (%) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
52 | Placement | flatFee | Placement Fee (Flat) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
53 | Placement | hoursPerDay | Hours Per Day | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
54 | Placement | isMultirate | Rate Entry Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
55 | Placement | markUpPercentage | Mark-up % | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
56 | Placement | overtimeRate | Pay Rate (Over-time) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
57 | Placement | payRate | Pay Rate | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
58 | Placement | referralFeeType | Referral Fee Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
59 | Placement | salary | Salary | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
60 | Placement | salaryUnit | Pay Unit | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
61 | Placement | status | Status | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
62 | Placement | vendorClientCorporationID | Umbrella Company | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
63 | Placement File Attachment | name | Name | yes | FILES | YES |  | STANDARD | REVIEW
64 | Placement File Attachment | type | Type | yes | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 5. Job Application Stage Mappin
|  |  |  | STATUS : | In Review
No | Bullhorn Stage | Required ? | Vincere Stage | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | 1st Interview | YES | FIRST_INTERVIEW |  | STANDARD | REVIEW
2 | 2nd Interview | YES | SECOND_INTERVIEW |  | STANDARD | REVIEW
3 | CV Sent | YES | SENT |  | STANDARD | REVIEW
4 | Placed | YES | PLACED |  | STANDARD | REVIEW
Note: At this stage any REJECTED status can only be migrated to REJECTED status under the SHORTLISTED stage thru Custom Script work. This is not covered under our standard migration.
Job Types
No | Bullhorn Employment Type | Required ? | Vincere Job Type | Comments
1 | Contract | YES | CONTRACT
2 | Permanent | YES | PERMANENT

## 6. CUSTOM FIELD Industry Mappin
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Business Sector Field | Required ? | Vincere Industry Field | Comments
1 | TBD | TBD | TBD | TBD
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
23
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
25
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM FIELD Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment
| TBD | TBD | TBD | TBD | TBD

## 8. CUSTOM FIELD Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD |  | TBD | TBD
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM FIELD Candidate Sour
Candidate Source Field |  | Commented
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SOURCE Field values | Required ? | Vincere Candidate Source values | Comment
| TBD | TBD | TBD | TBD