## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Bullhorn
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
No | Date | Category | Customer Questions | Sample Data | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference

## 1. Company Fields Mapping
Bullhorn to Vincere Fields Mapping (COMPANY) |  |  | STATUS : | In Review |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client | Company ID | Company ID | YES | Company External ID | YES |  | STANDARD | REVIEW
2 | Client | address1 | Main Address | YES | Location Address | YES |  | STANDARD | REVIEW
3 | Client | address2 |  | YES | Location Address | YES |  | STANDARD | REVIEW
4 | Client | billingAddress1 | Billing Address | YES | Location Address | YES | Append the word "Billing" to Location Name | STANDARD | REVIEW
5 | Client | billingAddress2 |  | YES | Location Address | YES | Append the word "Billing" to Location Name | STANDARD | REVIEW
6 | Client | billingCity | Billing City | YES | Location Address Location City Location Name | YES |  | STANDARD | REVIEW
7 | Client | billingContact | Billing Contact | YES | NOTE | YES |  | STANDARD | REVIEW
8 | Client | billingPhone | Billing Phone | YES | NOTE | YES |  | STANDARD | REVIEW
9 | Client | billingState | Billing County | YES | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
10 | Client | billingZip | Billing Post Code | YES | Location Address Location ZIP (Postal) Location Name | YES |  | STANDARD | REVIEW
11 | Client | businessSectorList | Industries | YES | CUSTOM FIELD > INDUSTRY | YES |  | CUSTOM | PRODUCTION
12 | Client | city | City | YES | Location Address Location Town / City Location Name | YES |  | STANDARD | REVIEW
13 | Client | companyDescription | Company Bio | YES | NOTE | YES |  | STANDARD | REVIEW
14 | Client | companyURL | Company Website | YES | Website | YES |  | STANDARD | REVIEW
15 | Client | countryID | Country | YES | Location Address Location ZIP (Postal) Location Name | YES |  | STANDARD | REVIEW
16 | Client | customText1 | TV Business Area | YES | CUSTOM FIELD > TV Business Area | NO | LIst: Tempting Talent and Tempting Ventures | CUSTOM | PRODUCTION
17 | Client | customText3 | Commission Cycle | YES | NOTE | YES |  | STANDARD | REVIEW
18 | Client | customTextBlock1 | Commission Structure | YES | NOTE | YES |  | STANDARD | REVIEW
19 | Client | customTextBlock2 | Interview Prep | YES | NOTE | YES |  | STANDARD | REVIEW
20 | Client | feeArrangement | Standard Fee Arrangement (%) | YES | NOTE | YES |  | STANDARD | REVIEW
21 | Client | fullAddress | Address | YES | NOTE | YES |  | STANDARD | REVIEW
22 | Client | fullBillingAddress | Billing Address | YES | NOTE | YES |  | STANDARD | REVIEW
23 | Client | invoiceFormat | Invoice Format Information | YES | NOTE | YES |  | STANDARD | REVIEW
24 | Client | name | Company Name | YES | Company Name | YES |  | STANDARD | REVIEW
25 | Client | notes | Company Comments | YES | Activities Comments | YES |  | STANDARD | REVIEW
26 | Client | numEmployees | # of Employees | YES | No. of Employees | YES |  | STANDARD | REVIEW
27 | Client | numOffices | # of Offices | YES | NOTE | YES |  | STANDARD | REVIEW
28 | Client | parentClientCorporationID | Parent Company | YES | NOTE | YES |  | STANDARD | REVIEW
29 | Client | phone | Main Phone | YES | Phone | YES |  | STANDARD | REVIEW
30 | Client | state | County | YES | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
31 | Client | status | Status | YES | NOTE | YES |  | STANDARD | REVIEW
32 | Client | taxRate | Tax % | YES | NOTE | YES |  | STANDARD | REVIEW
33 | Client | zip | Post Code | YES | Location Address Location ZIP (Postal) Code Location Name | YES |  | STANDARD | REVIEW
34 | Company File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
35 | Company File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 2. Contact Fields Mapping
Bullhorn to Vincere Fields Mapping (CONTACTS) |  |  | STATUS : | In Review |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Client Contact | address1 | Address | YES | Location Address | YES | This is the record ID of Bullhorn. Vincere will need to migrate it and populate it to the Contact External ID to identify the correct Contact records to be migrated. | STANDARD | REVIEW
2 | Client Contact | address2 |  | YES | Location Address | YES |  | STANDARD | REVIEW
3 | Client Contact | businessSectorID | Desired Industry Experience | YES | CUSTOM FIELD > INDUSTRY | NO |  | CUSTOM | PRODUCTION
4 | Client Contact | categoryID | Desired Categories | YES | FUNCTIONAL EXPERTISE | NO |  | CUSTOM | PRODUCTION
5 | Client Contact | city | City | YES | Location Address Location City / Town Location Name | YES |  | STANDARD | REVIEW
6 | Client Contact | clientCorporationID | Company | YES | Company External ID | YES |  | STANDARD | REVIEW
7 | Client Contact | comments | General Comments | YES | NOTE | YES |  | STANDARD | REVIEW
8 | Client Contact | countryID | Country | YES | Location Address Location Country Location Name | YES |  | STANDARD | REVIEW
9 | Client Contact | customText1 | TV Business Area | YES | CUSTOM FIELD > TV Business Area | YES |  | CUSTOM | PRODUCTION
10 | Client Contact | division | Department | YES | Department | YES |  | STANDARD | REVIEW
11 | Client Contact | email | Work Email | YES | Primary Email | YES |  | STANDARD | REVIEW
12 | Client Contact | email2 | Personal Email | YES | Personal Email | YES |  | STANDARD | REVIEW
13 | Client Contact | firstName | First Name | YES | Contact First Name | YES |  | STANDARD | REVIEW
14 | Client Contact | fullAddress | Address | YES | NOTE | YES |  | STANDARD | REVIEW
15 | Client Contact | lastName | Surname | YES | Contact Last Name | YES |  | STANDARD | REVIEW
16 | Client Contact | mobile | Mobile Phone | YES | Mobile Phone | YES |  | STANDARD | REVIEW
17 | Client Contact | namePrefix | Title | YES | Title | YES |  | STANDARD | REVIEW
18 | Client Contact | nickName | Known As | YES | Preferred Name | YES |  | STANDARD | REVIEW
19 | Client Contact | npsIsEnrolled | Enrolled in NPS | YES | NOTE | YES |  | STANDARD | REVIEW
20 | Client Contact | occupation | Job Title | YES | Job Title | YES |  | STANDARD | REVIEW
21 | Client Contact | phone | Work Phone | YES | Work Phone | YES |  | STANDARD | REVIEW
22 | Client Contact | recruiterUserID | Consultant | YES | Contact Owners | YES |  | STANDARD | REVIEW
23 | Client Contact | referredByUserID | Referred By | YES | NOTE | YES |  | STANDARD | REVIEW
24 | Client Contact | reportToUserID | Reports to | YES | NOTE | YES |  | STANDARD | REVIEW
25 | Client Contact | secondaryOwners | Secondary Owners | YES | Contact Owners | YES |  | STANDARD | REVIEW
26 | Client Contact | skillID | Desired Skills | No |  | NO |  | CUSTOM | PRODUCTION
27 | Client Contact | state | County | YES | Location Address Location State Location Name | YES |  | STANDARD | REVIEW
28 | Client Contact | status | Status | YES | NOTE | YES |  | STANDARD | REVIEW
29 | Client Contact | zip | Post Code | YES | Location Address Location ZIP Location Name | YES |  | STANDARD | REVIEW
30 | Contact File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
31 | Contact File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
32 | Note | action | Action | YES | Activities Comments | YES |  | STANDARD | REVIEW
33 | Note | commentingUserID | Created by | YES | Activities Comments | YES |  | STANDARD | REVIEW
34 | Note | comments | Comments | YES | Activities Comments | YES |  | STANDARD | REVIEW
35 | Note | dateAdded | Date Added | YES | Activities Comments | YES |  | STANDARD | REVIEW
36 | Note | userID | About Who | YES | Activities Comments | YES |  | STANDARD | REVIEW
37 | JOBS | JOBS | JOBS | YES | JOBS | YES | VC: To be covered in 4. Job Fields Mapping tab. | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 4. Job Fields Mapping
Bullhorn to Vincere Fields Mapping (JOB) |  |  | STATUS : | In Review |  |  |  | 3 Custom Scripts are inclusive for all data sets.
1 Custom Script = 200 USD one time fee / additional custom script
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Job Posting | address | Address | YES | NOTE | YES |  | STANDARD | REVIEW
2 | Job Posting | businessSectorID | Industries | YES | CUSTOM FIELD > INDUSTRY | YES |  | CUSTOM | PRODUCTION
3 | Job Posting | city | City | YES | NOTE | YES |  | STANDARD | REVIEW
4 | Job Posting | clientCorporationID | Client | YES | Company External ID | YES |  | STANDARD | REVIEW
5 | Job Posting | clientUserID | Hiring Manager | YES | Contact External ID | YES |  | STANDARD | REVIEW
6 | Job Posting | countryID | Country | YES | NOTE | YES |  | STANDARD | REVIEW
7 | Job Posting | customText1 | Salary | YES | Annual Salary | YES |  | STANDARD | REVIEW
8 | Job Posting | description | Internal Description | YES | Internal Job Description | NO |  | STANDARD | REVIEW
9 | Job Posting | feeArrangement | Perm Fee (%) | YES | NOTE | YES |  | STANDARD | REVIEW
10 | Job Posting | fullAddress | Address | YES | NOTE | NO |  | STANDARD | REVIEW
11 | Job Posting | numOpenings | # of Openings | YES | Headcount | YES |  | STANDARD | REVIEW
12 | Job Posting | publicDescription | Published Description | YES | Public Job Description | YES |  | STANDARD | REVIEW
13 | Job Posting | salary | Salary | YES | Annual Salary | YES |  | STANDARD | REVIEW
14 | Job Posting | status | Job Status | YES | NOTE | YES |  | STANDARD | REVIEW
15 | Job Posting | title | Job Title | YES | Job Title | YES |  | STANDARD | REVIEW
16 | Job Posting | userID | Consultant | YES | Job Owners | YES |  | STANDARD | REVIEW
17 | Job Order File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
18 | Job Order File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
19 | Placement | billingFrequency | Billing Frequency | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
20 | Placement | billingUserID | Billing Contact | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
21 | Placement | clientOverTimeRate | Bill Rate (Over-time) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
22 | Placement | comments | Comments | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
23 | Placement | customBillRate1 | Bill Rate (Weekend Rate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
24 | Placement | customBillRate2 | Bill Rate (International) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
25 | Placement | customInt3 | Number Previous Weeks | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
26 | Placement | customPayRate1 | Pay Rate (Weekend Rate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
27 | Placement | customPayRate2 | Pay Rate (International) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
28 | Placement | customPayRate3 | Flat Fee Agreed | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
29 | Placement | customText1 | Salary | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
30 | Placement | customText10 | Placement Fee (Flat) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
31 | Placement | customText5 | Other | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
32 | Placement | customText6 | Referral Fee | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
33 | Placement | customText7 | Travelling Expenses | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
34 | Placement | customTextBlock1 | Specific Contract Terms | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
35 | Placement | dateBegin | Start Date | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
36 | Placement | dateClientEffective | Bill Effective Date (Client) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
37 | Placement | dateEffective | Pay Effective Date (Candidate) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
38 | Placement | employeeType | Employee Payment Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
39 | Placement | fee | Placement Fee (%) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
40 | Placement | flatFee | Placement Fee (Flat) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
41 | Placement | hoursPerDay | Hours Per Day | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
42 | Placement | isMultirate | Rate Entry Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
43 | Placement | markUpPercentage | Mark-up % | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
44 | Placement | overtimeRate | Pay Rate (Over-time) | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
45 | Placement | referralFeeType | Referral Fee Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
46 | Placement | salary | Salary | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
47 | Placement | status | Status | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
48 | Placement | vendorClientCorporationID | Umbrella Company | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
49 | Placement File Attachment | name | Name | NO | FILES | YES |  | STANDARD | REVIEW
50 | Placement File Attachment | type | Type | NO | FILES | YES |  | STANDARD | REVIEW
51 | Quick Placement | clientBillRate | Bill Rate | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
52 | Quick Placement | clientUserID | Client Contact | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
53 | Quick Placement | comments | Job Description / Comments | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
54 | Quick Placement | dateBegin | Start Date | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
55 | Quick Placement | dateEnd | Scheduled End Date | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
56 | Quick Placement | employmentType | Employment Type | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
57 | Quick Placement | hoursPerDay | Hours Per Day | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
58 | Quick Placement | payRate | Pay Rate | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
59 | Quick Placement | title | Job Title | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
60 | Quick Placement | userID | Candidate | NO | JOB APPLICATIONS > PLACED RECORDS | NO |  | CUSTOM | PRODUCTION
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 3. Candidate Fields Mapping
No | Bullhorn DB Table | Bullhorn DB Fieldname | Bullhorn UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | Candidate | businessSectorID | Recruitment Sector Tags | YES | CUSTOM FIELD > INDUSTRY | NO |  | CUSTOM | PRODUCTION
2 | Candidate | city | City | YES | Current Address > Location Address Current Address > Location City Current Address > Location Name | YES |  | STANDARD | REVIEW
3 | Candidate | comments | Candidate Profile | YES | Brief Note | YES |  | STANDARD | REVIEW
4 | Candidate | companyName | Current Company | YES | Current Employer | YES |  | STANDARD | REVIEW
5 | Candidate | countryID | Country | YES | Current Address > Location Address Current Address > Location Country Current Address > Location Name | YES |  | STANDARD | REVIEW
6 | Candidate | customText10 | Will Relocate to | YES | Brief Note | YES |  | STANDARD | REVIEW
7 | Candidate | customText11 | Current Annual Salary | YES | Current Annual Salary | YES |  | STANDARD | REVIEW
8 | Candidate | customText12 | Desired Annual Salary | NO | Desired Annual Salary | NO |  | STANDARD | REVIEW
9 | Candidate | customText4 | Notice Period | YES | Brief Note | YES |  | STANDARD | REVIEW
10 | Candidate | customTextBlock1 | Current Commission Structure | YES | Brief Note | YES |  | STANDARD | REVIEW
11 | Candidate | description | CV | YES | CV Text | YES |  | STANDARD | REVIEW
12 | Candidate | email | Personal Email | YES | Primary Email | YES |  | STANDARD | REVIEW
13 | Candidate | email2 | Work Email | YES | Work Email | YES |  | STANDARD | REVIEW
14 | Candidate | firstName | First Name | YES | Candidate First Name | YES |  | STANDARD | REVIEW
15 | Candidate | fullAddress | Address | YES | Current Address > Location Address | YES |  | STANDARD | REVIEW
16 | Candidate | lastName | Surname | YES | Candidate LastName | YES |  | STANDARD | REVIEW
17 | Candidate | latestComment | Latest Comment | YES | Brief Note | YES |  | STANDARD | REVIEW
18 | Candidate | mobile | Mobile Phone | YES | Mobile Phone | YES |  | STANDARD | REVIEW
19 | Candidate | namePrefix | Title | YES | Title | YES |  | STANDARD | REVIEW
20 | Candidate | occupation | Current Job Title | YES | Job Title | YES |  | STANDARD | REVIEW
21 | Candidate | recruiterUserID | Consultant | YES | Candidate Owners | YES |  | STANDARD | REVIEW
22 | Candidate | referredByUserID | Referred by | YES | Candidate Owners | YES |  | STANDARD | REVIEW
23 | Candidate | salary | Desired Annual Salary | YES | Desired Annual Salary | YES | VC : This item is duplicated with item #8. Which one is the correct one ? Use number 23 | CUSTOM | PRODUCTION
24 | Candidate | salaryLow | Current Annual Salary | YES | Current Annual Salary | YES |  | STANDARD | REVIEW
25 | Candidate | source | Source | YES | Candidate Sources | NO |  | CUSTOM | PRODUCTION
26 | Candidate | status | Job Search Status | YES | Brief Note | YES |  | STANDARD | REVIEW
27 | Candidate | willRelocate | Willing to Relocate | YES | Brief Note | YES |  | STANDARD | REVIEW
28 | Candidate | workPhone | Work Phone | YES | Work Phone | YES |  | STANDARD | REVIEW
29 | Candidate File Attachment | name | Name | YES | FILES | YES |  | STANDARD | REVIEW
30 | Candidate File Attachment | type | Type | YES | FILES | YES |  | STANDARD | REVIEW
31 | Education | certification | Certification | YES | Education Summary | YES |  | STANDARD | REVIEW
32 | Education | city | City | YES | Education Summary | YES |  | STANDARD | REVIEW
33 | Education | comments | Comments | YES | Education Summary | YES |  | STANDARD | REVIEW
34 | Education | dateAdded | Date Added | YES | Education Summary | YES |  | STANDARD | REVIEW
35 | Education | degree | Degree | YES | Education Summary | YES |  | STANDARD | REVIEW
36 | Education | endDate | End Date | YES | Education Summary | YES |  | STANDARD | REVIEW
37 | Education | expirationDate | Certification Expiration Date | YES | Education Summary | YES |  | STANDARD | REVIEW
38 | Education | graduationDate | Graduation Date | YES | Education Summary | YES |  | STANDARD | REVIEW
39 | Education | school | School | YES | Education Summary | YES |  | STANDARD | REVIEW
40 | Education | startDate | Start Date | YES | Education Summary | YES |  | STANDARD | REVIEW
41 | Education | state | County | YES | Education Summary | YES |  | STANDARD | REVIEW
42 | Education | userEducationID | Education ID | YES | Education Summary | YES |  | STANDARD | REVIEW
43 | Reference | candidateTitle | Candidate Title | YES | Brief Note | YES |  | STANDARD | REVIEW
44 | Reference | clientCorporationID | Client Corporation | YES | Brief Note | YES |  | STANDARD | REVIEW
45 | Reference | companyName | Company | YES | Brief Note | YES |  | STANDARD | REVIEW
46 | Reference | dateAdded | Date Added | YES | Brief Note | YES |  | STANDARD | REVIEW
47 | Reference | employmentEnd | Employment End | YES | Brief Note | YES | WorkHistory | STANDARD | REVIEW
48 | Reference | employmentStart | Employment Start | YES | Brief Note | YES |  | STANDARD | REVIEW
49 | Reference | jobPostingID | Job Posting | YES | Brief Note | YES | WorkHistory | STANDARD | REVIEW
50 | Reference | referenceEmail | Reference Email | YES | Brief Note | YES |  | STANDARD | REVIEW
51 | Reference | referenceFirstName | Reference First Name | YES | Brief Note | YES |  | STANDARD | REVIEW
52 | Reference | referenceLastName | Reference Last Name | YES | Brief Note | YES |  | STANDARD | REVIEW
53 | Reference | referencePhone | Reference Phone | YES | Brief Note | YES |  | STANDARD | REVIEW
54 | Reference | referenceTitle | Reference Title | YES | Brief Note | YES |  | STANDARD | REVIEW
55 | Reference | referenceUserID | Reference | YES | Candidate External ID | YES |  | STANDARD | REVIEW
56 | Reference | status | Status | YES | Brief Note | YES |  | STANDARD | REVIEW
57 | Reference | userReferenceID | Reference ID | YES | Brief Note | YES |  | STANDARD | REVIEW
58 | Reference | yearsKnown | Years Known | YES | Brief Note | YES |  | STANDARD | REVIEW
59 | Work History | bonus | Bonus | YES | Work History Summary | YES |  | STANDARD | REVIEW
60 | Work History | clientCorporationID | Company Name | YES | Work History Summary | YES |  | STANDARD | REVIEW
61 | Work History | comments | Comments | YES | Work History Summary | YES |  | STANDARD | REVIEW
62 | Work History | commission | Commission | YES | Work History Summary | YES |  | STANDARD | REVIEW
63 | Work History | companyName | Company Name | YES | Work History Summary | YES |  | STANDARD | REVIEW
64 | Work History | endDate | End Date | YES | Work History Summary | YES |  | STANDARD | REVIEW
65 | Work History | jobPostingID | Job Posting | YES | Work History Summary | YES |  | STANDARD | REVIEW
66 | Work History | salary1 | Salary Low | YES | Work History Summary | YES |  | STANDARD | REVIEW
67 | Work History | salary2 | Salary High | YES | Work History Summary | YES |  | STANDARD | REVIEW
68 | Work History | salaryType | Salary Type | YES | Work History Summary | YES |  | STANDARD | REVIEW
69 | Work History | startDate | Start Date | YES | Work History Summary | YES |  | STANDARD | REVIEW
70 | Work History | terminationReason | Termination Reason | YES | Work History Summary | YES |  | STANDARD | REVIEW
71 | Work History | title | Job Title | YES | Work History Summary | YES |  | STANDARD | REVIEW
72 | Candidate | userID | User ID | YES | Candidate External ID | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.

## 5. Job Application Stage Mappin
|  |  |  | STATUS : | In Review
No | Bullhorn Stage | Required ? | Vincere Stage | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | 1st Interview | YES | FIRST_INTERVIEW |  | STANDARD | REVIEW
2 | 2nd Interview | YES | SECOND_INTERVIEW |  | STANDARD | REVIEW
3 | 3rd Interview | YES | SECOND_INTERVIEW |  | STANDARD | REVIEW
4 | Candidate Rejected | YES | SHORTLISTED > REJECTED |  | CUSTOM | PRODUCTION
5 | Client Rejected | YES | SHORTLISTED > REJECTED |  | CUSTOM | PRODUCTION
6 | CV Sent | YES | SENT |  | STANDARD | REVIEW
7 | Final Interview | YES | SECOND_INTERVIEW |  | STANDARD | REVIEW
8 | Placed | YES | PLACED |  | STANDARD | REVIEW
9 | Shortlisted | YES | SHORTLISTED |  | STANDARD | REVIEW
10 | Submitted | YES | SENT |  | STANDARD | REVIEW
Note: At this stage any REJECTED status can only be migrated to REJECTED status under the SHORTLISTED stage thru Custom Script work. This is not covered under our standard migration.
Job Types
No | Bullhorn Employment Type | Required ? | Vincere Job Type | Comments
1 | Contract | YES | CONTRACT
2 | Permanent | YES | PERMANENT
3 | Temporary | YES | TEMPORARY

## 6. CUSTOM FIELD Industry Mappin
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Business Sector Field | Required ? | Vincere Industry Field | Comments
1 | Aerospace, Aviation and Defence | YES | Aerospace, Aviation and Defence | TBD
2 | Agriculture | YES | Agriculture
3 | Banking & FS | YES | Banking & FS
4 | C-level & Executive | YES | C-level & Executive
5 | Consultancy & Advisory | YES | Consultancy & Advisory
6 | Creative & Design | YES | Creative & Design
7 | Digital & Media | YES | Digital & Media
8 | Education | YES | Education
9 | Engineering & Manufacturing | YES | Engineering & Manufacturing
10 | Hospitality & Leisure | YES | Hospitality & Leisure
11 | HR | YES | HR
12 | Insurance | YES | Insurance
13 | Legal | YES | Legal
14 | Marketing | YES | Marketing
15 | Medical & Healthcare | YES | Medical & Healthcare
16 | Mining & Resources | YES | Mining & Resources
17 | Office Support | YES | Office Support
18 | Oil & Gas | YES | Oil & Gas
19 | Pharma & Life Science | YES | Pharma & Life Science
20 | Power, nuclear & renewables | YES | Power, nuclear & renewables
| PR & Comms | YES | PR & Comms
21 | Procurement & Supply Chain | YES | Procurement & Supply Chain
23 | Property & Construction | YES | Property & Construction
21 | Public Sector & Not for Profit | YES | Public Sector & Not for Profit
22 | Rec-to-Rec | YES | Rec-to-Rec
23 | Retail & FMCG | YES | Retail & FMCG
24 | Sales | YES | Sales
25 | Shipping and Maritime | YES | Shipping and Maritime
26 | Sport & Recreation | YES | Sport & Recreation
27 | Tax & Treasury | YES | Tax & Treasury
28 | Technical | YES | Technical
29 | Technology | YES | Technology
30 | Telecommunications | YES | Telecommunications
31 | Trades & Services | YES | Trades & Services
32 |  | YES
33 | Technology – Change and Transformation | YES | Technology – Change and Transformation
34 | Technology – BI, Data & Analytics | YES | Technology – BI, Data & Analytics
35 | Technology – Cyber Security | YES | Technology – Cyber Security
36 | Technology – CRM + ERP | YES | Technology – CRM + ERP
37 | Technology – Digital Marketing | YES | Technology – Digital Marketing
38 | Technology – Strategy and Architecture | YES | Technology – Strategy and Architecture
39 | Technology – Software Development | YES | Technology – Software Development
40 |  | YES
| Property and Construction – White Collar | YES | Property and Construction – White Collar
25 | Property and Construction – Blue Collar | YES | Property and Construction – Blue Collar
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM FIELD Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment
| Sales | YES | Sales | TBD
| Business Development | YES | Business Development
| 360 | YES | 360
| Executive Search | YES | Executive Search
| Resourcing | YES | Resourcing
| Research | YES | Research
| Operations | YES | Operations
| HR | YES | HR
| Talent Acquisition | YES | Talent Acquisition
| CEO | YES | CEO
| Director | YES | Director
| Finance | YES | Finance
| Marketing | YES | Marketing
| Graduate | YES | Graduate
| Project Consulting | YES | Project Consulting
| Statement-of-work | YES | Statement-of-work
| RPO | YES | RPO

## 8. CUSTOM FIELD Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD |  | TBD | TBD
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM FIELD Candidate Sour
Candidate Source Field |  | Commented
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Bullhorn SOURCE Field values | Required ? | Vincere Candidate Source values | Comment
| We do currently track candidate source against placements for ROI on advertising tracking. We can either migrate current data or just go forward from now. It is not critical... | Preferably but not critical | TBD | TBD

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
[5 empty] | Total : | 0
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.