## 1. Project Gantt Chart
Data Migration Project
Client Name: BMA Group
Office Locations : Puerto Rico, USA
Timezone : UTC-04:00
System of Origin : Voyager Infinity
Person in Charge : Steven Fernandez <sfernandez@bmapr.com> Tel: (787) 620-3998 Cell: (787) 647-6800 ✎ Skype: vamp07
No | Tasks | Accountable Owner | Dependency | Status | Start Date | Completion Date | Duration (man-days) | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Comments / Reference
1 | Nominate Data Migration Manager on the Customer side. Nominated: Steven Fernandez <sfernandez@bmapr.com> | BMA Group | None | Completed | 2018-01-29 | 2018-01-29 | 0 | bar: 2018-01-29
2 | Customer to send SQL Backup to Vincere | BMA Group | None | Completed | 2018-02-05 | 2018-02-09 | 4 | [12 empty] | Standard SQL Backup is provided on 13 Dec 2017 | bar: 2018-02-05
3 | Vincere to Restore the SQL Backup and perform initial Analysis | Vincere | 2 | Completed | 2018-02-09 | 2018-02-09 | 0 | [12 empty] | SQL Backup Data: Company: 3244 Contact: 7853 Job: 118 Candidate:91326 Total Files: | bar: 2018-02-05
4 | Vincere to get the list of Fields to be Captured on each of the data sets of System of Origin Database. | Vincere | 3 | Completed | 2018-02-09 | 2018-02-12 | 5 | bar: 2018-02-05 to 2018-02-12
5 | Vincere to conduct Data Migration Process Overview Meeting | BMA Group, Vincere | 4 | Pending | 2018-02-14 | 2018-02-14 | 1 | bar: 2018-02-12
6 | Customer to confirm the final Data including with the Fields Mapping Definition | BMA Group | 5 | Pending | 2018-02-14 | 2018-02-20 | 4 | bar: 2018-02-12 to 2018-02-19
7 | Data Migration : DATA EXTRACT | Vincere | 6 | Pending | 2018-02-20 | 2018-02-22 | 2 | bar: 2018-02-19
8 | Data Migration : DATA CLEANSING | Vincere | 7 | Pending | 2018-02-22 | 2018-02-27 | 3 | bar: 2018-02-19
9 | Data Migration : DATA MAPPING & TRANSFORM | Vincere | 8 | Pending | 2018-02-27 | 2018-03-01 | 2 | bar: 2018-02-19 to 2018-02-26
10 | Data Migration : DATA LOAD to Review Site | Vincere | 9 | Pending | 2018-03-01 | 2018-03-05 | 2 | bar: 2018-02-26 to 2018-03-05
11 | REVIEW : Customer to Review the migrated data on the Review Site | BMA Group, Vincere | 10 | Pending | 2018-03-05 | 2018-03-08 | 3 | bar: 2018-03-05
12 | REVIEW : Vincere to send Data Migration Completion Form | Vincere | 11 | Pending | 2018-03-08 | 2018-03-09 | 1 | bar: 2018-03-05
13 | REVIEW : Customer to Sign off the Data Migration Completion Form | BMA Group | 12 | Pending | 2018-03-09 | 2018-03-12 | 1 | bar: 2018-03-05 to 2018-03-12
14 | REVIEW : Customer to send the final SQL Backup files | BMA Group | 13 | Pending | 2018-03-12 | 2018-03-12 | 1 | bar: 2018-03-12
15 | PRODUCTION : Vincere to run the final data migration to Production Site | Vincere | 13,14 | Pending | 2018-03-12 | 2018-03-16 | 5 | bar: 2018-03-12
16 | Data Migration is COMPLETED | Vincere | 15 | Pending | 2018-03-16 | 2018-03-16 | 0 | bar: 2018-03-12
17 | Data Migration of Custom Fields | Vincere | 16 | Pending | 2018-03-16 | 2018-03-20 | 2 | bar: 2018-03-12 to 2018-03-19
18 | Training to Start | Vincere | 17 | Pending | TBD | TBD
[6 empty] | TOTAL | 36

## Q&A
No | Date | Category | Customer Questions | Sample Data | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Date | Vincere Response | Date | Customer Response | Resolved ? (Y/N) | Comments | Reference
1 | 2018-07-28 | Clarificaftion | Where it is a VC Core Field and I have put an “n”, it is not that I want the field removed from Vincere, just that I am not particularly worried about transferring the data. | E.g. Company ID can be populated with the standard format Vincere IDs so we have a common format going forward. | 2018-08-06 | AT: Yes understood. The Y/N value under the "Required ?" column only to state that the field is required / not required to be migrated. When you are in Vincere later, you can make the modification you need on the existing fields. |  | OK
2 | 2018-07-28 | Company fields mapping 69 | I have said do not extract but is it possible to reindex our Outlook to back search and populate? |  | 2018-08-06 | AT: Yes once your email is integrated to Vincere, you can run Email Synchronization which will link all of the past email correspondence that you had with the Contacts / Candidates that have been registered in Vincere and populate them to the respective Contacts / Candidates Email tab. This email syncronization only link 2000 emails or 3 months worth of emails which ever smaller. |  | OK
3 | 2018-07-28 | Contact fields mapping 31 | We don't use it so no need to transfer. It has been auto populated. |  | 2018-08-06 | AT: ok |  | OK
4 | 2018-07-28 | Contact fields mapping 36 | There is a difference between a notice period (4 weeks rolling) and a definative availabe date... |  | 2018-08-06 | AT: we can bring them to NOTE. Or if you prefer to migrate them to the "Custom Field > Notice period" or "Custom Field > Available Date" under the contact we could do also but this would require custom script. |  | OK - Not needed. Little used and out of date information in the most part.
5 | 2018-07-28 | Contact fields mapping 43 | We really do want to see placement history. Does this not come across with the 5. Job Application Stage Mapping that includes place "placed"? |  | 2018-08-06 | AT: Yes placement history can be migrated and will be included under Tab 5. Job Application Stage Mapping. |  | OK
6 | 2018-07-28 | Contact fields mapping 90 | Missing clarification fields but not sure it is needed |  | 2018-08-06 | AT: We don't see clarification field in the backend. We may need to check more if this is needed. |  | OK - not needed
7 | 2018-07-28 | Jobs field mapping 1 | Is this the internal ID or the client reference (no. 12)? Happy to repopulate internal with Vincere format but if this is the client reference, it needs to remain the same. |  | 2018-08-06 | AT: This is the backend DB record's ID for the Job Records in Voyager. We will need this to uniquely identify the records during the migration process. |  | OK
8 | 2018-07-28 | Jobs field mapping 6 | Yes for the Closed status. This appears to mean that we are not migrating live jobs to live jobs as the Vincere field is Note. Please clarify as this is important to us. |  | 2018-08-06 | AT: Vincere doesn' have Job Status field per say. The Job Status in Vincere is only Open or Closed. They are determined by the Closed Date of the Job. The Job is live when it is in Open status. But if the Closed Date is set in the past, the Job will be set to be closed. When they are closed, any job posting that are available on the Internal Job Board, will be unpublished. If Voyager status is really important to be migrated, this should be migrated to Job Custom Field > Job Status. However, we will need a custom script to populate this. |  | OK - lets not delay with custom scripting
9 | 2018-07-28 | Jobs field mapping 10 | This is a gerneral clasiffication field to group role types/functions e.g. Sales, IT or Marketing roles. The client then calls the roles what they like in 11. Maybe mapping to a different field is more appropriate... |  | 2018-08-06 | AT: We don't have similar type of role field in a pull down menu like Voyager. We have only a Freetext field under the Job Title but this is already being mapped. If you want, we can migrate this to "Custom Field > Job Classification". This will require Custom Script if it is required though. |  | OK - client job title is most important so not needed.
10 | 2018-07-28 | Jobs field mapping 12 | This is the client's internal job number that sometimes needs to be referenced. I suspect this needs mapping to a different field as I am sure you have one. |  | 2018-08-06 | AT: Yes we have Company External ID. This is basically the ID reference to the client's company record so we can link the job to the correct company. |  | Perfect
11 | 2018-07-28 | Jobs field mapping 15 | There is the main point of contact (e.g. HR) and then the actual hiring manager (a different person). This field is the hiring manager - do you have this field? |  | 2018-08-06 | AT: Yes we have the hiring manager but the contact that can be linked there must be a contact record with unique ID linked. If in Voyager the Report To field is populated with the name of the Hiring Manager in a text format without any ID reference, we would need to migrate this to NOTE instead or Custom Field. |  | Hiring managers do have an ID. Let me know if you need further help on this. If it went to Note, it would not be the end of the world though. | 2018-08-10 | OK
12 | 2018-07-28 | Jobs field mapping 18 & 19 | This is when the client wants to the person to start. Do you have a similar field to map to? |  | 2018-08-06 | AT: We have this but on the Placement details. The work start date can be populated only when you are offering the Candidate. So this information is not linked to the Job but to the Placement records in Vincere. If this information exist in the Job, we would need to mirgate it to NOTE or a Custom Field. |  | OK - not important. Don't transfer.
13 | 2018-07-28 | 6. CUSTOM FIELD: Industry Mapping | Not sure what this is and whether we use it |  | 2018-08-06 | AT: Ok. This is the tagging of the Job for Industry classification so you can use it to search for the Job as well as the Candidate for easier matching. If not needed it is not a problem. Please indicate it on the "Required ?" field. |  | OK - No
14 | 2018-07-28 | 7. CUSTOM FIELD : Functional Expertise Mapping | Not sure what this is and whether we use it |  | 2018-08-06 | AT: Ok. This is the tagging of the Job for Functional Expertise classification so you can use it to search for the Job as well as the Candidate for easier matching. If not needed it is not a problem. Please indicate it on the "Required ?" field. |  | OK - No
15 | 2018-07-28 | 8. CUSTOM FIELD : Sub Functional Expertise | Not sure what this is and whether we use it |  | 2018-08-06 | AT: Ok. This is the tagging of the Job for Sub Functional Expertise classification so you can use it to search for the Job as well as the Candidate for easier matching. If not needed it is not a problem. Please indicate it on the "Required ?" field. |  | OK - No
16 | 2018-07-28 | 9. CUSTOM FIELD : Candidate Source | We do currently track candidate source against placements for ROI on advertising tracking. We can either migrate current data or just go forward from now. |  | 2018-08-06 | AT: We can populate Candidate Source to the Candidate records. They are listed on the tab 3. Candidate Fields Mapping > item 54. |  | Yes please. | 2018-08-10 | OK

## 1. Company Fields Mapping
Voyager Infinity to Vincere Fields Mapping (COMPANY) |  |  | COMPLETE
1 Custom Script = 200 USD one time fee
No | Voyager Infinity DB Table | Voyager Infinity DB Fieldname | Voyager Infinity UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | dCompany | intCompanyId | Company ID | NO | Company External ID | YES |  | STANDARD | REVIEW
2 | dCompany | vchAlternateCode | Alternate Code | NO | Note | YES |  | STANDARD | REVIEW
3 | dCompany | vchCompanyName | Company Name | YES | Company name | YES |  | STANDARD | REVIEW
4 | dCompanyTelecom | vchValue | Company Phone | YES | Company Phone | YES |  | STANDARD | REVIEW
5 | dCompanyTierTelecom | vchValue | Company Phone 2 | YES | Company Phone | YES | Will be appended | STANDARD | REVIEW
6 | dCompanyTelecom | vchValue | Website | YES | Company Website | YES |  | STANDARD | REVIEW
7 | dCompanyCompetitor | vchValue | Competitor | NO | Note | YES | No list of values found in the database | STANDARD | REVIEW
8 | dCompany | bitActive | Active Flag | YES | Note | YES |  | STANDARD | REVIEW
9 | dCompany | tintCompanyTypeId | Type | YES | Note | YES | List of Values include: 1. Client 2. Agency 3. Prospect 4. Supplier 5. Asset Management....etc | STANDARD | REVIEW
10 | dCompany | tintBusinessSectorId | Business Sector | NO | Note | YES | Sample value include: "Business" | STANDARD | REVIEW
11 | lconsultantCompany | intConsultantId | Consultants | NO | Company Owners | YES |  | STANDARD | REVIEW
12 | N/A |  | Parent / Subsidiary | NO | Note | YES |  | STANDARD | REVIEW
13 |  |  | 3 Current Jobs | NO | JOBS | NO | Visible when linking jobs to contacts | CUSTOM | PRODUCTION
14 | dCompany | vchNote | Notes | YES | Note | YES |  | STANDARD | REVIEW
15 | N/A |  | Parent Company ID | NO | Note | NO |  | CUSTOM | PRODUCTION
16 | N/A |  | Subsidiary Company IDs | NO | Note | NO |  | CUSTOM | PRODUCTION
17 | dCompanyTier | vchCompanyTierName | Location Name | YES | Company Location Name | YES | The branch name will be copied as Location name and the Phone number of the location will be appended after the Branch name. i.e. Location - Phone | STANDARD | REVIEW
18 | dCompanyTier | vchCompanyTierName | Location Type | NO | Note | YES |  | STANDARD | REVIEW
19 | dCompanyTier | sintCountryId | Location Country | YES | Company Location Country | YES |  | STANDARD | REVIEW
20 | dCompanyTierTelecom | vchValue | Location Phone | YES | Note | YES |  | STANDARD | REVIEW
21 | dCompanyTier | vchAddressLine1,2,3 | Location Name | YES | Company Location Name | YES |  | STANDARD | REVIEW
22 | dCompanyTier | vchAddressLine1 | Location Address Line 1 | YES | Company Location Address | YES | The phone number will be appended to the Address Field | STANDARD | REVIEW
23 | dCompanyTier | vchAddressLine2 | Location Address Line 2 | YES | Company Location Address | YES |  | STANDARD | REVIEW
24 | dCompanyTier | vchAddressLine3 | Location Address Line 3 | YES | Company Location Address | YES |  | STANDARD | REVIEW
25 | dCompanyTier | vchTown | Location Town | YES | Company Location City | YES |  | STANDARD | REVIEW
26 | dCompanyTier | vchPostcode | Location Postcode | YES | Company Location Zip | YES |  | STANDARD | REVIEW
27 | dCompanyTier | vchDescription | Location Description | YES | Note | YES |  | STANDARD | REVIEW
28 | dCompanyTierTelecom | vchValue | Location Telecom | NO | Note | YES | Dulicate with row 20 | STANDARD | REVIEW
29 | dCompanyTier | bitOKToMailshot | Location OK to Mailshot Flag | YES | Note | YES |  | STANDARD | REVIEW
30 | dCompanyTierTelecom | bitOKToSMS | Location OK to SMS Flag | YES | Note | YES |  | STANDARD | REVIEW
31 | dCompanyTierTelecom | bitSendByDefault | Location Send by Default Flag | YES | Note | YES |  | STANDARD | REVIEW
32 | dCompanyTier | vchCounty | Location Value | NO | Note | YES |  | STANDARD | REVIEW
33 | dCompanyTierTelecom | vchExtension | Location Ext | YES | Note | YES |  | STANDARD | REVIEW
34 | dCompany | intPreferredTelecomId | Preferred Telecom | YES | Note | YES |  | STANDARD | REVIEW
35 | dCompanyTelecom | vchValue | Company Fax | YES | Company Fax | YES |  | STANDARD | REVIEW
36 | N/A |  | Company Work Email | NO |  | NO |  | CUSTOM | PRODUCTION
37 | dCompanyTier | vchNearestTrainStation | Nearest Location | NO | Note | YES |  | STANDARD | REVIEW
38 | dCompanyTier | vchNote | Location Notes | YES | Note | YES |  | STANDARD | REVIEW
39 | dCompany | vchCompanyRegNo | Company Financials > Registered No | YES | Note | YES |  | STANDARD | REVIEW
40 | dCompany | vchVATNumber | Company Financials > VAT No | YES | Note | YES |  | STANDARD | REVIEW
41 | dCompany | tintVATCodeId | Company Financials > VAT Code | YES | Note | YES |  | STANDARD | REVIEW
42 | dCompany | vchNonUKTaxCode | Company Financials > Non-UK Tax Code | NO | Note | YES | No data found | STANDARD | REVIEW
43 | dCompany | decCreditLimit | Company Financials > Credit Limit | NO | Note | YES |  | STANDARD | REVIEW
44 | dCompany | decCreditBalance | Company Financials > Credit Balance | NO | Note | YES |  | STANDARD | REVIEW
45 | dCompany | tintChargeCurrencyId | Company Financials > Default Currency | YES | Note | YES |  | STANDARD | REVIEW
46 | dCompany | sintTerritoryId | Company Financials > Territory | YES | Note | YES | List of Country names | STANDARD | REVIEW
47 | dPONumber | vchPONumber | Company PO Number | NO | Note | YES |  | STANDARD | REVIEW
48 | dPONumber | dValidFromDate | Company Valid From | YES | Note | YES |  | STANDARD | REVIEW
49 | dPONumber | dValidToDate | Company Valid To Date | YES | Note | YES |  | STANDARD | REVIEW
50 | dPONumber | decValue | Company Origin | YES | Note | YES |  | STANDARD | REVIEW
51 | dPONumber | tintValueCurrencyId | Company Currency | YES | Note | YES |  | STANDARD | REVIEW
52 | dPONumber | decActualValue | Company Balance | YES | Note | YES |  | STANDARD | REVIEW
53 | dPONumber | vchDescription | Company PO Description | YES | Note | YES |  | STANDARD | REVIEW
54 | dCompany | intInvoiceCompanyTierId | Company Invoice Location | YES | Note | YES |  | STANDARD | REVIEW
55 | dCompany | intInvoiceContactId | Company Invoie Contact | YES | Note | YES |  | STANDARD | REVIEW
56 | dCompany | tintBackOfficeSectorId | Company Back Office Sector | YES | Note | YES |  | STANDARD | REVIEW
57 | lMODivisionMODepartmentCompany | tintMODivisionId | Company Division | NO | Note | NO |  | CUSTOM | PRODUCTION
58 | lMODivisionMODepartmentCompany | tintMODepartmentId | Company Department | NO | Department | NO |  | CUSTOM | PRODUCTION
59 | lMODivisionMODepartmentCompany | fltSplit | Company Split % | NO | Note | NO |  | CUSTOM | PRODUCTION
60 | dPONumber |  | Company Project Code | NO | Note | NO |  | CUSTOM | PRODUCTION
61 | dPONumber |  | Company Description | NO | Note | NO |  | CUSTOM | PRODUCTION
62 | dPONumber |  | Company PO Location | NO | Note | NO |  | CUSTOM | PRODUCTION
63 | dCompanyTier | bitOverrideInvoiceDetails | Company Overide Defaults - Invoice Location | NO | Note | YES |  | STANDARD | REVIEW
64 | dCompany | intInvoiceContactId | Company Overide Defaults - Invoice Contact | NO | Note | YES |  | STANDARD | REVIEW
65 | dPlacement | bitOverrideBOSector | Company Overide Defaults - Back Office Sector | NO | Note | YES |  | STANDARD | REVIEW
66 | dCompanyTier | bitOverrideDivDept | Company Overide Defaults - Division & Department | NO | Note | YES |  | STANDARD | REVIEW
67 |  |  | LIST OF CONTACTS - Will be linked to the CONTACT records | YES | CONTACTS | YES |  | STANDARD | REVIEW
68 |  |  | Active / Inactive | YES | Note | YES |  | STANDARD | REVIEW
69 |  |  | Emails | Don't worry about extraction but migrate over if readable text. However, is it possible to reindex our Outlook to back search and populate? | Activities Comments | YES | .EML or .MSG files won't be migrated. If the body contents are stored in the .EML or .MSG files, they need to be extracted separately thru our Partner. We don't offer services to extract email contents. If the email contents are stored in the database as readable text format, we can migrate them over. | STANDARD | REVIEW
70 |  |  | Events |  | Activities Comments | YES |  | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.
Note on G3: CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated. All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope. Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required. -Andi Taufiq

## 2. Contact Fields Mapping
Voyager Infinity to Vincere Fields Mapping (CONTACTS) |  |  | Completed
1 Custom Script = 200 USD one time fee
No | Voyager Infinity DB Table | Voyager Infinity DB Fieldname | Voyager Infinity UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | dContact | intContactId | Contact ID | YES | Contact External ID | YES | This is the record ID of Voyager. Vincere will need to migrate it and populate it to the Contact External ID to identify the correct Contact records to be migrated. | STANDARD | REVIEW
2 | lCompanyTierContact | tintContactPriorityId | Contact Priority (PTY) | YES | Note | YES |  | STANDARD | REVIEW
3 | lCompanyTierContact | vchJobTitle | Job Title | YES | Job title | YES |  | STANDARD | REVIEW
4 | lCompanyTierContact | intCompanyTierId | Location ID | YES | Note | YES |  | STANDARD | REVIEW
5 | dCompanyTier | vchTown | Location City | YES | Note | YES |  | STANDARD | REVIEW
6 | dContact | datLastContacted | Last Contacted Date | YES | Note | YES |  | STANDARD | REVIEW
7 | N/A |  | Next Contact Date | NO | N/A | NO |  | CUSTOM | PRODUCTION
8 | dPerson | vchLinkedInUrl | LinkedIn URL | YES | LinkedIn URL | YES |  | STANDARD | REVIEW
9 | dPerson | tintTitleId | Title | NO | Note | YES | Mr., Mrs. etc | STANDARD | REVIEW
10 | dPerson | vchForename | Forename | YES | First name | YES |  | STANDARD | REVIEW
11 | dPerson | vchMiddlename | Middlename | YES | Middle name | YES |  | STANDARD | REVIEW
12 | dPerson | vchSurname | Surname | YES | Last name | YES |  | STANDARD | REVIEW
13 | dPerson | vchKnownAs | Known As | YES | Note | YES |  | STANDARD | REVIEW
14 | dContact | vchAlternateCode | Alternate Code | NO | Note | YES |  | STANDARD | REVIEW
15 | dCompanyTierContactTelecom | vchDescription=Email1 | Primary email | YES | Primary Email | YES |  | STANDARD | REVIEW
16 | dCompanyTierContactTelecom | vchDescription=DDI | Phone | YES | Primary Phone | YES |  | STANDARD | REVIEW
17 | dCompanyTierContactTelecom | vchDescription=Mobile Phone | Mobile Phone | YES | Mobile phone | YES |  | STANDARD | REVIEW
18 | dContact | bitFestiveGreetingsCard | Festive Greetings Card Flag | NO | Note | YES |  | STANDARD | REVIEW
19 | dPerson | intCurrentPhotoId | Photo File | NO | N/A | NO |  | CUSTOM | PRODUCTION
20 | dCompanyTierContactTelecom | vchDescription | Telecoms > Description | NO | Note | YES |  | STANDARD | REVIEW
21 | dCompanyTierContactTelecom | tintTelecomId | Telecoms > Telecom | NO | Note | YES |  | STANDARD | REVIEW
22 | dCompanyTierContactTelecom | bitOKToMailshot | Telecoms > OK to mailshot | NO | Note | YES |  | STANDARD | REVIEW
23 | dCompanyTierContactTelecom | bitOKToSMS | Telecoms > OK to SMS | NO | Note | YES |  | STANDARD | REVIEW
24 | dCompanyTierContactTelecom | bitSendByDefault | Telecoms > Send by default | NO | Note | YES |  | STANDARD | REVIEW
25 | dCompanyTierContactTelecom | sintCountryId | Telecoms > Country | NO | Note | YES |  | STANDARD | REVIEW
26 | dCompanyTierContactTelecom | vchValue | Telecoms > value | YES | Note | YES |  | STANDARD | REVIEW
27 | dCompanyTierContactTelecom | vchExtension | Telecoms > Ext | YES | Note | YES |  | STANDARD | REVIEW
28 | dCompanyTierContactTelecom | intCompanyTierId | Telecoms > Location | NO | Note | YES | Get phone of the location | STANDARD | REVIEW
29 | lCompanyTierContact | intPreferredTelecomId | Telecoms > Preferred Telecom | NO | Note | YES |  | STANDARD | REVIEW
30 | N/A |  | Current Flag | NO | N/A | NO |  | CUSTOM | PRODUCTION
31 | dWorkHistory | vchLineManager | Line Manager | YES | Work History | YES | should put it as a Comment with tag "Work History" in Contact Activities instead Format: WORK HISTORY Microsoft Project Manager Start Date : End Date: | STANDARD | REVIEW
32 | dWorkHistory | tintJobType | Job Type | YES | Work History | YES |  | STANDARD | REVIEW
33 | dWorkHistory | sintAgencyUsedId | Agency Used | NO | Note | YES |  | STANDARD | REVIEW
34 | dWorkHistory | datStartDate | Start Date | YES | Work History | YES | should put it as a Comment with tag "Work History" in Contact Activities instead | STANDARD | REVIEW
35 | dWorkHistory | datEndDate | End Date | YES | Work History | YES | should put it as a Comment with tag "Work History" in Contact Activities instead | STANDARD | REVIEW
36 | dWorkHistory | tintSalaryCurrencyId | Salary Currency | YES | Work History | YES | should put it as a Comment with tag "Work History" in Contact Activities instead | STANDARD | REVIEW
37 | dWorkHistory | decSalary | Salary | YES | Note | YES |  | STANDARD | REVIEW
38 | dWorkHistory | tintSalaryPeriodId | Salary per | NO | Note | YES |  | STANDARD | REVIEW
39 | dWorkHistory | vchNote | Notes | YES | Work History | YES | should put it as a Comment with tag "Work History" in Contact Activities instead | STANDARD | REVIEW
40 | dPlacement | intPlacementId | Placement | YES | LINK TO JOBAPP | YES | COMMENTED IN Q&A Question: "How can we see how many placements have been made with specific contacts? There is a placements list with each Contact and we'd like to still see this data" AT: The Voyager field here represents only numeric field. So this will be appended to NOTE. But moving forward, you will be able to see the number of placed candidates from the Contact Chevron (Quick View). We cannot migrate this value to the Chevron number because it requires the actual candidate records to be linked to the Job where the status is showing as Placed to actually see the number of Placed candidates on the Vincere Chevron. | STANDARD | REVIEW
41 | lCompanyTierContact | bitActive | Active / Inactive at this location flag | NO | Note | YES |  | STANDARD | REVIEW
42 | lCompanyTierContact | bitDecisionMaker | Is decision maker flag | NO | Note | YES |  | STANDARD | REVIEW
43 | lCompanyTierContact | vchDepartment | Department | NO | Note | YES |  | STANDARD | REVIEW
44 | lConsultantCompanyTierContact | intConsultantId | Consultants | YES | Contact Owner | YES |  | STANDARD | REVIEW
45 | lEventCompanyTierContact | sdtEventDate | EVENTS > Date | NO | Note | YES |  | STANDARD | REVIEW
46 | lEventCompanyTierContact | intLoggedById | EVENTS > By | NO | Note | YES |  | STANDARD | REVIEW
47 | lEventCompanyTierContact | tintDirection | EVENTS > Back / Forward arrow | NO | Note | YES |  | STANDARD | REVIEW
48 | N/A |  | EVENTS > To/From | YES |  | YES |  | STANDARD | REVIEW
49 | lEventCompanyTierContact | sintEventActionId | EVENTS > Action | NO | Note | YES |  | STANDARD | REVIEW
50 | lEventCompanyTierContact | vchEventDetail | EVENTS > Details | YES | Note | YES |  | STANDARD | REVIEW
51 | N/A |  | EVENTS > Web Link | YES |  | YES |  | STANDARD | REVIEW
52 | lAttachmentEvent | intAttachmentId | EVENTS > Attachments | YES | Note | YES |  | STANDARD | REVIEW
53 | N/A |  | EVENTS > Logged Against | YES |  | YES |  | STANDARD | REVIEW
54 | lAttributeCompanyTierContact | sintAttributeScoreId | ATTRIBUTES > Score | NO | Note | YES |  | STANDARD | REVIEW
55 | lAttributeCompanyTierContact | intAttributeChildId | ATTRIBUTES > Attribute | NO | Note | YES |  | STANDARD | REVIEW
56 | lAttributeCompanyTierContact | vchNote | ATTRIBUTES > Notes | NO | Note | YES |  | STANDARD | REVIEW
57 |  |  | ATTRIBUTES > Against | YES |  | YES |  | STANDARD | REVIEW
58 | lQualificationCompanyTierContact |  | QUALs & CERTS > | NO | Note | YES |  | STANDARD | REVIEW
59 | lQualificationCompanyTierContact |  | QUALs & CERTS > Qual/Cert | NO | Note | YES |  | STANDARD | REVIEW
60 | lQualificationCompanyTierContact |  | QUALs & CERTS > Type | NO | Note | YES |  | STANDARD | REVIEW
61 | lQualificationCompanyTierContact |  | QUALs & CERTS > Level | NO | Note | YES |  | STANDARD | REVIEW
62 | lQualificationCompanyTierContact |  | QUALs & CERTS > Notes | NO | Note | YES |  | STANDARD | REVIEW
63 | lQualificationCompanyTierContact |  | QUALs & CERTS > Against | NO | Note | YES |  | STANDARD | REVIEW
64 | lCompanyTierContact lJobTitleCompanyTierContact | vchJobTitleName | JOB TITLES > Job Title | YES | Note | YES |  | STANDARD | REVIEW
65 | lCompanyTierContact lJobTitleCompanyTierContact | vchNote | JOB TITLES > Notes | YES | Note | YES |  | STANDARD | REVIEW
66 | N/A |  | JOB TITLES > Against | YES |  | YES |  | STANDARD | REVIEW
67 | dCompanyTierContactCallBack | datCallBackDate | CALL BACKS > Due Date | NO | Note | YES | No data found: get callbackdate instead | STANDARD | REVIEW
68 | dCompanyTierContactCallBack |  | CALL BACKS > For | NO |  | YES | no data found | STANDARD | REVIEW
69 | dCompanyTierContactCallBack | vchCallBackDetail | CALL BACKS > Details | NO | Note | YES |  | STANDARD | REVIEW
70 | dCompanyTierContactCallBack | tintCallBackTypeId | CALL BACKS > Type | NO | Note | YES |  | STANDARD | REVIEW
71 | lCompanyTierContact | intPreferredTelecomId | CALL BACKS > Preferred Telecom | NO | Note | YES | no data found | STANDARD | REVIEW
72 | dCompanyTierContactCallBack | bitActive | CALL BACKS > Flag | NO | Note | YES |  | STANDARD | REVIEW
73 | dCompanyTierContactCallBack | (self contact) | CALL BACKS > Against | NO | Note | YES | No data found | STANDARD | REVIEW
74 | dCompanyTierContactCallBack | value=contact | CALL BACKS > Entity | NO | Note | YES |  | STANDARD | REVIEW
75 | dTask | sdtDue | TASKS > Due | NO | Activities Comments | YES |  | STANDARD | REVIEW
76 | dTask | sdtStart | TASKS > Start | NO | Activities Comments | YES |  | STANDARD | REVIEW
77 | dTask | vchSubject | TASKS > Subject | NO | Activities Comments | YES |  | STANDARD | REVIEW
78 | dTask | tintPriority | TASKS > Exclamation Flag | NO | Activities Comments | YES |  | STANDARD | REVIEW
79 | dTask | vchNote | TASKS > In Task Of | NO | Activities Comments | YES |  | STANDARD | REVIEW
80 | dTask | tintSensitivity | TASKS > Alert | NO | Activities Comments | YES |  | STANDARD | REVIEW
81 | dTask | tintPercentageCompleted | TASKS > Completed Flag | NO | Activities Comments | YES |  | STANDARD | REVIEW
82 | N/A |  | TASKS > Against | NO | Activities Comments | YES |  | STANDARD | REVIEW
83 | dCalendar |  | MEETINGS > Logged Against | NO | Activities Comments | YES |  | STANDARD | REVIEW
84 | dCalendar | sdtStart | MEETINGS > Start | NO | Activities Comments | YES |  | STANDARD | REVIEW
85 | dCalendar | sdtEnd | MEETINGS > End | NO | Activities Comments | YES |  | STANDARD | REVIEW
86 | dCalendar | vchSubject | MEETINGS > Subject | NO | Activities Comments | YES |  | STANDARD | REVIEW
87 | dCalendar | vchLocation | MEETINGS > Location | NO | Activities Comments | YES |  | STANDARD | REVIEW
88 | dAttendee | intAttendeeId | MEETINGS > To attendees | NO | Activities Comments | YES |  | STANDARD | REVIEW
89 | dAttendee |  | MEETINGS > Other attendees | NO | Activities Comments | YES |  | STANDARD | REVIEW
90 | dCalendar | vchCategoryName | MEETINGS > Category | NO | Activities Comments | YES |  | STANDARD | REVIEW
91 | dCalendar | vchNote | MEETINGS > In Calendar of | NO | Activities Comments | YES |  | STANDARD | REVIEW
92 |  |  | JOBS | YES |  | YES | links to Jobs | STANDARD | REVIEW
93 |  |  | SHORTLIST | YES |  | YES | links to JobApp | STANDARD | REVIEW
94 |  |  | INTERVIEWS | YES |  | YES | links to JobApp | STANDARD | REVIEW
95 |  |  | PLACEMENTS | YES |  | YES | links to JobApp | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.
Note on G3: CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated. All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope. Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required. -Andi Taufiq

## 4. Job Fields Mapping
Voyager Infinity to Vincere Fields Mapping (JOB) |  |  | COMPLETED
1 Custom Script = 200 USD one time fee
No | Voyager Infinity DB Table | Voyager Infinity DB Fieldname | Voyager Infinity UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | dJob | intJobId | Job ID | YES | Job External ID | YES | This is the record ID of Voyager. Vincere will need to migrate it and populate it to the Job External ID to identify the correct Job records to be migrated. | STANDARD | REVIEW
2 | dJob | intCompanyId | Company | YES | Company External ID | YES | Link to company | STANDARD | REVIEW
3 | dJob | intMainContactId | Contact | YES | Contact External ID | YES | Link to contacts | STANDARD | REVIEW
4 | N/A |  | Other Contacts | YES | Job Information: Hiring Line Manager | YES |  | STANDARD | REVIEW
5 | dJob | tintJobType | Job Type | YES | Job Type | YES | contract / perm job type = 0 or 1: Permanent, = 2 or others: contract | STANDARD | REVIEW
6 | dJob | tintJobStatusId | Job Status | YES | Custom Field > Job Status | YES | COMMENTED ON Open/Closed Open statuses / ACTIVE JOBS : • Open • Ongoing • On Hold • Partially Filled • Always Looking • Urgent • Speculative Closed statuses / INACTIVE JOBS: • Filled all places • Closed all places • Client closed job • Client cancelled • Client unsatisfied • Client unsuitable • Filled by other agency • Filled by client • Filled Internally • No Candidates Should we migrate the job with Closed statuses ? | CUSTOM | PRODUCTION
7 | dJob | bitSpecJob | Spec Job Flag | NO |  | YES | Can you spec a candidate to a Client without a role? AT: Yes you can. We call this Floating a Candidate. This means the client doesn't have any role but you want to send a great talent to be considered if in case there is a new role opened. | STANDARD | REVIEW
8 | dJob | tintSectorId | Sector | NO | INDUSTRY | NO |  | CUSTOM | PRODUCTION
9 | dJob | vchAlert | Alert | NO | NOTE | YES |  | STANDARD | REVIEW
10 | refJobTitle | vchJobTitleName | Job Title | YES | Custom Field > Job Classification | NO | Commented in Q&A | CUSTOM | PRODUCTION
11 | dJob | vchClientJobTitle | Client Job Title | YES | Job Title | YES |  | STANDARD | REVIEW
12 | dJob | vchClientRef | Client Ref | YES | Company External ID | YES | Commented in Q&A | STANDARD | REVIEW
13 | dJob | sintNumberOfPlaces | No of Places | YES | Headcount | YES |  | STANDARD | REVIEW
14 | dJobLocation | vchAddressLine1,2,3 | Job Locations | YES | NOTE | YES |  | STANDARD | REVIEW
15 | dJob | intCandidateReportsToId | Reports To | YES | NOTE / Hiring Manager / Custom Field > Reports To | NO | Commented in Q&A | CUSTOM | PRODUCTION
16 | lJobTitleJob | vchEssential | TITLES > E | NO | NOTE | YES |  | STANDARD | REVIEW
17 | dJob | intJobTitleId | TITLES > Job Title | NO | NOTE | YES |  | STANDARD | REVIEW
18 | dJob | datStartDate | Job Start Date | YES | NOTE | YES | Commented in Q&A | STANDARD | REVIEW
19 | dJob | bitASAP | Asap flag | YES | NOTE | YES | Commented in Q&A | STANDARD | REVIEW
20 | dJob | decBasicMinSalary | SALARY > Salary Min | YES | Salary from | YES |  | STANDARD | REVIEW
21 | dJob | decBasicMaxSalary | SALARY > Salary Max | YES | Salary to | YES |  | STANDARD | REVIEW
22 | dJob | decPackageMinSalary | SALARY > Package Min | NO | NOTE | YES |  | STANDARD | REVIEW
23 | dJob | decPackageMaxSalary | SALARY > Package Max | NO | NOTE | YES |  | STANDARD | REVIEW
24 | dJob | tintSalaryIntervalId | SALARY > Per Year / Month | NO | NOTE | YES |  | STANDARD | REVIEW
25 | dJob | decMinSalaryFeePercentage | SALARY > Fee % Min | NO | NOTE | YES |  | STANDARD | REVIEW
26 | dJob | decMaxSalaryFeePercentage | SALARY > Fee % Max | YES | Use Quick Fee Forecast' | YES |  | CUSTOM | PRODUCTION
27 | dJob | decMinSalaryFee | SALARY > Fee value Min | NO | Note | YES |  | STANDARD | REVIEW
28 | dJob | decMaxSalaryFee | SALARY > Fee value Max | NO | Note | YES |  | STANDARD | REVIEW
29 | dJob | decCapFeeAt | SALARY > Cap fee value Min | NO | NOTE | YES |  | STANDARD | REVIEW
30 | dJob | tintPayCurrencyId | SALARY > Pay Currency | YES | Currency Tab | YES |  | STANDARD | REVIEW
31 | dJob | tintChargeCurrencyId | SALARY > Charge Currency | NO | NOTE | YES |  | STANDARD | REVIEW
32 | dJob | vchDescription | Description | YES | Internal Job description | YES |  | STANDARD | REVIEW
33 | dJob | vchComments | Comments | YES | NOTE | YES |  | STANDARD | REVIEW
34 | lConsultantJob | intConsultantId | Consultants | YES | Job Owner | YES |  | STANDARD | REVIEW
35 | dJob | intPONumberId | PO | NO | NOTE | YES |  | STANDARD | REVIEW
36 | dPONumber | dValidFromDate | PO Valid From | NO | NOTE | YES |  | STANDARD | REVIEW
37 | dPONumber | dValidToDate | PO Valid To | NO | NOTE | YES |  | STANDARD | REVIEW
38 | dJob | intProjectCodeId | Project Code | NO | NOTE | YES |  | STANDARD | REVIEW
39 | lBenefitJob | sintBenefitId | Benefit | NO | NOTE | YES |  | STANDARD | REVIEW
40 | dJob | vchAlternateCode | Alternate Code | NO | NOTE | YES |  | STANDARD | REVIEW
41 | dJob | datReviewDate | Review Date | NO | NOTE | YES |  | STANDARD | REVIEW
42 | lEventJob | intEventId | EVENTS | YES | Activities - comment, info includes: - Event Date - Event Details - Event Actions - Logged by | YES | Inject as Comments in Activities tab | STANDARD | REVIEW
43 | N/A |  | TASKS | NO | Activities | YES | Activies page (seperate tab) - No data found | STANDARD | REVIEW
44 |  |  | SHORTLIST | YES | JOB APPLICATIONS | YES | Links to Job Application | STANDARD | REVIEW
45 |  |  | INTERVIEWS | YES | JOB APPLICATIONS | YES | Links to Job Application | STANDARD | REVIEW
46 |  |  | PLACEMENTS | YES | JOB APPLICATIONS | YES | Links to Job Application | STANDARD | REVIEW
IMPORTANT NOTE:
1 | Any fields that cannot be mapped to the Vincere CORE field, will be appended to the Note by default. CORE fields : https://docs.google.com/spreadsheets/d/1QjjAApVVI61Q-xKF0BtPjAWW_CP2DeMrLsdZaes0Vj8/edit?usp=sharing
2 | If any specific fields are to be mapped to specific Vincere NON-CORE field, this will be treated as CUSTOM FIELD mapping. This will be billable depending on what has been agreed in the Contract.
3 | CUSTOM FIELD mapping is excluded by default from the STANDARD Data Migration process. If this is required, the field mapping must be stated as such on the list above. The Type of Migration will then be marked as CUSTOM.
4 | CUSTOM FIELD mapping can be added at the end of Data Migrationt to the Production Live Site (Last Migratio Stage) and not the Review Site.
Note on G3: CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated. All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope. Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required. -Andi Taufiq

## 3. Candidate Fields Mapping
Voyager Infinity to Vincere Fields Mapping (Candidates) |  |  | COMPLETED
1 Custom Script = 200 USD one time fee
No | Voyager Infinity DB Table | Voyager Infinity DB Fieldname | Voyager Infinity UI Fieldname | Required ? | Vincere Field | VC CORE Fields ? | Comments | Type of Migration STANDARD / CUSTOM | Target System REVIEW / PROD
1 | iCapture Code | icapInboxItem | intICaptureCandidateId | NO | N/A | NO |  | CUSTOM | PRODUCTION
2 | Web Id | dCandidate | vchWebId | NO | N/A | NO |  | CUSTOM | PRODUCTION
3 | Candidate ID | dCandidate | intCandidateId | YES | External Id | YES | This is the record ID of Voyager. Vincere will need to migrate it and populate it to the Candidate External ID to identify the correct Candidate records to be migrated. | STANDARD | REVIEW
4 | Status | dCandidate | tintCandidateStatusId | YES | Note | YES |  | STANDARD | REVIEW
5 | Title | dPerson | vchJobTitle tintTitleId | YES | Title | YES | MR MRS MS MISS DR | STANDARD | REVIEW
6 | Consultants | lConsultantCandidate | intConsultantId | NO | Candidate Owners | YES | In order the ownership can be assigned, the value of the field must be showing email address of the consultant users. | STANDARD | REVIEW
7 | Forename |  | vchForename | YES | First Name | YES |  | STANDARD | REVIEW
8 | Middlename |  | vchMiddlename | YES | Middle Name | YES |  | STANDARD | REVIEW
9 | Surname |  | vchSurname | YES | Last Name | YES |  | STANDARD | REVIEW
10 | Known as |  | vchKnownAs | YES | Note | YES |  | STANDARD | REVIEW
11 | Address Line 1 | dCandidateAddress | vchAddressLine1 | YES | Location Address, Location Name | YES |  | STANDARD | REVIEW
12 | Address Line 2 | dCandidateAddress | vchAddressLine2 | YES | Location Address, Location Name | YES |  | STANDARD | REVIEW
13 | Address Line 3 | dCandidateAddress | vchAddressLine3 | YES | Location Address, Location Name | YES |  | STANDARD | REVIEW
14 | Town | dCandidateAddress | vchTown | YES | Town / City | YES |  | STANDARD | REVIEW
15 | County | dCandidateAddress | vchCounty | YES | State | YES |  | STANDARD | REVIEW
16 | Post Code | dCandidateAddress | vchPostcode | YES | Zip (Postal) code | YES |  | STANDARD | REVIEW
17 | Country | dCandidateAddress | sintCountryId | YES | Country | YES |  | STANDARD | REVIEW
18 | Date of Birth | dPerson | dDOB | YES | Date of Birth | YES |  | STANDARD | REVIEW
19 | Gender | dPerson | tintGenderId | YES | Gender | YES |  | STANDARD | REVIEW
20 | Marital Status | dPerson | tintMaritalStatusId | YES | Marital Status | YES |  | STANDARD | REVIEW
21 | Nationality | dPerson | sintNationality1Id | YES | Citizenship - Nationality | YES |  | STANDARD | REVIEW
22 | Nationality 2 | dPerson | sintNationality2Id | NO | N/A | NO |  | CUSTOM | PRODUCTION
23 | Nationality 3 | dPerson | sintNationality3Id | NO | N/A | NO |  | CUSTOM | PRODUCTION
24 | Nationality 4 | dPerson | sintNationality4Id | NO | N/A | NO |  | CUSTOM | PRODUCTION
25 | Country of Origin | dPerson | sintCountryOfOriginId | NO | Note | YES |  | STANDARD | REVIEW
26 | Ethnic Origin | dPerson | tintEthnicOriginId | NO |  | YES |  | STANDARD | REVIEW
27 | TELECOMS > Telecom Type | dCandidateTelecom | tintTelecomId | YES | Phone Type | YES | This will be used to determine the type of phone -refer from sTelecom | STANDARD | REVIEW
28 | TELECOMS > Value | dCandidateTelecom | vchValue | YES | Primary Phone, Mobile, Work Phone, Home Phone | YES |  | STANDARD | REVIEW
29 | TELECOMS > Description | dCandidateTelecom | vchDescription | NO | Note | YES |  | STANDARD | REVIEW
30 | LinkedIn Public URL | dPerson | vchLinkedInUrl | YES | LinkedIn | YES |  | STANDARD | REVIEW
31 | XING Public URL | dPerson | vchXingUrl | YES | Xing | YES |  | STANDARD | REVIEW
32 | Facebook Public URL | dPerson | vchFacebookProfileUrl | YES | Facebook | YES |  | STANDARD | REVIEW
33 | Twitter Profile URL | dPerson | vchTwitterProfileUrl | YES | Brief > Note | YES |  | STANDARD | REVIEW
34 | Notice | dCandidate | tintNoticePeriodIntervalId | YES | Brief > Note | YES |  | STANDARD | REVIEW
35 | Notice Menu | N/A |  | NO |  | NO |  | CUSTOM | PRODUCTION
36 | Availability | dCandidateAvailability |  | YES | Brief > Note | NO |  | STANDARD | REVIEW
37 | Candidate Type | N/A |  | NO |  | NO |  | CUSTOM | PRODUCTION
38 | Expected Rates > Perm Min | dCandidateExpectedRate | decMin | YES | Brief > Note | YES |  | STANDARD | REVIEW
39 | Expected Rates > Perm Max | dCandidateExpectedRate | decMax | YES | Brief > Note | YES |  | STANDARD | REVIEW
40 | Expected Rates > Perm Per Type | dCandidateExpectedRate |  | YES | Brief > Note | YES |  | STANDARD | REVIEW
41 | Expected Rates > Cont Min | dCandidateExpectedRate | decMin | YES | Brief > Note | YES |  | STANDARD | REVIEW
42 | Expected Rates > Cont Max | dCandidateExpectedRate | decMax | YES | Brief > Note | YES |  | STANDARD | REVIEW
43 | Expected Rates > Cont Per Type | dCandidateExpectedRate |  | YES | Brief > Note | YES |  | STANDARD | REVIEW
44 | Expected Rates > Temp Min | dCandidateExpectedRate | decMin | YES | Brief > Note | YES |  | STANDARD | REVIEW
45 | Expected Rates > Temp Max | dCandidateExpectedRate | decMax | YES | Brief > Note | YES |  | STANDARD | REVIEW
46 | Expected Rates > Temp Per Type | dCandidateExpectedRate |  | YES | Brief > Note | YES |  | STANDARD | REVIEW
47 | Expected Rates > Currency | dCandidate | tintCurrencyId | YES | Brief > Note | YES |  | STANDARD | REVIEW
48 | Based In | dCandidate | vchBasedIn | NO | Brief > Note | YES |  | STANDARD | REVIEW
49 | Preferred Location | dCandidate | vchPreferredLocation | YES | Brief > Note | YES |  | STANDARD | REVIEW
50 | Relocate Flag | dCandidate | bitRelocate | NO | Brief > Note | YES |  | STANDARD | REVIEW
51 | Transport Flag | dCandidate | bitTransport | NO | Brief > Note | YES |  | STANDARD | REVIEW
52 | Comments | dCandidate | vchComment | YES | Candidate Activity Comments | YES |  | STANDARD | REVIEW
53 | Summary | dCandidate | vchSummary | YES | Candidate Notes | YES |  | STANDARD | REVIEW
54 | SOURCES > Source | dCandidateSource | intCandidateSourceId | NO | Candidate Source | NO | List of Candidate Source name needs to be registered first in the Production Site. This would require CUSTOM SCRIPTS mapping. | CUSTOM | PRODUCTION
55 | SOURCES > Type | dCandidateSource | sintSourceId | NO | Candidate Source | NO |  | CUSTOM | PRODUCTION
56 | SOURCES > Details | dCandidateSource | vchFreeText | NO | Candidate Source | NO |  | CUSTOM | PRODUCTION
57 | SOURCES > Added | dCandidateSource | sdtAdded | NO | Candidate Source | NO |  | CUSTOM | PRODUCTION
58 | ATTRIBUTES > Score | lAttributeCandidate | sintAttributeScoreId | NO | N/A | NO |  | CUSTOM | PRODUCTION
59 | ATTRIBUTES > Attributes | lAttributeCandidate | intAttributeId | NO | SKILLS | NO | List of Attributes need to be populated first on the Production Site. This is considered as CUSTOM FIELDS mapping. | CUSTOM | PRODUCTION
60 | ATTRIBUTES > Hits | lAttributeCandidate | sintHits | NO | N/A | NO |  | CUSTOM | PRODUCTION
61 | QUALS & CERTS > Qual/Cert | lQualificationCandidate | intQualificationId | NO | Education Summary | YES | Text of Qualification will be migrated to the Qualification field as a Free Text field. - Inject to Qualification field in Education tab | STANDARD | REVIEW
62 | QUALS & CERTS > Type | lQualificationCandidate | intQualificationTypeId | NO | Education Summary | YES |  | STANDARD | REVIEW
63 | QUALS & CERTS > Level | lQualificationCandidate | intQualificationLevelId | NO | Education Summary | YES |  | STANDARD | REVIEW
64 | QUALS & CERTS > Expiry | lQualificationCandidate | datExpiryDate | NO | Education Summary | YES |  | STANDARD | REVIEW
65 | QUALS & CERTS > Review | lQualificationCandidate | datReviewDate | NO | Education Summary | YES |  | STANDARD | REVIEW
66 | QUALS & CERTS > Ref | lQualificationCandidate | vchReferenceNumber | NO | Education Summary | YES |  | STANDARD | REVIEW
67 | JOB TITLES > Job Title | licapJobTitleCandidate | intJobTitleId | YES |  | YES |  | STANDARD | REVIEW
68 | JOB TITLES > Hits | licapJobTitleCandidate | sintHits | YES |  | YES |  | STANDARD | REVIEW
69 | EMP HISTORY > Company Name | dWorkHistory | vchCompanyName | YES | Employment History > Company name | YES | WorkHistory | STANDARD | REVIEW
70 | EMP HISTORY > Job Title | dWorkHistory | vchJobTitle | YES | Employment History > Job Title | YES | WorkHistory | STANDARD | REVIEW
71 | EMP HISTORY > Line Manager | dWorkHistory | intLineManagerId | YES |  | YES |  | STANDARD | REVIEW
72 | EMP HISTORY > Start Date | dWorkHistory | datStartDate | YES | Employment History > Date Range From | YES | WorkHistory | STANDARD | REVIEW
73 | EMP HISTORY > End Date | dWorkHistory | datEndDate | YES | Employment History > Date Range To | YES | WorkHistory | STANDARD | REVIEW
74 | EMP HISTORY > Salary Currency | dWorkHistory | tintSalaryCurrencyId | YES |  | YES |  | STANDARD | REVIEW
75 | EMP HISTORY > Salary | dWorkHistory | decSalary | YES | Employment History > Employee experience with the Employer | YES | WorkHistory | STANDARD | REVIEW
76 | EMP HISTORY > Salary Per | dWorkHistory | tintSalaryPeriodId | YES | Employment History > Employee experience with the Employer | YES |  | STANDARD | REVIEW
77 | EAA Flag | dCandidate | bitEAA | NO | Brief > Note | YES |  | STANDARD | REVIEW
78 | Right to Work Flag | dCandidate | bitRightToWork | NO | Brief > Note | YES |  | STANDARD | REVIEW
79 | CV Name | dCandidateCV | vchCVName | YES | Files | YES |  | STANDARD | REVIEW
80 | CV File | dCandidateCV | vchFileType | YES | Files | YES | File Type will be determined from the File extension of the filename not from this field.. | STANDARD | REVIEW
81 | CV Formatted Flag | dCandidateCV | bitFormatted | NO | N/A | NO |  | CUSTOM | PRODUCTION
82 | CV Default Flag | dCandidateCV | bitDefault | NO | N/A | NO |  | CUSTOM | PRODUCTION
83 | CV Received Date | dCandidateCV | dtInserted | NO | Files > Created Date | NO | To be appended to File name | CUSTOM | PRODUCTION
84 | Source | dCandidateSource | intCandidateSourceId | NO | Candidate Sources | NO |  | CUSTOM | PRODUCTION
85 | Active Call Backs Due Date | dCandidateCallBack | datCallBackDate | YES | Candidate Activity Comments | YES |  | STANDARD | REVIEW
86 | Active Call Backs For | dCandidateCallBack | tintCallBackTypeId | YES | Candidate Activity Comments | YES |  | STANDARD | REVIEW
87 | Active Call Backs Details | dCandidateCallBack | vchCallBackDetail | YES | Candidate Activity Comments | YES |  | STANDARD | REVIEW
88 | Festive greetings card flag | dCandidate | bitFestiveGreetingsCard | NO | N/A | NO |  | CUSTOM | PRODUCTION
89 | Emails |  |  | YES | Candidate Activity Comments | YES | Email body is not stored in the database, only email subject can be migrated. | STANDARD | REVIEW
90 | Note: Get additional fields: - Current job title and company from dPersonCurrentEmployment |  |  | YES |  | YES | Commented in Q&A | STANDARD | REVIEW
Note on G3: CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated. All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope. Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required. -Andi Taufiq

## 5. Job Application Stage Mappin
No | Voyager Infinity Stage | Required ? | Vincere Stage | Comments
|  | YES | SHORTSLITED
|  | YES | SENT
|  | YES | FIRST_INTERVIEW
|  | YES | SECOND_INTERVIEW
|  | YES | OFFERED
|  | YES | PLACED
|  | NO | ONBOARDING | SM: we dont have this field in Voyager.
Note: At this stage any REJECTED state will not be mapped to REJECTED status in Vincere due to the limitation on the available tool. So all REJECTED candidates will be moved to the PENDING state of the SHORTLISTED stage.
Job Types
No | Voyager Infinity Employment Type | Required ? | Vincere Job Type | Comments
| Permanent | YES
| Contract | YES
| Fixed term | YES
| Temporary | NO |  | No data

## 6. CUSTOM FIELD Industry Mappin
Industry Mapping
Note: Industry mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Voyager Infinity Business Sector Field | Required ? | Vincere Industry Field | Comments
1 |  | N | TBD | TBD
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
23
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
25
27
41
42
43
44
45
46
47
48
49
50
51
52
53

## 7. CUSTOM FIELD Functional Exp
Functional Expertise Field Mapping
Note: Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Voyager Infinity Category Field | Required ? | VINCERE FUNCTIONAL EXPERTISE FIELD | VINCERE SUB FUNCTIONAL EXPERTISE FIELD | Comment
| TBD | N | TBD | TBD

## 8. CUSTOM FIELD Sub Functiona
Sub Functional Expertise Field Mapping
Note: Sub Functional Expertise mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Voyager Infinity SKILLS Field | Required ? | Vincere Functional Expertise Field | Vincere Sub Functional Expertise | Comment
1 | TBD | N | TBD | TBD
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 9. CUSTOM FIELD Candidate Sour
Candidate Source Field |  | Commented
Note: Candidate Source mapping is part of Custom Field Mapping process which will be done only after the final migration to Production is completed.
No | Voyager Infinity SOURCE Field values | Required ? | Vincere Candidate Source values | Comment
| We do currently track candidate source against placements for ROI on advertising tracking. We can either migrate current data or just go forward from now. It is not critical... | Preferably but not critical | TBD | TBD

## CUSTOM SCRIPT SUMMARY
List of required CUSTOM SCRIPTS
No | Category | System of Origin Field | Vincere Field | Target Instance | Comments | Count
[5 empty] | Total : | 0
NOTES:
1 | Read here on how we determine STANDARD / CUSTOM migration : https://drive.google.com/file/d/19psV-v9h5N8Z9SyJRhlVbyLdLqHKWvI4/view?usp=sharing
2 | CORE fields are the fields where it can be migrated to the similar fields in Vincere. It means Vincere has the corresponding fields AND it can be migrated.
3 | All CORE fields can be migrated. NON-CORE fields can only be migrated to NOTES as part of the STANDARD basic migration scope.
4 | Any NON-CORE fields that are required to be migrated to other than NOTES field, would need a CUSTOM migration which would need to be executed in the Final Production Live Site and the work will be billable.
5 | CUSTOM Migration is calculated based on the number of CUSTOM scripts required. The cost is 200 USD / Custom Script required.